## 25-D2070A 11 18 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | V3 GATE LLC | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 25-D2070 | [6 empty] | OR
Status Update ID | 25-D2070A | [5 empty] | Invoice Number
T3334
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 5% | X | 36144.73 | = | 1807.24 | 1807.24 | - | 0 |  | 0 | = | 1807.24
2 | 0% | X | 6024.11 | = | 0 | 0 | - | 0 |  | 0 | = | 0
3 | 0% | X | 74371.88 | = | 0 | 0 | - | 0 |  | 0 | = | 0
4 | 0% | X | 29748.75 | = | 0 | 0 | - | 0 |  | 0 | = | 0
5 | 0% | X | 23799.01 | = | 0 | 0 | - | 0 |  | 0 | = | 0
6 | 0% | X | 22311.56 | = | 0 | 0 | - | 0 |  | 0 | = | 0
7 | 0% | X | 44623.13 | = | 0 | 0 | - | 0 |  | 0 | = | 0
|  |  | 237023.17 |  | 1807.24 | 1807.24 |  | 0 |  | 0 |  | 1807.24
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date