## 25-D0774A 11 18 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | INNOSYS INC | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 25-D0774 | [6 empty] | OR
Status Update ID | 25-D0774A | [5 empty] | Invoice Number
379405
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 90% | X | 25000 | = | 22500 | 22500 | - | 0 |  | 0 | = | 22500
2 | 80% | X | 59204.4 | = | 47363.52 | 47363.52 | - | 0 |  | 0 | = | 47363.52
3 | 20% | X | 20000 | = | 4000 | 4000 | - | 0 |  | 0 | = | 4000
|  |  | 104204.4 |  | 73863.52 | 73863.52 |  | 0 |  | 0 |  | 73863.52
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date