## 25-C0200N 11 20 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | THE RESEARCH FOUNDATION | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 25-C0200 | [6 empty] | OR
Status Update ID | 25-C0200N | [5 empty] | Invoice Number
K7103
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 800000 | = | 800000 | 800000 | - | 0 |  | 796000 | = | 4000
2 | 25% | X | 800000 | = | 200000 | 200000 | - | 0 |  | 73333.33 | = | 126666.67
|  |  | 1600000 |  | 1000000 | 1000000 |  | 0 |  | 869333.33 |  | 130666.67
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date