## 22-C0405M 11 20 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | OCEM ACQUISITION CORP | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 22-C0405 | [6 empty] | OR
Status Update ID | 22-C0405M | [5 empty] | Invoice Number
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 87177.9 | = | 87177.9 | 87177.9 | - | 0 | - | 87177.9 | = | 0
2 | 100% | X | 58118.6 | = | 58118.6 | 58118.6 | - | 0 | - | 58118.6 | = | 0
3 | 100% | X | 87177.9 | = | 87177.9 | 87177.9 | - | 0 | - | 87177.9 | = | 0
4 | 100% | X | 17525.6 | = | 17525.6 | 17525.6 | - | 0 | - | 17525.6 | = | 0
5 | 100% | X | 11533.7 | = | 11533.7 | 11533.7 | - | 0 | - | 11533.7 | = | 0
6 | 100% | X | 14529.65 | = | 14529.65 | 14529.65 | - | 0 |  | 14529.65 | = | 0
7 | 100% | X | 14529.65 | = | 14529.65 | 14529.65 | - | 0 |  | 14529.65 | = | 0
8 | 100% | X | 290479.5 | = | 290479.5 | 290479.5 | - | 0 |  | 290479.5 | = | 0
9 | 100% | X | 193653 | = | 193653 | 193653 | - | 0 |  | 193653 | = | 0
10 | 100% | X | 290479.5 | = | 290479.5 | 290479.5 | - | 0 |  | 290479.5 | = | 0
11 | 100% | X | 96826.5 | = | 96826.5 | 96826.5 | - | 0 |  | 96826.5 | = | 0
12 | 100% | X | 48413.25 | = | 48413.25 | 48413.25 | - | 0 |  | 28604 | = | 19809.25
13 | 0% | X | 48413.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
14 | 100% | X | 60269.18 | = | 60269.18 | 60269.18 | - | 0 |  | 60269.18 | = | 0
15 | 0% | X | 6012.8 | = | 0 | 0 | - | 0 |  | 0 | = | 0
|  |  | 1319127.18 |  | 1270713.93 | 1270713.93 |  | 0 |  | 1250904.68 |  | 19809.25
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date