## 24-C0164F 11 20 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | ANDERSON & DAHLEN INC. | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 24-C0164 | [6 empty] | OR
Status Update ID | 24-C0164F | [5 empty] | Invoice Number
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 243160 | = | 243160 | 243160 | - | 0 |  | 243160 | = | 0
2 | 100% | X | 121580 | = | 121580 | 121580 | - | 0 |  | 121580 | = | 0
3 | 100% | X | 486320 | = | 486320 | 486320 | - | 0 |  | 486320 | = | 0
4 | 0% | X | 121580 | = | 0 | 0 | - | 0 |  | 0 | = | 0
5 | 100% | X | 243160 | = | 243160 | 243160 | - | 0 |  | 243160 | = | 0
6 | 100% | X | 135665 | = | 135665 | 135665 | - | 0 |  | 0 | = | 135665
7 | 70% | X | 38325 | = | 26827.5 | 26827.5 | - | 0 |  | 0 | = | 26827.5
|  |  | 1389790 |  | 1256712.5 | 1256712.5 |  | 0 |  | 1094220 |  | 162492.5
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date