## 25-C0005C 11 20 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | IMEC VZW INTERUNIVERSITAI | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 25-C0005 | [6 empty] | OR
Status Update ID | 25-C0005C | [5 empty] | Invoice Number
T3334
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 200000 | = | 200000 | 200000 | - | 0 |  | 200000 | = | 0
2 | 100% | X | 200000 | = | 200000 | 200000 | - | 0 |  | 200000 | = | 0
3 | 40% | X | 200000 | = | 80000 | 80000 | - | 0 |  | 0 | = | 80000
4 | 0% | X | 199862.8 | = | 0 | 0 | - | 0 |  | 0 | = | 0
5 | 0% | X | 250000 | = | 0 | 0 | - | 0 |  | 0 | = | 0
6 | 0% | X | 250000 | = | 0 | 0 | - | 0 |  | 0 | = | 0
7 | 0% | X | 250000 | = | 0 | 0 | - | 0 |  | 0 | = | 0
8 | 0% | X | 129336.7 | = | 0 | 0 | - | 0 |  | 0 | = | 0
|  |  | 1679199.5 |  | 480000 | 480000 |  | 0 |  | 400000 |  | 80000
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date