## Sheet1
Work package | Institute | Expenditure type | Year 1 ($k) | Year 2 ($k) | Total ($k) | Group by: | Work package | Year 1 ($k) | Year 2 ($k) | Total ($k)
Permanent magnet construction | BNL | Hardware | 200 | 50 | 250 |  | Permanent magnet construction | 300 | 100 | 400
|  | Labour | 100 | 50 | 150 |  | Magnet measurement, tuning/shimming and radiation tests | 200 | 400 | 600
Magnet measurement, tuning/shimming and radiation tests | BNL | Hardware | 50 | 100 | 150 |  | Lattice design and tracking studies | 300 | 300 | 600
|  | Labour | 50 | 100 | 150 |  | CEBAF vacuum chamber size studies | 200 | 200 | 400
| Cornell | Hardware | 50 | 100 | 150
|  | Labour | 50 | 100 | 150 |  | Institute | Year 1 ($k) | Year 2 ($k) | Total ($k)
Lattice design and tracking studies | BNL | Labour | 100 | 100 | 200 |  | BNL | 500 | 400 | 900
| Cornell | Labour | 100 | 100 | 200 |  | Cornell | 200 | 300 | 500
| JLAB | Labour | 100 | 100 | 200 |  | JLAB | 300 | 300 | 600
CEBAF vacuum chamber size studies | JLAB | Hardware | 100 | 100 | 200
|  | Labour | 100 | 100 | 200 |  | Expenditure type | Year 1 ($k) | Year 2 ($k) | Total ($k)
|  | Total ($k) | 1000 | 1000 | 2000 |  | Hardware | 400 | 350 | 750
[7 empty] | Labour | 600 | 650 | 1250
Initial guess logic was: most people don't want less than 100k in any of these cells, otherwise work done is marginal
Permanent magnet construction will be front-loaded for hardware to buy permanent magnet material, which is expensive right now
This can be balanced by making the magnet testing be larger in year 2 (as we'll need a magnet to measure first)