A staged upgrade scenario
Jay Benesch
1 May 2022

1. During the next decade, at a rate of four per year, refurbish all C25 modules into C50 or C75 modules with input QL such that 8 kW klystrons will drive ~720 µA. Goal 1300 MeV/linac with 100 MeV headroom at that current.
2. Build a 123 MeV electron/positron source in the LERF vault and a 650+ MeV capable transfer line from LERF to the SL stub, along the SL, along the west arc and inject into the NL with dispersion suppression. Magnets hanging from ceiling for the most part. Buncher cavities may be needed along the ~800 m line to maintain longitudinal emittance. Reversing switches for all dipoles, requiring new buildings. Positron physics for some years. Present injector intact.
3. If a layout can be made within LERF, add a parity-capable chopped electron injector and a ring to take the electrons (and perhaps positrons) up to 650 MeV. If space is not sufficient, scrap the positron source. Test 650 MeV beam delivery to a 100 kW beam dump in SL stub.
4. Warm up CEBAF, selling helium back to vendor. Improve linac girders with triplets and better diagnostics. Replace all linac gate valves and o-rings. Plasma processing of C100s if that has proved useful. Replace all CEBAF spreader/recombiner magnets; discard pass 1 arc magnets and all stands; move pass 2-5 magnets up one notch, leaving fifth pass empty on new stands. With CM improvement of (1), 11 GeV to A/B/C and 12 GeV to D with four passes.
5. Install fifth pass spreader/recombiner and extraction magnets and RF separators; pass 5 FFA (four passes within); new magnets in all the Hall lines. New beam dumps. New Environmental Assessment. If (3) retained positron capability, two-aperture FFA permanent magnets. If not, one aperture. Final energy ~20 GeV. Eight passes through linacs so 45 µA each to A and C at full energy would be possible with 720 µA capability in linacs. Since this is 900 kW each at 20 GeV it may be that the beam dumps would not need to be replaced; they've been evaluated to 16 GeV.

Impact on CEBAF operation of (1-3) would be small although the transfer line probably would require more than a three month down plus commissioning time. The political problem is that (4) does not add any new physics capability. It simply maintains capability while one awaits approval on (5). In current dollars, step (1) ~$100M including LLRF and klystrons. Steps (2) and (3) might stay under $200M each. Steps (4) and (5) probably do not.

Acknowledgments:
Andrei Seryi suggested hanging magnets from ceiling in an email exchange.
Discussions with Katheryne Price helped focus my ideas.