## Sheet1
Date | Shift | Hall Status | Hall Details | Experiment Status | Shift Status | Notes
2023-02-22 | Owl
2023-02-22 | Day | Controlled/Beam Permit | Return to Production | Ready, Plan is production | Both ON | 45 C on Fringe then stop
2023-02-22 | Swing | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-23 | Owl | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-23 | Day | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-23 | Swing | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-24 | Owl | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-24 | Day | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-24 | Swing | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-25 | Owl | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-25 | Day | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-25 | Swing | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-26 | Owl | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-26 | Day | Beam Permit | Production | Ready, Plan is production | Both ON
2023-02-26 | Swing | Beam Permit | Production finish up, Moller
2023-02-27 | Owl | Beam Permit | Moller | ~1 shift
2023-02-27 | Day | Beam Permit | Target Studies | ~1 shift
2023-02-27 | Swing | Controlled/Beam Permit | Optics | we need sieve in which needs access |  | Will need escorted access and Techs
2023-02-28 | Owl | Controlled/Beam Permit | Optics. Potentially start Target at 7am | Depends on RadCon
2023-02-28 | Day | Controlled | Start target install | Take sieve out. Will require access |  | Will need sweep and Radcon Support
2023-02-28 | Swing | Controlled | Target Install
2023-03-01 | Owl | Controlled | Target Install
2023-03-01 | Day | Controlled | Target Install
2023-03-01 | Swing | Controlled | Target Install