Here are best guesses for upcoming work  
  
Finish Isotope 1X shielding by 9/5  
  
Remove concrete shield blocks 9/5/2019  
  
Warm up LCLS-II CMs - 9/6/2019 (weekend)  
  
Re-commission drive laser by 9/15/2019  
  
Disconnect 2 LCLS-II CMs complete by 9/30/2019  
  
Hold ERR readiness review before 9/30/2019 – need EH&S Chapter 3130 signed off! (RSAD – Keith)

LOD – need update/signoff – we use old version  
  
Remove both LCLS-II CMs 10/1/2019  
  
Re-install concrete shield blocks week of 10/1  
  
Run LERF CW to 1G dump (3 days?) week of 10/7 - dependent on Cryo turbine speed reduction experiments   
  
Run Isotope 1 kWatt irradiation week of 10/14 – setup + beam on target 4 shifts

Run 5 kWatt isotope before May 2020 shutdown – setup + beam on target 4 shifts  
  
No answer on if any more LCLS-II CMs will be installed prior to HE upgrade (May 2021)