## Slide 1: Isotope Production Update Sept. 30, 2020
Kevin Jordan
+1-757-876-1742

## Slide 2: Recent Activities
Sept. 14 – 18
  LERF was run for isotope irradiations
Sept. 23
  Shield blocks were removed from the LERF truck ramp
Sept. 28
  LCLS-II CM20 was removed from the LERF and transported to the test lab
Daily
  Gamma spectroscopy performed on the irradiated Gallium sample
  Calibration of temperature sensors

## Slide 3: Things that need attention
Quarter CM cavity #3 HPA still tries on crowbar
Remove clean room from LERF vault and deliver to test lab
Extend side cooling plates on base

## Slide 4: 1kW THERMAL ANALYSIS FLUKA (SIDE PLATE EXTENSION)
JOE GUBELI
CURRENT SIDE PLATES
EXTENDED SIDE PLATES

## Slide 5: Future Activities
Week of October 12
  ERR Review for 5 kwatt irradiation
Week of October 26
  Reinstall shield blocks
November 9 – 12
  Re-run “Stack' arrangement using metallic Ga71 (1 hour, 100 watts)
  Run solid block of graphite to validate temperatures (~20 minutes, 5 kw)
  Run graphite crucible with natural occurring Gallium for 30 hours, this sample would not leave JLab - gamma spec done by RadCon to validate Fluka model
January 11 – 14
  Possible “Stack” exposure w/metalic Ga71 to refine Fluka results
  Run naturally occurring Gallium at 5 kw
May (Depends on CHL status)
  Run new 50 kw target at 5 kw to validate design & model