## Slide 1: Isotope 5kW Irradiation

## Slide 2: Plan week of Jan 4 – 10, 2021
Resuscitate & hot checkout LERF Jan 6-8,
  Confirm survey & alignment (pacing item for lockup)
  Install ¼ CM #3 solenoid power supply – still in progress
  Commission 1X box power supply – nearly finished, electricians are connecting 480 now…
Wednesday 1/6 afternoon lockup (power permit)
  Test 1/4 CM – tune all SRF cavities
  Text 1X box supply
Thursday ~9:00 lockup
  PSS certification ¼ #3 + 1X box power supply
Friday ~10:00 lockup (there will be accesses during the day)
  MPS certification
  SRF soaking
  HCO…

## Slide 3: Plan for exposure
Monday 1/11/2021 Restore 32 MeV beam (day & swing)
Tuesday 1/12/2021
  Carry out 1 hour calibration run at ~100 W on foils stack (Vanadium, Gallium 71, & Nickel)
  Carry out 1 hour test irradiation on solid graphite block@ 5kW on Tuesday afternoon Jan 12
    Confirm photo before & after exposure + check max temperature and instrumentation
Wednesday 1/13/2021
  Initiate 34 hour run with liquid gallium in graphite crucible @5kW
Stop run on Thursday evening Jan 14
  Install RadCon lock on hutch
Open hutch for quick inspection on Monday Jan 18
Remove crucible on Monday Feb 1 after 18 days cooldown

## Slide 4: Instrumentation
Beamline has standard instrumentation: BPMs, profile monitors, etc.
The target is indirectly cooled by LCW; flow rate and inlet and outlet temperatures will be monitored
Thermocouples will be attached to the crucible to monitor temperatures during and after irradiation
Radiation levels outside the vault will be monitored during the irradiation
Radiation levels next to the hutch will be monitored during cool-down
When the hutch is opened to remove the crucible, a radiation monitor will be introduced into the hutch to monitor cool-down of the radiator, target raft and SEG blocks
Ozone will be monitored in the return air plenum