# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of March 25-31, 2016

Issues:  Some material remains to be delivered. Q3 funding is delayed.

Accomplishments this week:

Continue to push BCRs, EACs

Held multiple PRRs, End lever tuners and Cold Compressors, and received approvals

Collected P6 progress, input, process and review to come next week.

Upcoming Activities:

# Weekly Reporting

WBS 1.04.6 JLAB Cryomodules

Week of March 25-31, 2016

Issues: JLab pCM schedule is driven by the availability of parts including a completed GHRP assembly.  Project schedule driven by production cavity delivery schedule – need to recover float.

Accomplishments this week:

The following list of BCRs have been discussed with the SM: Production Tuner Schedule, pCM Cancellation Coils (status: proceed as of 2/25), production CM Cancellation Coils (in preparation) and Beamline Bellows / Spools Cost and Schedule (status: developing P6 what-if file).  Need to consider how to handle cavity acceleration incentives via BCR or other mechanism.

EAC for pCM is being prepared for presentation at CCB in April.

Cavity Procurement

Actively working cavity production schedule issues in order to recover schedule float by accelerating vendor delivery rates.  Current P6 what-if reflects JLab’s best estimate showing significant negative float.

RI has been contracted to provide 16 cavities – 8 in early July and 8 in early August.  Additionally RI had provided a proposal for acceleration of all production cavities.  We are currently negotiating with RI to pull more cavities forward in time.

ZANON provided an updated delivery schedule that is being reviewed.  It does not contain any acceleration proposal. We have developed a counter proposal for ZANON’s review.

RI and ZANON have first article production is underway.

Both vendors have materials suitable for first article production.  Currently there are no customs issues related to materials.

Remainder of HOM housings and rods, inadvertently omitted from FNAL shipment to DESY, will be shipped from FNAL as an expedited shipment.

Remaining tube materials from ATI are being inspected at FNAL and will be shipped upon completion, expected mid-April.  QCR on connecting tubes dispositioned – three tubes returned to ATI due to dimensional issues.  QCR on short tubes awaiting disposition – at least three tubes unacceptable; another has a dent.

Remaining cell material (39%) has been inspected at DESY and is expected to ship to both companies in Mid-April.  Vendors have 61% of total materials in-hand.

DESY colleagues plan to visit RI for to refurbish CTM in early April.  Visit to ZANON is pending negotiations between DESY & Zanon.  JLab has given ZANON approval to proceed with refurbishment activities.

Cavity vendor visit planning is on-going – tentative dates are 10-19 May to ZANON and RI respectively.  Agenda is being developed.

Cavity string assembly: As of Wednesday evening, small leaks have been sized, string has been vented is being disassembled.   Cavity AES035 will be re-tuned to ensure it meets cold frequency target.  Cavity components will be inspected and re-cleaned.  Expect re-assembly of first cavity on rail by end of next week.

Modification of parts and assembly of UCM (GHRP) ongoing: 5K Cu straps are being installed, instrumentation in progress, heater assembly being built, upper cold mass supports installed and verified, GV support bracket fit up was modified, two-phase pipe sub-assemblies being welded, magnet tooling being fabricated, magnet modifications have been completed, assembly rail extension in machine shop.

T. Hiatt attended a meeting to discuss the SC magnet testing on both the test bench as well as in the CM.

Participated in Production End Lever Tuner PRR.  Need to have confirmation that design is complete as some minor corrections were provided to FNAL by JLab SOTR.

Initial planning is on-going for vendor visit to production VV manufacturer – tentatively late April.  JLab staff are planning a coordination meeting with FNAL colleagues in advance of the trip.

CMTF – The VVU panel has been installed. Cable tray installation is ~ 80% complete. All of the RF circulators have been tested successfully up to 3.8 kW in SW mode. Hardline Coax installation (~33% complete) awaits arrival of SSAs to continue installation in 3rd floor SSA area.

QUALITY

- Working on the LCLSII Significant NCR Dashboard.  The first one is due to SLAC by April 5, 2016 from the individual partner labs.  In the QA Coordination meeting with Fermilab last week, we discussed the process, expectations and approach in completing the Dashboard form.

- Also in the QA meeting with Fermilab:

  - Jamie Blowers provided a demo on their process of material traceability.  In particular, a Kit List is the key document that ties in the bulk or batch materials to the Routing Form System from where the information on history and material pedigree are kept.  For batched materials, such as nuts, bolts, washers, clamps, & etc., traceability is maintained if and only if those individual pieces are kitted to an assembly through the use of the Kit List.

  - We discussed the topic of Suspect Counterfeit Items and the management approach by each lab.  The general approach and processes between Fermilab and JLab appear to be very similar.

  - JLab provided an update to Fermilab on the status of our ACS Table.  The ones that needed feedback from Fermilab were identified.

- Participated in the PRR for the end lever tuner.

Upcoming Activities:

- Timergali to visit JLab to support cavity re-tuning plans, 6-7 April

- Visit FNAL to observe cryomodule alignment process April 2016

- Visit FNAL to observe tuner installation April 2016

- Vacuum Vessel Vendor Visit to China April 24-29, 2016

- Cavity Vendor Visit to Germany & Italy May 10-19, 2016

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of March 25-31, 2016

Issues: 4.5K Cold Box PDR Action Items, Warm Helium Compressor CDR Readiness

Accomplishments this week:

A PRR for the cryoplant CP1 & CP2 2K cold compressors was held at JLab on March 30.  JLab has received approval to move ahead with the procurement following the review.

The 4.5K Cold Box PDR was held at JLab on March 10.  Major comments from reviewers are currently being addressed by the vendor with additional comments to be transmitted by April 31.

Warm helium compressor skid frame weldments are underway at the vendor shop.  A planned visit to the vendor facilities is planned for April 4-5 to review progress is preparation of the planned CDR on April 25th.

Specifications for the warm helium oil removal vessels, gaseous helium storage vessels, and final charcoal vessel are being circulated for final review.  JLab has received comments from reviewers and these are being addressed.

P&IDs are being continuing to be updated for CP2.

A planned visit to meet with the 4.5K cold box and sub vendor (PHPK) is being planned for April 13.  Topics of discussion include status of completion of PDR action items, general arrangement drawings and interfaces for the cold boxes, MLI welding protection, and cryogenic cold box valves (PHPK valves).

The compressor/cold box room cooling water piping design is underway.

Substantial progress was made on the preliminary design of the LN2 transfer lines and associated P&ID drawing.

QUALITY

Bruce Lenzer (JLab QA) has joined the team to help coordinate specification requirements with the various cryoplant vendors.

Upcoming Activities:

Warm Helium Compressor Visit,  4 April 2016

4.5K Cold Box Vendor Visit, 13 April 2016

Warm Helium Compressor CDR, 25 April 2016

# Weekly Reporting

WBS 1.02.03.05.12 LLRF

Week of March 25-31, 2016

Issues:  None

Accomplishments this week:

JLAB

LLRF Coordination/Documentation:

  - Worked with JLAB people to finalize the CMTF tests with LLRF.

  - BMB7 FPGA board is in the mail to JLAB.

- Resonance/Stepper Motor Board:

  - Stepper board mods are complete ready to go out for manufacture.

  - Chassis power boards and FMC breakout should be through design(CAD) next week.

  - Resonance chassis in design, we hope to have the drafts next week.

- Interlock Board/Chassis:

  - FEM: Board has been sent out for manufacture.

  - Temp board mods are being reviewed should go out for manufacture Monday.

- Common Power Supply/Chassis:

  - Chassis: We are going with the JLAB chassis vendor.

  - PS Chassis front panels are done. We have begun mounting the PS’s on the bottom plate.

- CMTF

  - Issue with electrician availability. They are supporting higher priority tasks.

  - Cable Tray: This is done.

  - Documentation: System block diagram is being updated weekly.

  - SSA EPICS interface work continues.

Upcoming Activities:

- JLAB:

  - Continue prototype tests and assembly (resonance, interlocks, power supply)

  - CMTF: Continue working on documentation, installation and instrumentation.

  - Resonance chassis tests with FNAL early May.

  - June 6-8 Rack assembly, test and shake down (JLAB)