Weekly Reporting

WBS 1.01.07 JLAB Management

Week of July 27-August 2, 2017

**Issues:**

**Accomplishments this week:**

Continued working with the 4.5K CB vendor to address delivery concerns.

Continued planning efforts regarding CM testing in LERF.

Preparing CM Schedule alignment BCR and 2+2 CMs BCR.

**Upcoming Activities:**

LERF Review August 3-4, 2017

CP Controls Review August 30, 2017

FAC at SLAC September 12-14, 2017

Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of July 27-August 2, 2017, 2017

**Issues**: Expect delays in cavity shipments due to lack of availability of PICs.

**Accomplishments this week:**

Preparations for LERF as a test LCLS II CM test bed review.

Preparing the pCM for shipping to FNAL on the 11th.

CM02 testing continues and planned to complete this week.

Last cavity for CM07 cavity string was qualified.

**QUALITY**: Submitted the monthly SNCR Dashboard to SLAC.

**Upcoming Travel:**

E. Zanon Vendor Oversight August (D. Gonella), September 2017 (C. Reece)

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of July 27-August 2, 2017

**Issues:**

**Accomplishments this week:**

Significant progress made toward completion of the GC installation package deliverables. JLab will submit documentation to SG & SLAC on Monday 8/7.

Received SLAC BIO authorization to proceed with the oil removal vessels anchorage.

Held PDR for the oil processor with PHPK. All required documentation was provided by the vendor and is under final review.

**QUALITY**: No update.

**Upcoming Travel/Reviews:**

CP Controls Specification Review August 30, 2017

FDRs are scheduled for the Purifier on Aug 9th and the LN2 dewar on Aug 10.

Weekly Reporting

WBS 1.02.03.05.12 LLRF

Week of July 27-August 2, 2017

**Issues:** None

**Accomplishments this week at JLab:** No report.