# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of October 4-10, 2018

Issues:

Need to converge on a shipping solution.

Upcoming Reviews:

Oct 2018	LERF Readiness Review

Nov 2018	CM Shipping Review

Dec 2018	DOE OPA Mini Review

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of October 4-10, 2018

Issues:

High performing cavities for CMs, the EZ furnace is broken and the path forward needs to be finalized.

QUALITY:  No report.

Upcoming Travel/Meetings:

- Shaker Table Vendor Visit Oct 12-15 (N. Huque)

- Vendor Visit to E. Zanon Nov 5-7 (A. Palczewski)

- QA/QC Workshop at MSU/FRIB (TBD, TBD date)

# Weekly Reporting

WBS 1.04.06 Cryomodules - LERF Conversion

Week of October 4-10, 2018

Issues:

This week JLab folks on-site at Eden Cryogenics to witness leak checking and pressure test.  This is now on critical path for early January cool-down.

Schedule for the 3 months is being populated & can be tracked at:

http://lerfboard.acc.jlab.org/board1.html

http://lerfboard.acc.jlab.org/board2.html

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of October 4-10, 2018

Issues:

- Reduction in baseline resources (Return funding to contingency; the top-down EAC) without corresponding reduction in scope of cryoplant commissioning.

- Resolution of structural interferences created during the design of the platforms and cable trays support systems (identified in 2017).

- Installation of the LN2 Dewar and helium ‘tank farm’ foundations.  The warm helium tanks have been in storage for several months awaiting completion of these supports.

- Engineering change request associated with the interface box design-build subcontract resulting in increased cost and schedule delay.

Accomplishments this week:

At SLAC for Cryoplant #2 4.5K Upper Cold Box lift and placement (see photo below); and also attending reassembly meeting.

Quality:

Addressed welding and machining issues that were documented and presented by Linde for the 2k Upper Cold Box plate unit 1 from Craft.  Working with vendor to prevent the same issues with unit 2 going to PHPK.

On Site Vendor (Craft) welding review for 2K Cold Box Top Plate Unit 2 and Cold Mass Assembly Fixture.

Upcoming Travel/Deliveries/Reviews:

- Reassembly of 4.5K Cold Box Meeting @SLAC		10-October-2018

- Delivery of Gas Helium Tanks (6) @SLAC			15-Oct-2018

- Delivery of first LN2 @SLAC					27-Oct-2018

- CryoPlant Software Development Review			TBD - November