# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of November 1-7, 2018

Issues:

Need to converge on a shipping solution.

Upcoming Reviews:

Nov 12	LERF Readiness Review

Nov 13-14	QA Audit Review

Nov 14	CryoPlant Software Development Review

Nov 2018	CM Shipping Review

Jan 2018	DOE OPA Mini Review

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of November 1-7, 2018

Issues:

- High performing cavities for CMs may be late due to potential schedule delays due to Zanon furnace issues.

- Current workload at JLab is being dominated by unplanned work compared with baseline including F5 shipping activities and inspection of J8 & J10 helium vessel bellows.  This will negatively impact cost and schedule performance indices.

F5 had a successful short trip 06-NOV to Richmond and back - no vacuum leaks.  Data for cavity 1 was analyzed showing .  Re-test planned for 08-NOV to verify instrumentation power supplies are reliable.  Long trip (3000 miles) is planned to start Friday 09-NOV and return to JLab on Monday 12-NOV.

Two CMs (J-02, J-04) are completed and ready for shipment.

One HOM BLA assembly was shipped to SLAC.  Awaiting report on shipment results.

QUALITY:

- Prepared for LCLS-II QA assessment November 13-14.  Developed agenda and discussion examples / topics with SRF leadership and LCLS-II personnel.

- LCLS Cryomodule Upper Cold Mass Assembly tooling was reviewed at Craft and accepted.

- LERF CRYO can installation beginning welding should start Wednesday.

- CRM012 low-pressure line RT scheduled for Sunday morning 11-11-18.

Upcoming Travel/Meetings:

Vendor Visit to E. Zanon Nov 5-7 (A. Palczewski)

# Weekly Reporting

WBS 1.04.06 Cryomodules - LERF Conversion

Week of November 1-7, 2018

Issues:

The cryo-can has been (finally) delivered and it has been moved into place, field fit joints are next.

Center clean room for beam tube connections assembly has begun.

Cryo-can in LERF.

Schedule for the next 3 months is being populated and can be tracked at:

http://lerfboard.acc.jlab.org/board1.html

http://lerfboard.acc.jlab.org/board2.html

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of November 1-7, 2018

Issues:

- Reduction in baseline resources (Return funding to contingency; the top-down EAC) without corresponding reduction in scope of cryoplant commissioning.

- Resolution of structural interferences created during the design of the platforms and cable trays support systems (identified in 2017).

- Engineering change request associated with the interface box design-build subcontract resulting in increased cost and schedule delay.

Accomplishments this week:

October Deliveries

All six Gas Helium Tanks have been delivered from storage and installed into the tank farm.

Both upper 4.5K cold boxes and all oil removal vessels are delivered & installed.

Quality:

JLab/SLAC staff at vendor site to review the final design of the interface boxes.

STL @SLAC to witness and consult on the start of the reassembly of the upper 4.5K cold box platforms.

A comprehensive risk mitigation plan and procedure was developed and distributed to address the potential contamination associated with the oil removal vessels.

Pressure tested 2 LCLS Secondary Water Skids.

Began reviewing acceptance welding documentation and inspection results for the first LN2 Dewar from AES for CryoPlant.

Gibson site visit in Richmond for LCLS cryo-plant control cabinets and frames.

Upcoming Travel/Deliveries/Reviews:

- Interface Box FDR2							07-Nov-2018

- CryoPlant Software Development Review			14-Nov-2018

- Monthly 4.5K Cold box status and update			29-Nov-2018

- CryoPlant Commissioning Workshop @JLab			4&5-Dec-2018