# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of February 7-13, 2019

Issues:

Accomplishments this week:

Presented progress status and planning for Director’s Project Review at SLAC.

Continue to wringing out LERF interlocks and controls.

Changing the SRF cavity contract to implement a new doping recipe.

Upcoming Reviews:

February 12-14, 2019		Director’s “Mission Success Review”

February 27-March 1st, 2019	EVMS Surveillance Review

March 19-21, 2019			DOE OPA Review

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of February 7-13, 2019

Issues:  Delay in start of string 17 may impact CM test and delivery schedule.

Accomplishments this week:

Providing details to System Manager on cavity performance incentives earned at EZ.

Prepared presentations for and participating in Director’s Review at SLAC.

Preparing to ship J10 to SLAC – departing JLab on 16-Feb and arriving on 19-Feb since 18-Feb is holiday with SLAC closed.

QUALITY:

- Continue in process high and low pressure welding inspections on CM013 to prepare for RT on 2-16.

Pressure testing on low pressure circuit for CM013.

In process inspections on the removal and replacement of leaking 4 inch 2 phase T piping component for CM015 (UCM026).

Upcoming Travel/Meetings:

- Director’s Review – 12-14 Feb

- Cavity Vendor Contract Close-out Visits to RI & EZ (Wilson, Laney) – 10-15 Feb

- OPA Review – 19-21 March

# Weekly Reporting

WBS 1.04.06 Cryomodules - LERF Conversion

Week of February 7-13, 2019

Issues: None

Accomplishments this week:

Work continued on RF interlocks, testing to start when folks are done with commissioning workshop.

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of February 7-13, 2019

Issues:

- Reduction in baseline resources (return funding to contingency; top-down EAC) without corresponding reduction in scope of cryoplant commissioning.

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in Nov 2017).

- Ongoing delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

- First batch of gauge panels nearing completion for shipment this month.

- Shipping 40 gallon oil tanks to vendor for manifold installation.

- All pressure regulators delivered to SLAC.

- Presented Status and Planning for Director’s Review.

Major Procurement Status:

Vendor Progress:

C1 Vacuum pump skid (Lower Cold Box) & access hole for CryoDuct installed @SLAC

Outer vessel for 2nd LN2 Dewar nearing completion

QUALITY:

- Site visit to LN2 Dewar manufacturer to witness progress on second Dewar.

- Working with Demaco for onsite installation of Cryo Plant Main Transfer Lines and Interface Boxes.

Upcoming Travel/Deliveries/Reviews:

- LCLS-II Director’s Review						(12-14)-Feb-2019

- PHPK Oversight							14-Feb-2019

- Ambient heat exchangers (Vaporizers) vendor site visit 	19-Feb-2019

- 2K Cold box - PHPK/Linde Oversight				(20-21)-Feb-2019

- Delivery of Vaporizers 						26-Feb-2019

- CP1 Dewar neck can final leak test (Ability Engineering)	28-Feb-2019

- 4.5K Lower cold box Status meeting @PHPK			01-March-2019