# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of February 14-20, 2019

Issues:

Accomplishments this week:

- Participated in follow-up planning to address recommendations from Director’s Project Review held at SLAC.

- Progressing with wringing out LERF interlocks and controls.

- SRF cavity contract being modified to implement a new doping recipe.

Upcoming Reviews:

February 27-March 1, 2019	EVMS Surveillance Review

March 19-21, 2019			DOE OPA Review

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of February 14-20, 2019

Issues:  Delay in start of string 17 may impact CM test and delivery schedule.

Accomplishments this week:

Providing details to System Manager on cavity performance incentives earned at EZ.

Preparing proposal for reducing rework on J1.3-01 to improve schedule and reduce cost.

Participated in Director’s Review at SLAC.  Received feedback on presentation and began folding comments into OPA slides.

Shipped J10 to SLAC – the CM arrived on 19-Feb with beamline vacuum intact.

J-13 is in the CMTF and will be cooled down beginning 22-Feb.

QUALITY:

- In process high and low pressure welding inspections on CM014 to prepare for RT on 2-16

- Pressure testing on low pressure circuit for CM014

- Inspections on the removal and replacement of leaking 4 inch 2 phase T piping component for CM015 (UCM026) are completed

- RT of high pressure welding on both CM013 and 014 done Saturday 2-16.  All welds passed

Upcoming Travel/Meetings:

- OPA Review – 19-21 March

# Weekly Reporting

WBS 1.04.06 Cryomodules - LERF Conversion

Week of February 14-20, 2019

Issues: None

Accomplishments this week:

No report.

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of February 14-20, 2019

Issues:

- Reduction in baseline resources (return funding to contingency; top-down EAC) without corresponding reduction in scope of cryoplant commissioning.

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in Nov 2017).

- Ongoing delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

- First batch of gauge panels nearing completion for shipment this month.

- Shipping 40 gallon oil tanks to vendor for manifold installation.

- Review Risk Registryin prep for OPA Review.

Major Procurement Status:

Gauge Panels (manufactured @Jefferson Lab):

QUALITY:

- Site visits to 2K & 4.5K cold box and ambient vaporizers manufacturers to witness progress and push schedule.

- Working with Demaco for onsite installation of Cryo Plant Main Transfer Lines and Interface Boxes.

Upcoming Travel/Deliveries/Reviews:

- 2K Cold box - PHPK/Linde Oversight  (P&ID checkout)  	(20-22)-Feb-2019

- Delivery of Vaporizers 						26-Feb-2019

- CP1 Dewar neck can final leak test (Ability Engineering)	28-Feb-2019

- Lower cold box status meeting @PHPK		 		01-March-2019

- Ambient heat exchangers (Vaporizers) vendor site visit 	09-Mar-20194.5K