# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of February 28-March 6, 2019

Issues:

Accomplishments this week:

Preparations for the OPA review continue.

LERF:

  - Experts are here from LBNL and SLAC working on getting the LLRF software working.

  - Developing steady state Q0 measurements using cavity heaters.

CMTF testing of CM 13 is ongoing, finished Emax and started Q0 measurements.

Upcoming Reviews:

March 19-21, 2019		DOE OPA Review

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

February 28-March 6, 2019

Issues:  Delay in start of string 17 may impact CM test and delivery schedule.

Accomplishments this week:

Preparing proposal for reducing rework on J1.3-01 to improve schedule and reduce cost.

Finalizing and uploading presentations for OPA review.

Identified two control accounts that need increased spending authorization (1.4.6.15, 1.4.6.20) in line with the EAC values.

J-9 began disassembly at new WS3.

J-13 is in the CMTF.  Tested maximum gradients – total CM voltage ~150 MV.  Six cavities FE free, two with FE onset above 10 MV/m.  Performed fast cooldown and began Q0 testing.

Continued work on steady state Q0 measurement techniques in LERF while awaiting availability of LERF LLRF system.

QUALITY:

- Closed NCR 1689 on leaking 4 inch, 2-phase, T-piping component for LCLS CM015 (UCM026).

- LCLS Upper Cold Mass Assembly Station Hardware investigation/clarification.

Upcoming Travel/Meetings:

- OPA Review – 19-21 March

# Weekly Reporting

WBS 1.04.06 Cryomodules - LERF Conversion

Week of February 28-March 6, 2019

Issues: None

Accomplishments this week:

Work continues on LLRF commissioning, actual cavity testing should commence within days!

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of February 28-March 6, 2019

Issues:

- Reduction in baseline resources (return funding to contingency; top-down EAC) without corresponding reduction in scope of cryoplant commissioning.

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in Nov 2017).

- Ongoing delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

- Completed monthly status on 4.5K cold boxes @PHPK.

  - Delivery pulled forward 2-weeks to mid-June.

- Utility & gas management gauge panels complete & shipped to SLAC.

- Review Risk Registry in prep for OPA Review.

- Finalized presentation materials for March DOE review.

First set of JLab manufactured Gauge Panels Complete and sent to SLAC

Vacuum pumps delivered to SLAC

Major Procurement Status:

QUALITY:

- Reviewing operation & maintenance manuals from cold compressor vendors.

Upcoming Travel/Deliveries/Reviews:

- CP1 Dewar neck can final leak test (AET)			7-Mar-2019

- Vaporizers delivery to SLAC					12-Mar-2019

- First batch of gauge panels delivery to SLAC 			12-Mar-2019

- DOE OPA Project Review						19-21-Mar-2019