# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of April 11-17, 2019

Issues:

Accomplishments this week:

Cryomodule production continues to run smoothly. Cavity String 18 is complete and rolled out of the clean room.

LERF:  High power 16 cavity run completed.

CP procurements are progressing well. 4.5 K LCB insulating vacuum is being pumped.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of April 11-17, 2019

Issues:

Accomplishments this week:

J1.3-14 - Planning to ship to SLAC on 24-APR.  Pre-ship review planned for 17-APR.

J1.3-15 installed in CMTF and cold.  Testing started on 16-APR.

J1.3-16 at WS-5.  Once completed, it is scheduled for LERF testing during the summer run.

J1.3-17 moved to WS-3 on 16-APR.

J1.3-18 string assembly completed and leak tight.  Rolled out to WS-2 on 17-APR.

J1.3-19 has 5 of 8 cavities qualified.

J1.3-12 16-cavity testing with J1.3-5 completed on 12-APR.  Planning to pull u tubes on 20-APR.

J1.3-01 is at WS-4 for retro-fit.  Shields and MLI installed.

QUALITY:  No report.

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of April 11-17, 2019

Issues:

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in Nov 2017).

- Delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

- IBX/MTL subcontract (Demaco)

  - Successful FAT of C1 Multi-transfer Line (MTL)

  - This keeps the C1 MTL on schedule for delivery to SLAC late next month.

- 4.5K Cold Box – Final closure welding complete – Initial pump-down in progress

QUALITY:

- JLAB & SLAC staff scheduled to be present for Factory Acceptance Testing

  - C1 MTL

  - C2 Dewar Neck Can

- QA resource for CP document control in place and working.

Upcoming Travel/Deliveries/Reviews:

- Vendor Visit for IBX & MTL factory acceptance test		      17-19 Apr 2019

- 4.5K & 2K cold boxes oversight vendor visit at PHPK			18 Apr 2019

- 4.5K & 2K cold boxes oversight vendor visit at PHPK			25 Apr 2019

- Factory Acceptance Test for C2 Dewar Neck Can	       Week of 25-Apr-2019

- 4.5K Cold box Monthly status update @PHPK				02-May-2019