# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of April 18-24, 2019

Issues:

Accomplishments this week:

Cryomodule production continues to run smoothly. Cavity String 19 preparations have started.

J1.3-14 shipped to SLAC on 24-APR and scheduled to arrive on 30-APR for unload on 01-MAY.

LERF:  We are progressing with disassembly and on track to replace J-12 with J-16 on 29-30 APR.

CP procurements are progressing well.  Four Gauge Panels fabricated at JLab shipped out to SLAC – ETA 29-APR.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of April 18-24, 2019

Issues:

Accomplishments this week:

J1.3-14 - Planning to ship to SLAC on 24-APR with arrival on Tue 30-APR for Wed 01-MAY unload.  Pre-ship review completed 17-APR.

J1.3-15 installed in CMTF and cold.  Emax’s completed – total ~152 MV.  FCD was conducted on 23-APR.  Qo’s are in progress.

J1.3-16 at WS-5.  Once completed, it is scheduled for LERF testing during the summer run.  Planned to move to LERF on 30-APR.

J1.3-17 at WS-3.  Lollipops will be returned for J-19 later this week.

J1.3-18 at WS-2.

J1.3-19 has 7 of 8 cavities qualified.

J1.3-12 Pulled u tubes at LERF on 20-APR.  Opened up interconnect and removed bellows.  Setting up to remove beamline connection.  Plan to remove CM from LERF on 29-APR.  Plan to ship to SLAC on 21-JUN or earlier.

J1.3-01 moved to WS-5 on 23-APR.  Plan to ship to SLAC on 17-MAY.

J1.3-03 installed on WS-4 on 23-APR.

HOM BLA assembly (1 unit) was completed on Monday.

QUALITY:  J1.3-16 was RT on Saturday 4-20; welding passed.

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of April 11-17, 2019

Issues:

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in NOV 2017).

- Delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

- IBX/MTL subcontract (Demaco) installation scope kickoff meeting held 18-APR

- Four Gauge Panels fabricated at JLab shipped out to SLAC – ETA 29-APR

- Gas Analyzer Cabinets fabrication complete at JLab – crating underway for shipment to SLAC

Gas Analyzer Cabinets.

Gauge Panels loaded at JLab for delivery to SLAC.

QUALITY:

- JLAB & SLAC staff present for CP1 MTL Factory Acceptance Testing at Demaco

- JLab staff scheduled to be present for C2 Dewar Neck Can Factory Acceptance Testing at Ability Engineering (AET)

- QA resource for CP document control in place and working.

Upcoming Travel/Deliveries/Reviews:

- 4.5K & 2K cold boxes oversight vendor visit at PHPK	                    25-Apr, 2019

- 4.5K Cold box Monthly status update @PHPK			        02-May, 2019

- Factory Acceptance Test for C2 Dewar Neck Can	       Week of 6-May, 2019