# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of April 25 to May 1, 2019

Issues:

Accomplishments this week:

Cryomodule production continues to run smoothly. Cavity String 19 preparations have started.

J1.3-14 shipped to SLAC on 24-APR and scheduled to arrive on 30-APR for unload on 01-MAY.

LERF:  We are progressing with assembly of J-16.

The project has issued a shipping hold for cryomodule.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of April 25 to May 1, 2019

Issues:  Shipping hold instructions issued on 30-APR.

Accomplishments this week:

J1.3-01 at WS-5.  Warm couplers in progress.  Plan to ship to SLAC on 17-MAY.

J1.3-03 installed on WS-4 on 23-APR.  Preparing for VV removal.

J1.3-12 at WS-5.  Removed from LERF on 29-APR.  Plan to ship to SLAC on 21-JUN or earlier pending shipping restart authorization.

J1.3-14 - Shipped to SLAC on 24-APR.  Arrival planned for Wed 01-MAY unload.

J1.3-15 installed in CMTF and cold.  Q0’s are complete.  Multi-cavity runs complete.  Pre-warm up review planned for Wednesday 1-MAY.

J1.3-16 at LERF.  Moved to LERF on 30-APR, installed and aligned.  Beamline work starting on 1-MAY.

J1.3-17 at WS-3.  Alignment in progress.

J1.3-18 at WS-2.

J1.3-19 has 8 cavities qualified.  String assembly started.

J1.3-20 has 1 of 8 cavities qualified.

QUALITY:  Pressure testing of CM 016 (# 30) low-pressure circuit prior to moving to LERF for testing.  LCLS II Tooling receipt inspection and document review for LCLS-II Cryomodule Assembly Rail weldments PO 19-P0346 from Astro Machine.

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of April 25 to May 1, 2019

Issues:

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in NOV 2017).

- Delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

- Final factory acceptance leak check of CP2 4.5K lower cold box

- Initial pump-down of 2KCB (@PHPK) in progress

- Gauge Panels (fabricated at JLab) en-route to SLAC

- Gas Analyzer Cabinets fabrication complete ready to ship to SLAC

CP2 4.5K LCB in final leak-check   ----   2KCB initial pump-down in progress @PHPK

QUALITY:

- JLAB & SLAC staff present for CP1 MTL Factory Acceptance Testing at Demaco

- JLab staff scheduled to be present for C2 Dewar Neck Can Factory Acceptance Testing at Ability Engineering (AET)

- QA resource for CP document control in place and working.

Upcoming Travel/Deliveries/Reviews:

- Onsite visit to SLAC to witness/coordinate install/com	               01-03-May-2019

- Final leak check of CP2 4.5K lower cold box				02-May-2019

- 4.5K Cold box Monthly status update @PHPK				02-May-2019

- Factory Acceptance Test for C2 Dewar Neck Can	       Week of 6-May, 2019