# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of May 16-29, 2019

Issues:

Accomplishments this week:

The last 4.5K (lower) cold box for the cryoplant has made it to SLAC.

Cryomodule production continues to run smoothly.  We are on a shipping hold. We need a qualified alternative to the current M-Mount configuration.

J1.3-12 is at SLAC.

The project has rescinded the approval to ship J-01. We need to develop the p[lan for how to ship this CM.

LERF:  J-16 Cooldown has been completed.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of May 16-29, 2019

Issues:  Shipping hold instructions issued on 30-APR.  J-01 has been put on hold while SLAC reconsiders RoD on shipping configuration.  Lack of qualified cavities due for string 20 due to lower than expected yield in testing.

Accomplishments this week:

LERF is at 2K as of 28-May.

J1.3-20 has 4 of 8 cavities qualified.  String may be delayed at project’s direction.

J1.3-19 rolled out on 15-May.

J1.3-18 – WS3, WS3, Magnet leads, Welding 2 phase piping

J1.3-17 – WS4, Instrumentation, tune HOM’s

J1.3-16 – In LERF, Cooled down to 2K on 28-May.

J1.3-15 – Removed from CMTF; Configure for Shipping 8-Jun – delayed to arrive at SLAC on 17-Jun at project’s direction.

J1.3-12 – Received at SLAC on 5-21

J1.3-09 – Disassembled

J1.3-05 – In LERF, Cooled down to 2K on 28-May.

J1.3-03 – WS3, Installing shipping manifold.

J1.3-01 – WS5, Flex line repair on-going, SHIPPING HOLD

J1.3-02, 07 – Waiting for cantilever fixture for retrofit

J1.3-04, -08, -10, -13, -14, -12 @ SLAC

QUALITY:  CM001 leak repair work in process for second repair attempt (welding is done).  RT to be scheduled this week.  Document review for LCLS Cryo Module UCM039 and VV039 completed.

Upcoming Travel/Deliveries/Reviews:

- J-15 arrival at SLAC		 	17-June-2019

- J-01 arrival at SLAC			ON HOLD

- J-03 arrival at SLAC			TBD

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of May 16-29, 2019

Issues:

- Resolution of structural interferences created during the design of the cold box room platforms and cable trays support systems (identified in NOV 2017).

- Delays installing interconnecting piping systems in cryoplant is delaying startup of commissioning activities.

Accomplishments this week:

Bench testing of Utility software in progress.

CP2 Dewar-neck-can delivered to SLAC.

First 2K CB successfully completed factory acceptance test at PHPK, and was shipped to SLAC (see photo below).

CP2 4.5K LCB delivered and set in position at SLAC (see photo below).

QUALITY:

First set of commissioning documentation delivered to SLAC.

  - Routine in place for documentation review and submittal to SLAC.

JLab witness first 2K cold box factory acceptance test on 20-May-2019.

JLab staff onsite for C2 Dewar Neck Can Factory Acceptance Testing at Ability Engineering (AET).

JLab staff onsite to witness progress on C2 LN2 Dewar at AES.

Upcoming Travel/Deliveries/Reviews:

- Delivery of C2 Dewar Neck Can					30-May-2019

- Delivery of first 2K CB to SLAC  					05-Jun-2019

- Delivery of C1 Multi-transfer Line (MTL) 				07-Jun-2019