LCLS-II MAY PROJECT STATUS REPORT

DATE:	June 3, 2019

LOCATION OF PROJECT:	Jefferson Lab

SENIOR TEAM LEAD:	Joe Preble

MONTHLY PROGRESS

Summary

JLab continues to make significant progress in all areas.  Cost, schedule, and scope are being managed to the baseline.  We received earned value and variance data, analyzed data and submitted VARs.

EV performance is as of April close

Overall % complete = 90%, SPI = 0.96, CPI = 0.98

Management

The last 4.5K (lower) cold box for the cryoplant completed the final factory acceptance test and was shipped to SLAC where it arrived May 22.

Cryomodule production continues to run smoothly.  Cavity String 19 rolled out on 15-May. All cavities for cavity string 20 are qualified.

J1.3-12 shipped from JLab on 18-May and arrived at SLAC.

LERF:  J-16 cooldown was completed.

Cryoplant System:

EV Performance

Overall % complete = 87%, SPI = 0.95, CPI = 0.97

Successful shipment of C2 4.5K lower cold box to SLAC.

C1 2K cold box shipped from PHPK to SLAC. The cold box is delayed in Wyoming due to the truck breaking down. Delivery is expected the week of 3 June.

Final shipment of gauge panels delivered to SLAC.

Gas Analyzer Cabinets fabrication complete and shipped to SLAC.

Completed assignment of IBX installation scope to SLAC.

Bench testing of Utility software in progress.

CP2 Dewar-neck-can delivered to SLAC.

Gas Analyzer cabinets complete & shipped to SLAC.

CP2 Lower Cold Box successfully completed final leak-check.

Shipping to SLAC this week

C2 4.5K Lower Cold Box delivered and set in position at SLAC.

First 2K CB successfully completed factory acceptance test at PHPK, and was shipped to SLAC.

Major equipment continued to be shipped to SLAC.

Component Count = 94.  Delivered = 88.  In Fabrication = 5.  Installed = 83.  In storage = 5.

Cryomodules:

EV performance

Overall % complete = 92%, SPI = 0.96, CPI = 0.98

J1.3-20 has 8 of 8 cavities qualified.

J1.3-19 rolled out on 15-May.

J1.3-18 – WS3, Magnet leads, Welding 2 phase piping.

J1.3-17 – WS4, Instrumentation, tune HOMs.

J1.3-16 – In LERF, Cooled down to 2K on 28-May.

J1.3-15 – Removed from CMTF; Configure for shipping 8-Jun – delayed to arrive at SLAC on 17-Jun at project’s direction.

J1.3-12 – Received at SLAC on May 21.

J1.3-09 – Disassembled.

J1.3-05 – In LERF, Cooled down to 2K on 28-May.

J1.3-03 – WS3, Installing shipping manifold.

J1.3-01 – WS5, Flex line repair on-going, SHIPPING HOLD.

J1.3-02, 07 – Waiting for cantilever fixture for retrofit.

One HOM BLA assembly was completed.

LERF is at 2K as of 28-May.