# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of June 26 to July 10, 2019

Issues:

Accomplishments this week:

The last cold box for the cryoplant is in route to SLAC.

The final equipment FAT, IBX#1&2 and MTL#2, is scheduled for 29 July – 2 August.

Cryomodule production continues to run smoothly.

J-17 is ready for installation into the CMTF

Working BCRs for the CP commissioning change, aligning CP payment dates, and rework of J11.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of June 26 to July 10, 2019

Issues:  Shipping hold instructions issued on 30-APR.  J-01 was put into storage.

Accomplishments this week:

Received direction from project to begin rework on J11.  BCR details in development.

LERF testing is ongoing – J16 & J5 Qo measurements began 8-JUL.

J1.3-21 – Seven of eight cavities are qualified for the string.

J1.3-20 – String assembly scheduled to start on 11-JUL.

J1.3-19 – WS3

J1.3-18 – WS4

J1.3-17 – installed in CMTF; cooldown planned for later this week

J1.3-16 – Testing in LERF

J1.3-11 – In storage

J1.3-09 – Disassembled

J1.3-07 – WS6, rework in progress; fastener spreadsheet

J1.3-05 –Testing in LERF

J1.3-03 – WS5, preparing for shipment on 26-JUL; trailer arrived back at JLab on 8-JUL.

J1.3-02 – Waiting for cantilever fixture for retrofit

J1.3-01 – In storage

J1.3-04,08,10,12,13,14,15@SLAC

QUALITY:  Low pressure testing on CRM003.

Upcoming Travel/Deliveries/Reviews:

- J-03 arrival at SLAC				30-July-2019

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of June 26 to July 10, 2019

Issues:

- Delays installing interconnecting mechanical, electrical and controls infrastructure in cryoplant is delaying startup of CP1 commissioning activities.

Accomplishments this week:

Site visit to 2nd LN2 Dewar vendor to witness progress.

Second 2K cold box (Linde) is en route with live tracking to SLAC.

QUALITY:

Commissioning documentation progressing by JLab QA group.

  - Routine in place for documentation review and submittal to SLAC.

JLab SO onsite to witness CP2 LN2 Dewar manufacturing (AES).

Software bench testing progressing well in advance of equipment readiness.

Upcoming Travel/Deliveries/Reviews:

- SME visit to LN2 Dewar vendor 					10-July-2019

- Delivery of Second 2K cold box (week of)			12-July-2019

- Factory Acceptance Test of CP1 & CP2 IBX & MTL		29-July-2019