# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of July 11-17, 2019

Issues:

Accomplishments this week:

The last cold box for the cryoplant was delivered to SLAC!

The final equipment FAT, IBX#1&2 and MTL#2, is scheduled for 29 July – 2 August.

J-17 is installed in the CMTF.

Working BCR/EACs for the CP commissioning change, aligning CP payment dates, and rework of J11.

Visitors are here testing CMs in the LERF.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of July 11-17, 2019

Issues:  Shipping hold instructions issued on 30-APR.  J-01 was put into storage.

Accomplishments this week:

Received direction from project to begin rework on J11.  EAC details in development.

LERF testing is ongoing – J16 & J5; FPC High Qext studies ongoing; Issue with GDR operation using SLAC control system

J1.3-21 – Seven of eight cavities are qualified for the string.

J1.3-20 – String assembly scheduled to start on 11-JUL.

J1.3-19 – WS3

J1.3-18 – WS4

J1.3-17 – installed in CMTF; cooldown planned for later this week; delayed due to reconfiguration needed after testing C20 style CM

J1.3-16 – Testing in LERF

J1.3-11 – In storage

J1.3-09 – Disassembled

J1.3-07 – WS3, rework in progress; BPM hardware replacement

J1.3-06 - Disassembled

J1.3-05 –Testing in LERF

J1.3-03 – WS5, preparing for shipment on 26-JUL

J1.3-02 – Waiting for cantilever fixture for retrofit

J1.3-01 – In storage

J1.3-04,08,10,12,13,14,15@SLAC

QUALITY:  Low pressure testing on CM03.

Upcoming Travel/Deliveries/Reviews:

- J-03 arrival at SLAC				30-July-2019

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of July 11-17, 2019

Issues:  Delays installing interconnecting mechanical, electrical and controls infrastructure in cryoplant is delaying startup of CP1 commissioning activities.

Accomplishments this week:

LN2 Dewar vendor completed inner vessel.  MLI wrapping is underway.

Second 2K cold box (Linde) delivered to SLAC.

2nd LN2 Dewar Inner Vessel

CP2 2K Cold Box Delivered

QUALITY:

Commissioning documentation progressing by JLab QA group.

  - Routine in place for documentation review and submittal to SLAC.

Software bench testing progressing well in advance of equipment readiness.

Upcoming Travel/Deliveries/Reviews:

- Factory Acceptance Test of CP1 & CP2 IBX & MTL		29-July-2019