# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of August 1-7, 2019

Issues:

Accomplishments this week:

Continue to work on finalizing the CP commissioning BCRs to transfer scope and responsibility to SLAC.

Reviewing June EAC.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of August 1-7, 2019

Issues:

Accomplishments this week:

LERF testing is ongoing – J16 & J5; SLAC test plans ongoing.  CEBAF run has been extended to 9-SEP.  Need request from SLAC on additional proposed tests in LERF.

J1.3-20- WS2-LC 2 phase piping, MLI, Mag shields

J1.3-19- WS4- RF Cables, tune HOM’s

J1.3-18- WS5- MC Line, Configure for testing

J1.3-17- In CMTF, Testing

J1.3-16-Testing in LERF

J1.3-11- Disassemble, to TL mid August

J1.3-06/09 – Disassembled

J1.3-07- WS3-FSS, Waiting for Cantilever

J1.3-05 –Testing in LERF

J1.3-02– In storage offsite

J1.3-01- In storage

QUALITY:

- RT for CM018 passed Saturday 8-3-19.

- Welding review completed for UCM 039.

Upcoming Travel/Deliveries/Reviews:

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of August 1-7, 2019

Issues:  Finalizing the EAC for planning purposes.

Accomplishments this week:

Visited LN2 Dewar vendor to check welds.

  - JLab witness and consult on completion.

  - SLAC survey crew onsite to verify mounting locations for interface with foundations in the tank filed.

Both ends (heads) welded onto the final LN2 Dewar in preparation for FAT next week.

QUALITY:  Traveled to AES for second LN2 Dewar welding review and doc pack review.

Upcoming Travel/Deliveries/Reviews:

- Factory Acceptance Test of the 2K transfer line		7-August-2019

- SLAC survey of LN2 Dewar foundation mounting 	7-August-2019

- Factory Acceptance Test of 2nd LN2 Dewar		14-August-2019