# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of August 8-14, 2019

Issues:

Need to finalize CP commissioning BCR

Need to finalize J1.3-11 rework EAC

Accomplishments this week:

Continue to work on finalizing the CP commissioning BCRs to transfer scope and responsibility to SLAC.

Reviewing June EAC.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of August 8-14, 2019

Issues:

Accomplishments this week:

LERF testing is ongoing – J16 & J5; SLAC test plans ongoing.  CEBAF run has been extended to 9-SEP.  Received request from SLAC on additional proposed tests in LERF.  Performing fast cooldown in LERF on J16 & J5.  SLAC visitors (Fauve, Shrishrimal) observing.

J1.3-20- WS3- Unite to UCM

J1.3-19- WS4- Align CM in VV

J1.3-18- WS5- Configure for testing

J1.3-17- Removed from CMTF.  Great test results reported at SRF weekly meeting.  Currently at WS5 - Configure for Shipping 8/24

J1.3-16-Testing in LERF- Warm-up Sept

J1.3-11- Disassemble, to TL mid August

J1.3-06/09 – Disassembled

J1.3-07- WS3- Waiting for Cantilever

J1.3-05 –Testing in LERF

J1.3-02– In storage offsite

J1.3-01- In storage

QUALITY:  No report.

Upcoming Travel/Deliveries/Reviews:

Participate in LERF testing (Fauve, Shrishrimal)

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of August 8-14, 2019

Issues:  Finalizing scope transfer & the EAC for planning purposes.

Accomplishments this week:

Visited LN2 Dewar vendor to witness/consult on progress.

  - SLAC survey completed onsite to verification of mounting locations for interface with foundations in the tank farm.

C1&C2 IBXs and C2 MTL packaged for shipping

QUALITY:

Continuing with QA review of commissioning documentation package; prior to submittal in support of system readiness review.

Upcoming Travel/Deliveries/Reviews:

- LN2 Dewar manufacturer to witness/consult	 	7-August-2019

- Factory Acceptance Test of 2nd LN2 Dewar		28-August-2019