# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of August 15-21, 2019

Issues:

Need to finalize J1.3-11 rework EAC.

Accomplishments this week:

Finalized the CP commissioning BCRs to transfer scope and responsibility to SLAC.

Completed review of June EAC and we are in agreement with the numbers.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of August 15-21, 2019

Issues:

Accomplishments this week:

LERF testing is ongoing – J16 & J5; SLAC test plans ongoing.  CEBAF run has been extended to 9-SEP.  Received request from SLAC on additional proposed tests in LERF.  Conducting another fast cooldown in LERF on J16 & J5 based on proposal from SLAC visitors (Fauve, Shrishrimal).

J1.3-6- 2/8 cavities qualified for string.  Four below-spec cavities identified.

J1.3-21- String will roll out on 21-AUG.

J1.3-20- WS3- Welding Process Piping, magnet leads prepped, need intercepts.

J1.3-19- WS5- Warm Couplers

J1.3-18- WS5- Ins Vac leak check, failed Magnet flange

J1.3-17- WS5- Configure for Shipping 8/24

J1.3-16-Testing in LERF- Warm-up Sept

J1.3-11- Disassemble, brought to Test Lab 8/20

J1.3-06/09 – Disassembled

J1.3-07- WS4- Weld lower shields

J1.3-05 –Testing in LERF

J1.3-02– In storage offsite

J1.3-01- In storage

QUALITY:  No report.

Upcoming Travel/Deliveries/Reviews:

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of August 15-21, 2019

Issues:  Finalizing scope transfer & the EAC for planning purposes.

Accomplishments this week:

SLAC survey verified LN2 Dewar tank saddle mounting locations are correct and within tolerance for interface with tank farm foundations.

2nd LN2 Dewar pumping down in prep for final leak check in progress.

C1&C2 IBXs and C2 MTL loaded onto Shipping container – Due to arrive in Oakland, CA mid-Sep.

QUALITY:

JLab QA group leading the review and submittal process of final cryoplant documentation packages for manufacturing and commissioning.

Upcoming Travel/Deliveries/Reviews:

- Factory Acceptance Test of 2nd LN2 Dewar		28-August-2019

- C1&C2 IBXs and C2 MTL delivery to SLAC		27-Sep-2019