# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of August 29-September 4, 2019

Issues:

Need to finalize J1.3-11 rework EAC.

Lack of Magnet Thermal anchor components is holding up CM20 and will have knock on effects for later CMs. This will result in a delay in the delivery of the CMs CM21, 6, 9, 11.

Accomplishments this week:

Finished the last planned LERF test.

Finalized pCM N-mount installation procedures in preparation for shipping the pCM. Plan to ship the pCM mid-September.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of August 29-September 4, 2019

Issues:  Lack of qualified cavities for string 6.  Will need to use below-spec cavities to hold schedule.

Accomplishments this week:

LERF testing is completed – J16 & J5; CEBAF run was extended to 9-SEP.  Completed LLRF development with LLRF experts from SLAC (S. Hoobler), LBNL (L. Doolittle, S. Ferreira Paiagua) and FNAL (B. Chase).  Completed Qo’s on selected CM-5 cavities.

Shipped 5 BLAs to SLAC last week.

J1.3-6- 8/8 cavities qualified for string.  Five below-spec cavities identified.

J1.3-21- WS2- Process Piping, Berry Bolts

J1.3-20- WS3- Solder magnet leads to flags, install tuners

J1.3-19- WS5- MC line leak checking, Installing end cap, Low pressure testing

J1.3-18- Ready for testing, Installed in CMTF 9/03

J1.3-16-Testing in LERF- Warm-up Sept

J1.3-11- WS3N – Out of VV, Begin disassembly

J1.3-06/09 – Disassembled

J1.3-07- WS5- Warm couplers, instrumentation flanges

J1.3-05 –Testing in LERF

J1.3-02– In storage offsite

J1.3-01- Prep to Ship, 9/13 is the target

QUALITY:  No report.

Upcoming Travel/Deliveries/Reviews:

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of August 29-September 4, 2019

Issues:  None.

Accomplishments this week:

Interface Boxes (IBX) & Main Transfer Lines (MTL) in transit to SLAC.

  - Due to arrive in Oakland, CA mid-Sep.

2nd LN2 Dewar & helium transfer line completed final leak check.

QUALITY:

JLab SME witness successful factory acceptance testing of 2nd LN2 Dewar & LHe transfer line at Vendor site.

Upcoming Travel/Deliveries/Reviews:

- Shipment of 2nd LN2 Dewar				10-Sep-2019

- C1&C2 IBXs and C2 MTL delivery to SLAC		27-Sep-2019