# Weekly Reporting

WBS 1.01.07 JLAB Management

Week of September 5-11, 2019

Issues:

Need to finalize J1.3-11 rework EAC.

Lack of Magnet Thermal anchor components is holding up CM20 and will have knock on effects for later CMs. This will result in a delay in the delivery of the CMs CM21, 6, 9, 11.

Accomplishments this week:

Warming up CMs in LERF.

Completed pCM N-mount installation in preparation for shipping the pCM. Plan to ship the pCM mid-September.

Upcoming Reviews:  None

# Weekly Reporting

WBS 1.04.06 JLAB Cryomodules

Week of September 5-11, 2019

Issues:  Lack of qualified cavities for string 6.  Will need to use below-spec cavities to hold schedule.  Lack of magnet thermal intercepts from FNAL is delaying assembly schedule for remaining CMs.  Shipping moratorium for 8 weeks.

Accomplishments this week:

LERF testing was completed – J16 & J5 are warming up.  Conducted static heat load test for SLAC colleagues.

J1.3-9- 2/8 cavities identified for string; both are below-spec.

J1.3-6- String assembly in progress.  Roll-out planned on 9/20.

J1.3-21- WS2- LC Process Piping, Berry Bolts

J1.3-20- WS3- Heat station magnet leads

J1.3-19- WS5- LC 2 phase & Bayonet box

J1.3-18- 2K @ CMTF; tuner tests completed; set FPC Qext; conducting Emax’s

J1.3-16- LERF warming up

J1.3-11- WS3N –Magnet heat stations used for CM20, begin disassembly

J1.3-07- WS5-MC Line, Instrumentation flanges

J1.3-05 –LERF warming up

J1.3-02– In storage offsite

J1.3-01- Prepping to Ship

QUALITY:  No report.

Upcoming Travel/Deliveries/Reviews:

Weekly Reporting

WBS 1.04.08 JLAB Cryoplant System

Week of September 5-11, 2019

Issues:  None.

Accomplishments this week:

Interface Boxes (IBX) & Main Transfer Lines (MTL) in transit to SLAC.

  - Due to arrive in Oakland, CA 16-Sep.

2nd LN2 Dewar in transit to SLAC.

  - Due to arrive at SLAC 16-Sept

Second LN2 Dewar Shipping from Vendor (AES)

QUALITY:

JLab Quality personnel supporting formal transfer of documentation to SLAC

Upcoming Travel/Deliveries/Reviews:

- 2nd LN2 Dewar delivery to SLAC				16-Sep-2019

- C1&C2 IBXs and C2 MTL delivery to SLAC		27-Sep-2019