LCLS-II MAY PROJECT STATUS REPORT

DATE:	June 1, 2020

LOCATION OF PROJECT:	Jefferson Lab

SENIOR TEAM LEAD:	Joe Preble

MONTHLY PROGRESS

Summary

Due to the COVID19, on March 24 Jefferson Lab remains in MEDCON6 until further notice. On site personnel are limited to site essential personnel only.  All LCLS-II onsite activities are on a hold.

Report reflects April EV data. JLab continues to make progress in areas supported by work from home.  We received earned value and variance data, analyzed data and submitted VARs.

EV Performance as of April close.

Overall % complete = 97.0%, SPI = 0.99, CPI = 0.99

Management:

Addressing review recommendations from the April DOE OPA Review.

Leading replan of remaining Cryomodule and Cryoplant activities.

Cryoplant System:

EV Performance as of April close.

Overall % complete = 95.0%, SPI = 1.00, CPI = 0.97

Working on 4.5k Cold Box coding and training. Integrated bench testing on SLAC hardware with EPICS has started.

Liquid helium dewar delivered to SLAC on May 22, 2020.

Completed 2k cold compressors agreement; awaiting sign-off from SLAC.

Working on hand-off agreement.

Working on memorandum of agreement with SLAC on commissioning planning and support.

Continued the transfer of large equipment warranty packages to SLAC.

Cryomodules:

EV Performance as of April close.

Overall % complete = 99.0%, SPI = 0.99, CPI = 0.99

Compiling lessons learned.

Six BLAs, currently stored in cleanroom, are ready to ship when SLAC reopens.

J1.3-02- WS5 - Coupler replaced procedure ready for review and approval.

J1.3-06- Testing complete; planning to ship when we come back to work on the JLab site.

J1.3-09- In CMTF for testing; next to ship after CM6.

J1.3-11 – WS2 - Leaky cavity will be replaced.  Cavity swap procedure awaiting approval.

J1.3-20- In LERF; LLRF testing still needs to be complete with SLAC.

J1.3-01,03,04,05,07,08,10,12,13,14,15,16,17,18,19,21@SLAC