LCLS-II SEPTEMBER PROJECT STATUS REPORT

DATE:	October 2, 2020

LOCATION OF PROJECT:	Jefferson Lab

SENIOR TEAM LEAD:	Joe Preble

MONTHLY PROGRESS

Summary

A restart plan was submitted to DOE and approved.  On Monday, June 8, the Lab went to MEDCON 5; work from home will continue at least through May 2021.

Report reflects August EV data (most recent available data). JLab continues to make progress in areas supported by work from home.

Management:

EV Performance as of August close.

Overall % complete = 98.0%, SPI = 0.99, CPI = 0.98

Cryoplant System:

EV Performance as of August close.

Overall % complete = 96.0%, SPI = 0.99, CPI = 0.96

- Procurements all placed; 99% delivered; remaining contracts for4.5K CB and U-tubes, have been assigned to SLAC.

- Commissioning documentation complete

- Control software development 90%; December completion expected.  The following systems are complete:

  - Utilities, Gas Management

  - Warm Helium compressors

  - 4.5K cold box coding and bench testing

Continued to work on:

- 4.5K cold box integrated testing at SLAC

- 2K cold box bench testing

- Installation and checkout/testing support

Cryomodules:

EV Performance as of August close.

Overall % complete = 99.0%, SPI = 0.99, CPI = 0.99

39 of 40 planned BLAs at SLAC; 4 more at JLab includes additional purchase of 3; of the 4, 1 original assembly and 3 returned for rework.

- J1.3-02 (Spare) – Final Assembly; plan to ship in November.

- J1.3-11 – Acceptance testing in the CMTF will be done in October; plan to ship in December

- J1.3-20 – LERF testing complete; being prepared for shipping in October

- LERF - removal of SSAs complete and shipped to SLAC

- J1.3-01,03,04,05,06,07,08,09,10,12,13,14,15,16,17,18,19,21@SLAC