LCLS-II OCTOBER PROJECT STATUS REPORT

DATE:	November 2, 2020

LOCATION OF PROJECT:	Jefferson Lab

SENIOR TEAM LEAD:	Joe Preble

MONTHLY PROGRESS

Summary

A restart plan was submitted to DOE and approved.  On Monday, June 8, the Lab went to MEDCON 5; work from home will continue at least through May 2021.

Report reflects September EV data (most recent available data). JLab continues to make progress in areas supported by work from home.

Management:

EV Performance as of September close.

Overall % complete = 97.8%, SPI = 0.98, CPI = 0.99

Cryoplant System:

EV Performance as of September close.

Overall % complete = 95.3%, SPI = 0.96, CPI = 0.97

- Procurements all placed; 99% delivered; build-to-fit u-tubes remain to be delivered after measurements are completed.

- Remaining contracts for 4.5K CB and U-tubes, have been assigned to SLAC.

- Control software development 90%; November completion expected.

- Installation and checkout/testing support ongoing (will move to SOW/IWO with JLab Engineering Department). Final signoff of the SOW is ongoing.

- Remaining JLab project work includes:

  - Cryoplant 1 (C1) 4.5K cold box software integrated testing at SLAC; November completion expected.

  - 2K cold box bench testing at JLab; November completion expected.

Cryomodules:

EV Performance as of September close.

Overall % complete = 99.3%, SPI = 0.99, CPI = 1.00

39 of 40 planned BLAs at SLAC; 4 more at JLab includes additional purchase of 3; of the 4, 1 original assembly and 3 returned for rework.

- J1.3-20 – Shipped and arrived at SLAC on October 26.

- J1.3-02 (Spare) – Plan to ship to SLAC in November 6.

- J1.3-11 – Completed acceptance testing in the CMTF; plan to ship this last cryomodule to SLAC on November 20.

- J1.3-01,03,04,05,06,07,08,09,10,12,13,14,15,16,17,18,19,20,21@SLAC