LCLS-II JANUARY PROJECT STATUS REPORT

DATE:	February 2, 2021

LOCATION OF PROJECT:	Jefferson Lab

SENIOR TEAM LEAD:	Joe Preble

MONTHLY PROGRESS

Summary

A restart plan was submitted to DOE and approved.  On Monday, June 8, the Lab went to MEDCON 5; work from home will continue at least through May 2021.

Report reflects December EV data. The December data includes the rebaseline project planning. JLab continues to make progress in areas supported by work from home.

Management:

EV Performance as of December close.

Overall % complete = 96.9%, SPI = 1.00, CPI = 1.01

Cryoplant System:

EV Performance as of December close.

Overall % complete = 99.7%, SPI = 1.00, CPI = 1.00

- Cryoplant 1 (C1) 4.5K cold box software integrated testing at SLAC complete.

- Remaining JLab project work includes:

  - 2K cold box bench testing at JLab complete; need to cleanup comments from testing.

Cryomodules:

EV Performance as of December close.

Overall % complete 99.9%, SPI = 1.00, CPI = 1.00

All deliveries are complete. Closing down production and testing facilities is mostly complete.