## Slide 1
Closeout Report on the
DOE/SC Status Review of the
Linac Coherent Light Source-II High Energy (LCLS-II-HE) Project
SLAC National Accelerator Laboratory
December 1-3, 2020
Kurt W. Fisher
Committee Chair
Office of Science, U.S. Department of Energy
http://www.science.doe.gov/opa/

## Slide 2: Review Committee Participants
Kurt Fisher, DOE/SC, Chairperson

## Slide 3: Charge Questions
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? Are the risks associated with the LLP scope adequately addressed? Is the overall project scope properly defined to meet the preliminary KPPs? Is the proposed injector facility adequately defined and justified? Is the overall project technical progress to date appropriate at this stage of the project?
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? Is the overall project design maturity adequate at this point in the project?
Cost and Schedule: Is the LLP cost and schedule performance, including contingency utilization, reasonable and properly managed based upon project performance to date? Are the overall project cost and schedule estimates progressing adequately to support proposed CD-2 and CD-3 decisions as early as 2Q FY 2022? Is the increased preliminary point estimate adequately justified and credible for this stage of the project?
Management: Is the project being appropriately managed to advance the design effort and deliver the long lead procurements? Does the project have the necessary resources to succeed? Does the project team have sufficient expertise and experience to successfully execute the project? Are the multi-laboratory partnerships functioning effectively? Are the work plans for the next fiscal year appropriate and complete?
Risk Management: Are risks being properly managed? Is the overall risk registry sufficiently developed for this phase of the project?
ES&H: Are ES&H aspects properly addressed and are future plans sufficient given the project’s current stage of development? Has the project considered COVID-19 related safety protocols in their plans?
Recommendations: Has the project responded appropriately to recommendations from the last DOE review?

## Slide 4
4
2.1 Accelerator and FEL Physics P. Piot, NIU, G. Penn, LBL / SC 1
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? N/A Are the risks associated with the LLP scope adequately addressed? N/A Is the overall project scope properly defined to meet the preliminary KPPs? YES Is the proposed injector facility adequately defined and justified? YES? Is the overall project technical progress to date appropriate at this stage of the project? YES
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? Is the overall project design maturity adequate at this point in the project? Excluding the alternate RF gun, the overall design is adequate for this stage. There are specific concerns about HXR self-seeding that require further R&D efforts.
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? YES

## Slide 5
5
2.1 Accelerator and FEL Physics P. Piot, NIU, G. Penn, LBL / SC 1
Findings
The objective KPPs were changed from the LCLS-II-HE CD3A version. The most notable is the extension of the KPP photon energy from 12.8 to 20 keV
The plan to reach 20-keV photon energy will require the development of a lower-emittance source, currently based on a superconducting radiofrequency (SRF) gun
The 4-GeV low-energy extraction (LEX) transport line was removed from the proposed baseline. Instead the 8-GeV beam is also used for soft X-ray production.
Three additional accelerating cryomodules were included in the design to accommodate for possible lower-performing LCLS-II SRF cavities.
The removal of the LEX and longer linac improves electron beam quality even for the nominal RF gun

## Slide 6
6
2.1 Accelerator and FEL Physics P. Piot, NIU, G. Penn, LBL / SC 1
Findings (cont’d)
Start-to-end simulations of the beam dynamics combined with FEL simulations for different charges (20/100 pC) and photon energies (SXR and HXR) confirm the proposed design can support the generation of 20 microJ pulses up to 18 keV (for the NC VHF gun)
The use of a 8-GeV beam for SXR provides higher-quality electron beam
Preliminary simulations using a brighter electron source show that 20 keV photon energy can be attained
The soft X-ray (SXR) undulator period has been changed from 39 mm to 56 mm. Both 4- and 8-GeV beams can be accomodated. More undulator sections are required, but performance is improved or similar in all cases
Cryo-cooling of the HXR monochromator can improve performance and reduce fluctuations

## Slide 7
7
2.1 Accelerator and FEL Physics P. Piot, NIU, G. Penn, LBL / SC 1
Comments
The removal of the LEX beamline addresses a previous concern regarding significant phase-space degradation. It also provides extra real estate to accommodate three cryomodules
The three added cryomodules will provide further safety margin given uncertainties on the final performances of the installed LCLS-II cryomodules
The SXR undulator period was increased to 56 mm to allow for electron energies up to 8 GeV, facilitating operations without the LEX
The addition of a separate injector system (gun, bunching system, and one cryomodule) will provide a redundant electron source for improved reliability of the LCLS-II HE facility and potentially a brighter electron beam without any change to the nominal injector beamline
These changes are welcome: they add flexibility, improve reliability, and reduce complexity of the accelerator

## Slide 8
8
2.1 Accelerator and FEL Physics P. Piot, NIU, G. Penn, LBL / SC 1
Comments (cont’d)
A new electron source based on an SRF gun is considered and will be critical to reaching the proposed objective KPPs (20 keV photon energies)
The understanding of the HXR self-seeding monochromator performances has improved over the last year through more detailed simulation methods
The experience at the European XFEL reveals that HXR self-seeding is challenging at high repetition rate. It is therefore critical to carry out the planned HXR monochromator experiments at LCLS in the near future

## Slide 9
9
2.1 Accelerator and FEL Physics P. Piot, NIU, G. Penn, LBL / SC 1
Recommendations
None

## Slide 10: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? Are the risks associated with the LLP scope adequately addressed? Is the overall project scope properly defined to meet the preliminary KPPs? Is the proposed injector facility adequately defined and justified? Is the overall project technical progress to date appropriate at this stage of the project? Yes, especially in light of how recently the SRF gun was added to project.
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? Is the overall project design maturity adequate at this point in the project? Yes, given that SRF injector is just getting started.
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Yes.

## Slide 11: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Findings
Scope of injector defined, justified, and supports KPP
Technical progress is based on establishing interlab collaboration. Process is moving forward rapidly but in early stages
Extensive preliminary design and beam dynamics studies of the SRF gun injector have been proceeding well
Current risk management is leveraged on ongoing LCLS II efforts including second APEX gun and parallel low MTE cathode development supported by SLAC Accelerator Directorate
LCLS II team judgment is that SRF gun is less risky that RT at the 30 MV/m level. The key limitation to SRF is the cathode assembly (loadlock, stalk). The SRF approach has been demonstrated at 20 MV/m (WiFEL gun). With improvements to the cathode assembly, it should be able to get to higher gradients

## Slide 12: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Findings/cont.
The APEX II gun seemed like a “routine” extrapolation from the LCLS II (APEX) gun operating at 30 MV/m. However, after further evaluation and lessons from LCLS II related to dark current, RF heating, and vacuum, the APEX II approach is judged challenging.
There is a need to develop a set of milestones and decision points but the 9 year timescale for the gun program will allow sufficient time if managed well

## Slide 13: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Comments
  Going to an ultra low emittance gun makes great sense. It is the most cost effective way to achieve 20 keV photons
  Secondary injection tunnel is a large investment, but well justified as it eliminates single point failure and allows parallel high brightness source development
  New injector presents risks in SRF gun and photocathode technology as it pushes both beyond state of the art but leveraging promising data. A vigorous R&D program is therefore well justified.
  SRF is a very promising approach with the most leverage for highest gradient and lowest emittance. Cathode assembly and cathode material issues remain to be sorted out, especially at highest gradients. Higher beam energy out of SRF offers some advantages over RT even for same cathode field

## Slide 14: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Comments/cont.
  Pursuing the SRF gun development is a sensible decision. But given associated risks, development of two gun and cathode assembly prototypes should be encouraged
  Higher field RTRF is an alternative, but has problems with heat load, vacuum, and especially dark current that offer substantial risk. Although SRF is likely to succeed, it would be good to keep an eye on alternatives, especially using very low MTE cathode materials in an existing RT gun. The second LCLS II APEX-like gun does provide some backup. Tests in the available APEX gun for low MTE at the highest fields with tunable laser wavelengths should be encouraged. Alternative solutions for dark current management (like fast kickers) could be explored and would benefit LCLS II as well

## Slide 15: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Comments/cont.
  Laser development should be a strong part of the effort. Some issues like stability or pulse shaping, especially if tuning wavelength is desired, are not straightforward
  Run S2E with bending merger line included
  Strengthening in-house cathode/laser development programs to ensure supply, performance, and quality control is prudent
  Studying the injector optimization with higher MTE cathodes is encouraged (at the moment cathode MTE improvement is required in this program while the behavior of cathodes at higher gradients is unknown.)
  Radiation Safety seems well in hand, assuming that it is reviewed by outside radiation safety experts

## Slide 16: 2.2 Injector J. Bisognano, P. Musumeci, L. Cultrera
Recommendations
  Pursue SRF gun program as presented
  Engage SLAC programs to strengthen in-house cathode/laser development
  Pursue (either through collaboration or in-house) efforts to expand the knowledge of operating characteristics of photocathodes at ~> 20 MV/m gradients (QE, MTE, lifetime) in RT and SRF guns

## Slide 17: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Project Scope:
Is there adequate technical progress on the long lead procurements (LLPs)?
Yes.
Are the risks associated with the LLP scope adequately addressed?
Verification cryomodule will provide essential information.
Is the overall project scope properly defined to meet the preliminary KPPs?
Yes.
Is the proposed injector facility adequately defined and justified?
N/A
Is the overall project technical progress to date appropriate at this stage of the project?
Yes.

## Slide 18: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Design Maturity:
Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project?
Yes, at this stage of the project.
Is the overall project design maturity adequate at this point in the project?
Yes.
Recommendations:
Has the project responded appropriately to recommendations from the last DOE review?
Yes, 3 closed and 1 ongoing.

## Slide 19: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Findings
  The scope of work consists of the fabrication, testing and delivery of twenty-four production cryomodules (twenty-three 1.3-GHz cryomodules for the linac and one for the low emittance injector) and the associated cryomodule stands, beamline absorbers and interconnecting components. The design accelerating gradient and the required quality factor of the 1.3-GHz HE cavities are 20.8 MV/m and 2.7  1010 respectively. The linac output energy will be doubled from 4 GeV to 8 GeV.
  Four additional cryomodules (three for the L4 string and one for the low emittance injector) were added to the scope since last review. Benefits from this new configuration are:
    The design beam energy can be achieved while keeping LCLS-II cryomodules operating at its design gradient, 16 MV/m.
    The new configuration (23 HE CMs in L4) increases the cryoplant operation margin from 9% to 13%.
    It requires minimal removal and re-installation of LCLS-II CM.
    It mitigates the installation schedule risk for the warm beamline.

## Slide 20: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Findings (cont.)
  The choice of L3/L4 break will be determined after the cryo distribution line design and the verification cryomodule (vCM) test.
  The installation schedule of LCLSII-HE was modified. Instead of two 6-month shutdowns now one 1-year long shutdown is in the revised project plan.
  Based on design accelerating gradients for LCLS-II and LCLS-II-HE, the number of spare cavities (energy margin) is estimated to be 10 in the LCLS-II segment and 11 in the LCLS-II-HE segment.
  Verification cryomodule (vCM) work started in September at FNAL after the completion of infrastructure upgrade. String assembly was competed in November 2020 and cold mass assembly is in progress. The whole assembly is scheduled to be complete in February 2021 followed by 6-month long cold test.

## Slide 21: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Findings (cont.)
  LCLS-II-HE cryomodules may use tuners with an extended range that will be tested with the vCM. The extended tuner range is proposed to provide ‘off-frequency operation’ for alternating bunches at 4 GeV and 8 GeV.
  The mechanical design of the LCLS-II-HE cryomodule is identical to LCLS-II except for the mechanical tuners. Lessons learned from LCLS-II have been implemented in HE such as revisions to as-built, clarifying dimensions and necessary changes for mechanical tuners to provide functionality for the off-frequency operation.
  The cryogenic system design is 92% complete for CD-3A scope and 95% complete for non CD-3A scope.

## Slide 22: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Findings (cont.)
  CD-3A approval for long lead procurement of cryomodules was received in May 2020. CD-3A approval provided $80.4M for cryomodule fabrication at the partner labs and the cryogenic system engineering/procurement at SLAC. CD3-A contracts for cavities, couplers, vacuum vessels, and upper cold mass were placed. In total 91% by value of CD-3A scope was awarded. The first batch of production cavities is scheduled to be delivered in July 2021. Cavity processes from doping at the vendor will be carried out after the vCM test.
  74 leftover cavities from LCLS-II were transferred to HE. Rework of these cavities will start soon.
  New cavity doping recipe, 2N0 was verified with vertical tests. Further verification is planned with vCM.

## Slide 23: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Findings (cont.)
  The new doping recipe 2N0 was transferred to the vendor. 10 new cavities were fabricated and doped with the new recipe at the vendor. All 10 cavities passed the LCLS-II-HE requirements. Eight of them will be used for vCM.
  LCLS-II construction delay partially due to COVID-19 impacted LCLS-II-HE such as delaying the vCM fabrication and limiting availability of personnel for HE.
  Production CM assembly starts in September 2021. COVID impact is projected in planning.
  Test for production cryomodules is scheduled to start in Q2FY22 and RF commissioning of cryomodules in the SLAC tunnel is in Q3FY26.

## Slide 24: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Comments
  Cavity R&D related to HE requirements has made excellent progress such as identifying nitride precipitates and quenching field dependencies on electro-polishing temperature. Based on a hypothesis and understanding, a new cavity process flow has been developed.
  A significant achievement on deploying the new doping recipe at the cavity vendor has been made. 10 new cavities processed by the vendor met or exceeded requirements for HE. The measured average accelerating gradient and quality factor during the vertical test were 26 MV/m and 3.6  1010 respectively. The vertical test results are satisfactory pending further verification with vCM.
  The flux expulsion requirement for HE is tighter than LCLS-II requirement. Experiment using single cell cavities suggests higher temperature heat-treatment at 950C ~ 975C for flux expulsion required for HE. Cavities in vCM were heat-treated at 950C. In addition, bandwidth of HE is narrower than that of LCLS-II. The vCM test will verify whether microphonics is acceptable for operation at HE conditions.

## Slide 25: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Comments (cont.)
  Collaboration between partner laboratories is in place. The personnel assembled between SLAC, FNAL and JLab are working very well as an integrated team. The team is highly experienced and key members for LCLS-II continue working for HE. This reduces the likelihood of loss of institutional knowledge and is important for complex cryomodule systems.
  Committee supports the proposed linac configuration where three cryomodules are added in L4.
  The cryomodule production schedule is success-oriented and is developed by incorporating lessons learned from LCLS-II. The partner laboratories have other project commitments that overlap with LCLS-II-HE. These competing priorities impose a potential schedule risk.
  74 failed or leftover cavities from LCLS-II were transferred to HE. The team estimates that >40 cavities can be qualified for HE after rework and that additional cavity procurement for 4 additional cryomodules may not be required.

## Slide 26: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Comments (cont.)
  Continued efforts for incorporating the lessons learned from LCLS-II such as infrastructure upgrade, revisions to as-built, QA, vendor oversight, shipping/handling, and management, are commendable.
  Committee supports the approach of a standardized methodology of assembling and testing CMs at FNAL and JLab. In particular, implementing mass flow instrumentation at the JLab LERF facility will be very beneficial.
  It was presented that choice of L3/L4 break will be determined after cryo distribution line design and vCM test. Since actual cryogenic loads from LCLS-II at high-Q operation will be available in FY23 or later, the optimal choice of L3/L4 break will be unknown by then.
  Production cryomodule testing is scheduled to start in Q1FY22 and RF commissioning of cryomodules in the SLAC tunnel will be in Q3FY26. A plan should be carefully developed for a long-term storage of cryomodules at SLAC site including monitoring of some cryomodule parameters.

## Slide 27: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Comments (cont.)
  vCM testing will provide essential information for the success of LCLS-II-HE. The test results and lessons learned from vCM test should be reflected in the production cryomodules. Additional tests specific to HE should be detailed in the cryomodule test plan and reviewed including;
    Verification of the new doping recipe for an extended period
    A full power test of the couplers at LCLS-II-HE design gradient or slightly higher and at both nominal frequency operation and off-frequency operation for an extended period
    Integrity test of the new tuner assembly during high power operation (fatigue, impact on piezo tuner, impact on coupler)
    Field flatness at nominal frequency operation and off-frequency operation
    Microphonics measurement at nominal frequency operation and off-frequency operation and, microphonic compensation using piezo tuner
    Multipacting processing and validation of in-situ plasma processing
  Enough time should be dedicated for vCM test to include all planned activities with adequate margin.

## Slide 28: 2.3 Cryomodules S. Kim, ORNL / S. Barbanotti, DESY / C. Madec, CEA / Subcommittee 3
Recommendations
  Develop a long-term storage plan for HE cryomodules at SLAC by the next DOE review.
  Evaluate the leftover cavities from LCLS-II and identify the number of those cavities qualified for HE by the end of December 2021.
  Conduct a review of the vCM test plan by the end of February 2021.

## Slide 29
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? Linac and RF Power Systems do not have any LLPs. However eighteen 1st-article 7-kW SSAs were procured. Other critical LLPs have been awarded and additional LLP (SXR Undulator Pole Magnet) is pending.
Are the risks associated with the LLP scope adequately addressed?
Yes.
Is the overall project scope properly defined to meet the preliminary KPPs?
Yes for Linac and RF Power Systems.
Is the proposed injector facility adequately defined and justified?
Yes for this stage of the project. Focused R&D is needed to mature the design. The proposed injector will provide a lower emittance beam allowing to extend the photon energy and increase reliability with a redundant source.
Is the overall project technical progress to date appropriate at this stage of the project?
Yes. Project is capitalizing on the LCLS-II experience and incorporating lessons learned.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 30
2. Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project?
Yes for Linac and RF Power Systems.
Is the overall project design maturity adequate at this point in the project?
Yes. The overall Accelerator Systems design maturity is estimated around 61%.
7. Recommendations: Has the project responded appropriately to recommendations from the last DOE review?
Yes. The remaining two are expected to be closed before CD-2/3.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 31
Findings - Linac
LCLS-II-HE will double the energy of the linac from 4 to 8 GeV
Recent design changes:
  The Low Energy Extraction and 4 GeV transfer line has been eliminated.
  To double the energy from 4 to 8 GeV, 23 CM will be added - three more of what was planned at CD-1.
A low emittance injector and SRF gun has been added to the scope.
Accelerator Systems manages integration of HE electron beam equipment.
The Accelerator Systems (1.03) scope includes:
  1.03.01 Management and Integration.
  1.03.04 Accelerator Linac - SRF Linac and Cryo Distribution System (CDS).
  1.03.05 Beam Transfer Line, Beam Dump, SXU Undulator Upgrade and Installation.
  1.03.06 SXR Undulator ( LBNL).
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 32
Findings - Linac
System Requirements
  26 out 46 PRD directly flow and apply to Accelerator Systems FRS
  10 out 24 L3 FRS’s apply to Accel Sys.
Accel Systems design status and maturity overall 61%.
  1.03.04 SC Linac and CDS ~59%.
    Roughly 10 % is new design, 38 % are LCLS-II design and the remaining part is a modification of LCLS-II design.
    HPRF design benefits from the LCLS-II and hence several sub-system are mature. 1st article SSAs are now under test.
    Vacuum design is based on the procedures and practices developed for LCLS-II. New design is required for the removable section.
  1.03.05 TL and SXR Upgrade ~ 64%.
  1.03.06 SXR-HE (LBNL) ~ 64%.
Development of the CD 2-3 scope is underway.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 33
Findings - Linac
Till now COVID-19 had a minor impact on Linac and RF Power Systems activities. In particular:
  the conceptual design is in the layout phase;
  thanks to effective collaboration between HE and AD/METSD the design team was identified and had transitioned to working remotely fairly well;
  to cope with limitations due of travel restrictions, team performed FAT and SAT of SSAs remotely developing the necessary procedures.
Managing and Staffing
  System manager onboard - Mar 2020
  CDS Scope Transfer from WBS 1.02 to WBS 1.03 - May 2020
  July 2020 - Accelerator Systems management staffing complete
  LCLS-II-HE relies on the matrixing of resources from the line organizations
Accelerator System cost/schedule is now under revision
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 34
Findings - Linac
The design gradient of the new 23 LCLS-II-HE CM is 20.8 MV/m.
The addition of three more CMs, instead of one as previously planned, allows to continue to operate the LCLS-II CMs at their design gradient, i.e. 16 MV/m, instead of pushing them to 18 MV/m as in CD-1.
This is a mitigation of the risk related to the actual gradient that will be achieved by LCLS-II cavities.
With the new layout, which eliminates the LEX, only one LCLS-II CM will have to be removed and re-installed in HE.
RECENT ACCOMPLISHMENTS in design and prototyping:
  Oct 2019 - Procurement of the First article (Qty 18) of the 7kW SSAs;
  Apr 2020 - Initiate the Integrated Linac Design Layout;
  Jun 2020 - Down selected the baseline design in favor of the SXR8GeV;
  Sep 2020 - 10/18 First Article units of 7kW SSA built, FAT passed, shipped to US.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 35
Findings - Linac
Layout has been updated to include recent design changes.
3D models have been developed.
L3/L4 warm transition has been reviewed:
  optimization purposes (simplification of the layout, reduction of pumping, etc.)
  Primary design pressure criteria: pressure < 1x10-10 Torr at Cryomodule.
  Molflow Analysis based on the Differential Pump Analysis performed to confirm (5.3 10-11 Torr at Valve extension).
L4 extension:
  Main challenges are related to the removable section (about 14.8 m for rigging Cryomodules / other equipment) and to particle free specifications.
  Primary design pressure criteria: pressure < 1x10-8 Torr.
  Secondary design criteria: reasonable recovery time following maintenance.
Dogleg:
  LCLS-II DogLeg Transition will be moved further East and will be relocated with minimal modifications.
Next steps will focus on the detailed design of the L3/L4 warm transition, L4 extension, dogleg and early vacuum design of L3/L4 transition and L4 extension.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 36
Findings - HPRF
The scope of HPRF basically is to duplicate the LCLS-II system for L4 with minor modifications (Accelerator Systems Scope) and to power the SRF Injector ( Injector Systems Scope).
Included in the Accelerator Systems Scope are:
  23 CMs in L4 plus one moved from L3, i.e. 24 CM in total;
  the layout of 192 new housing ceiling WG systems in L4 CMs;
  192 new high power (7 kW) 1.3 GHz SSAs;
  192 WR 650 directional couplers, isolators - identical to LCLS-II;
  ~2 miles of WR640 WG runs - identical to LCLS-II;
  48 radiation shields.
Included in the Injector Systems Scope are:
  1 of 185.7 MHz, 4 kW CW SSA and new transport line for the gun;
  1 of 1.3 GHz 3.8 kW CW SSA and new transport line for the buncher;
  8 of 1.3 GHz, 3.8 kW CW SSA and new transport line for the CM in the injector.
Lesson learnt from LCLS-II experience are being implemented.
LCLS II documentation with minor revisions will be applicable to LCLS-II-HE.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 37
Findings - HPRF
RF power requirements for the new LCLS-II-HE cavities are based on:
  Gradients: for LCLS-II cavities upstream BC1 no change, for LCLS-II downstream cavities 16 MV/m nominal, for LCLS-II-HE cavities 20.8 MV/m nominal;
  30 uA max beam current, power coupler Qext = 6.0e7 for cavities downstream of BC1 (4.1e7 for LCLS-II) detuning 10Hz max, rf loss 8% tuning overhead 8%
Based on the requirements:
  no change is needed to the existing 3.8 kW LCLS-II SSAs. Actually such power level allows gradients up to 19.9 MV/m;
  for the new HE cavities, the SSAs will be capable to operate up to 7 kW ( <1dB compression). 7 kW units will allow up to 26.0 MV/m gradient.
Eighteen 7 kW SSAs were ordered as first article procurement.
The new units will have the same topography as the 3.8kW LCLS-II ones, same connectors and fittings. Major changes will be:
  inclusion of new features such as reset buttons, 120 VAC and LAN switches;
  higher water flow and higher pressure drop requirements (3.9 GPM to 7.4 GPM and 15 PSI to 34 PSI).
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 38
Findings - HPRF
Recent noted accomplishments:
  18 isolator, 18 directional couplers ordered and passed FAT and delivered (2 @SLAC, 8 @FNAL and 8 @JLAB);
  18 1st article 7kW SSAs ordered and passed FAT (2 @S SLAC, 8 @S FNAL and 8 will be shipped to JLAB in Dec 2020).
Validation tests:
  acceptance procedure and EPICS control software were developed at SLAC and provided to Partner Labs;
  acceptance tests conducted at SLAC and at FNAL, soon to be performed at JLAB;
  first two SSAs delivered to SLAC also passed EEIP .
12 Months look ahead for HPRF will focus on:
  Q1 - Complete the HPRF plan and budget
  Q2 - Work on Document lists and revisions
  Q3 - Work on Housing Ceiling WG conceptual layout once Penetration allocations are determined
  Q4 - Work on Housing Ceiling WG layout drawings
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 39
Findings - LLRF
LCLS-II-HE LLRF design is mostly a duplicate of the LCLS-II except possibly for the new SRF injector.
Design activities benefit from the infrastructure built at SLAC to support development, troubleshooting and testing of LLRF equipment and of the support of the collaboration established for the LCLS-II LLRF with the partner labs.
Field control requirements specifications:
  Regulation (> 0.1 Hz) 0.01 deg rms and 0.01% rms, assuming less than 1% beam current fluctuation and less than 10 Hz microphone detuning.
  Resonance control - Piezo tuner <1 Hz.
The LLRF system includes:
  Hardware/firmware:
    PRC ( precision receiver chassis);
    RF Station (generates independent rf signal for 2 cavities. Detune freq. Calculation, PI loop control);
    Resonance control (Piezo, stepper motor, temp, interlock processing).
  Software ( automated scripting, channel access, transition between nodes).
  EPICS (all control displays and waveform, cavity control interface, hardware health)
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 40
Findings - LLRF
For the 24 additional CMs, 48 additional LLRF systems are required (one LLRF system serves 4 cavities).
Long lead time items require approximately 6-8 months delivery
Firmware provides flexibility for potential upgrades, e.g. potential need for Active Resonance Control (ARC)
Leveraging LCLS-II LLRF development helped the team to advance the LCLS-II-HE LLRF design. As the result, the LLRF controls system software and firmware are mature.
The system is ready for HE cryomodule testing at both CMTF @ FNAL and LERF @JLAB. HE has provided equipment to continue operating the PL test stands and LERF with the HE LLRF controllers.
  All modes of operation tested (SEL, SELAP, Pulsed), as well as SSA and LLRF control, user interfaces, calibration routines and tuning scripts
SLAC is testing LLRF system hardware and rack integration with full set of hardware installed in production test rack, cavity emulator for system testing, EPICS interfaces and control, waveform readouts.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 41
Findings - LLRF
12 months outlook for LLRF is focused on:
  Building LLRF chassis to replace the equipment kept in the HE CM test stands:
    5 racks (2.5 cryomodules) worth of LLRF chassis
    production by vendors who are able to meet SLAC qualifications.
  Use of off-site vendors to simplify production of large quantities of LCLS-II-HE LLRF chassis .
  Ensure the test stands at FNAL and JLab are ready for CM tests with LCLS-II-HE LLRF systems, in particular for vCM at FNAL ready for 1.3 GHz testing in Dec. 2020.
  Build and test replacement hardware for systems sent to FNAL and JLab to ensure that LCLS-II commissioning remains on schedule.
  Complete RF baseline doc, cost estimates and planning.
  Develop design and baseline for the new injector.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 42
Comments - Linac
We commend the Accelerator Team for their accomplishments since the last project review and their well-prepared, detailed and informative presentations at this review.
We are concerned about two high priority projects with notable overlaps. Unpredicted delays caused the pandemic and other laboratory’s priorities could further complicate resource availability for both LCLS-II and LCLS-II-HE.
We support the decision to procure three additional CMs to mitigate performance risks. With this addition, the LCLS-II CMs will continue operating at 16 MV/m. In addition, this may relax the operating gradient of the new LCLS-II-HE cavities if needed.
Eliminating LE extraction at the 4 GeV TL creates space for 3 additional CMs without impacting the adjacent program. In addition to technical benefits, this mitigates any schedule risks to the warm beamline. We support this decision.
Project must ensure that Cu-linac operation does not negatively impact the LCLS-II-HE installation activities, especially during the peak activities periods. Resource availability and sharing issues should be addressed accordingly.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 43
Comments - Linac
We support the addition of a 2nd injector with high gradient SRF gun . This will increase the operational reliability with a redundant source. However, it presents significant technical and schedule challenges to the project.
Timely performance results of the vCM are crucial to ensure reliable operation of the LCLS-II-HE linac at the on-line nominal gradients. This should be one of the project’s high priority tasks before the project is baselined.
The team is encouraged to fully utilize RF test beds ( at partner labs and SLAC) to continue testing and evaluation of relevant rf systems.
The overall design maturity of the linac technical systems appears to be appropriate for this stage of the project. A significant number of PRDs for the accelerator have been released. Continue working on the remaining documentations needed for CD-2/3.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 44
Comments - Linac
Although in the new configuration only one CM is relocated, we consider the removal activity to be critical and presents a risk. It requires a detail plan to be executed by highly qualified and experienced personnel.
Tunnel work is expected to be completed during the planned long shutdown. To assure success, the project has already started to develop an installation schedule for the CM and the warm beamline including the dependencies. We encourage the project team to continue to review and adjust their plan taking into account other project priorities, workload, and other dependencies.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 45
Comments - HPRF
Similarities between the LCLS-II and LCLS-II-HE HPRF systems will reduce the technical risks to the project. Stay vigilant on supply chain and pay close attention to QC/QA to mitigate nonconformities before the components are shipped. Provide sufficient and trackable vendors oversight.
The procurement of the 7kW 1st article HPRF systems is progressing well. The team has done a very good job.
Continue exploring and utilizing remote FAT as well as in-house remote testing as much as possible during current travel restrictions.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 46
Comments - HPRF
We consider the twelve months look ahead plan to be reasonable. The team has done a good job applying lesson learned from LCLS-II to LCLS-II-HE. The team should continue this practice as it prepares new and revised documentations needed for CD-2/3 review.
Although the installation of RF power and controls systems will be done in the gallery above the linac tunnel and does not impact LCLS-II operations, the final connection of control cabling and RF power waveguide to the installed cryomodules in the tunnel will have to be done during the LCLS-II shutdowns. The team should continue working on the planning and intergroup coordination efforts to make this activity as seamless as possible.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 47
Comments - LLRF
We appreciate the last-minute presentation and the additional information the team provided us.
The team has developed a plan to deal with the hardware obsolescence. We encourage the team to revise and update their plan with the appropriate risks mitigation as the project prepares for CD-2/3 review.
LLRF design is mostly identical to the LCLS-II, except possibly for the new SRF injector. The similarities will streamline the LCLS-II-HE LLRF Systems design process and will reduce the risks. Team should review the design and if needed, to include any modifications/updates including firmware/software required by the LCLS-II-HE CMs operation.
Keep pursuing the development of cavities active resonance control (ARC) in case it is needed for microphonics compensation.
The new injector with SC RF gun will require additional new LLRF features and enhanced functionalities. Resources should be analyzed and captured.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 48
Comments - LLRF
Since a large portion of the LLRF components are COTS procurements - some with longer procurement periods- timely selection of vetted qualified vendors becomes extremely important to stay ahead of schedule. The team should stay vigilant and be prepared to address fabrication and delivery delays that could delay onsite test and qualification of hardware.
We encourage team to strengthen its remote testing capabilities as much as possible.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 49
Comments - LLRF
LLRF system has been proven reliable for CM testing in LCLS-II, many testing tools have been built into the LLRF software/firmware set. The test stands at FNAL and JLab are important tools to test, evaluate, and improve the LLRF functionalities. They also have been used to train personnel. We commend the team for this work.
LLRF collaboration remains strong and ready to help if additional test or control features are needed. We consider this to be an important asset to both LCLS-II and LCLS-II-HE Accelerator Systems.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 50
Recommendations
Identify and evaluate potential resource and schedule risks and impacts of both the LCLS-II operations and other Laboratory high priority projects on the Linac and RF Power Systems. Develop a prioritized task-oriented, risk-based resource plan and schedule by CD-2/3.
Prepare a document that incorporates appropriate lessons learned from LCLS-II LLRF system experience. Use this document to analyze next phase of resource and schedule planning that encompasses any new functionalities that might be required for the LCLS-II-HE by CD-2/3.
2.4 Linac and RF Power Systems
A. Nassiri, ANL and A. Fabris, Elettra
Subcommittee 4

## Slide 51: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? Are the risks associated with the LLP scope adequately addressed? N/A. Is the overall project scope properly defined to meet the preliminary KPPs? Yes. Note there are no preliminary KPPs specific to the cryogenics scope. Is the proposed injector facility adequately defined and justified? Is the overall project technical progress to date appropriate at this stage of the project? Yes.
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? Yes. Is the overall project design maturity adequate at this point in the project? Yes.
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Yes.

## Slide 52: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Project scope definition
Unlike for LCLS-II, the HE CDS and the installation of HE cryomodules is combined into the same WBS 1.03.
The CDS reference design is in a conceptual design state, with preliminary design review targeted for April 2021. Final design review is planned for the end of calendar year 2021. There is an ongoing effort to update costs from CD-1 in preparation for baselining.
None of the WBS 1.03 effort falls within the CD-3a scope.

## Slide 53: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Project scope definition
The new CDS scope in support of the upgraded injector is expected to still be at the conceptual state at CD-2/3.
There is not yet an Interface Controlled Document (ICD) that lists the interfaces with, and defines the expected performance for, the LCLS-II cryoplants inherited by the HE project.
There are two BCRs affecting the WBS 1.03 that are currently pending:
  Unpacking the CDS scope after transferring from the WBS 1.02 to WBS 1.03
  New injector scope

## Slide 54: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Project resources
The organization supporting the WBS 1.03 cryogenic scope was staffed in August 2020. 80% of the team are veterans of the LCLS-II project.
Accelerator Systems have to date a negative schedule variance of 648 k$, apparently due to lacking resources. The LCLS-II project has now been prioritized by the lab.

## Slide 55: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Project resources
There is a draft Service Level Agreement (SLA) between the Accelerator Systems WBS and Accelerator Division/Mechanical Engineering & Technical Support Division (AD/METSD). This SLA is focused on the scope of work to be performed in FY21, primarily work to refine the reference design. The team expects to finalize and approve this SLA by the end of calendar year 2020.
Staffing plans for the out years will be discussed early next calendar year.

## Slide 56: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Project resources
There has been minimal direct impact on the HE cryogenics work due to COVID since the design effort is able to be done remotely. However, there is a significant indirect impact caused by the delay in LCLS-II commissioning due to COVID
The summarized labor schedule for the HE project shows two peaks:
Approx 23 FTE in FY21, primarily driven by engineering.
Approx 32 FTE in FT24, primarily driven by installation labor. This planned labor needs to be redistributed to align with the single 12-month installation window.
Commissioning labor is under the 1.08 WBS.

## Slide 57: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – CDS design strategy
Unlike for LCLS-II, SLAC will lead the conceptual design of the HE CDS components. The detail design is expected to be done by the supplier.
Overall the HE cryogenic system reference design is, on average, at 59% maturity per the weighted roll-up estimate.

## Slide 58: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – CDS reference design details
The L4 Distribution Box design will use all of the same major components, with some simplification and better integration of the safety valve exhaust based on lessons learned from the two LCLS-II units.
If the Feed Cap is used (and the Tee configuration proposal is not adopted), the team plans to improve the design of the support and the interface to the next cryomodule based on the LCLS-II lessons learned.
The Tee will be an entirely new design, if implemented.

## Slide 59: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – CDS reference design details
The End Cap will be modified from the reference design to add features allowing fast cool down.
The size of the subatmospheric return line (line B) in the 240m surface transfer line will be increased from 10 NPS to 14 NPS to reduce the pressure drop, which is critical to ensure adequate cryoplant capacity.
The existing LCLS-II interface box will be modified, and a new interface box supporting L4 will be added. The team plans to engage the original manufacturer of the LCLS-II interface box for the modification.

## Slide 60: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Procurement plan
It is expected that the procurement strategy will result in “veteran”/”known successful” suppliers being selected for the HE CDS work.
These longer-lead procurements (not rising to the level of the CD-3a LLPs) are planned:
  DBX vacuum shell and HX
  Multi-line interface box with large subatmopsheric isolation valve

## Slide 61: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Installation plan
The HE CDS installation will require the removal and re-installation of EC/FC in addition to relocation of one LCLS-II cryomodule; these are new activities that were not experienced during the LCLS-II installation, and therefore will require new procedures. The remainder of the cryogenic installation will mimic LCLS-II, utilizing the same support equipment such as lifting fixtures, glove boxes, clean room, welding procedures, etc.
The installation schedule will utilize maintenance downtime periods (PAMMs) as well as one 12-month shutdown.

## Slide 62: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Balancing actual loads with actual plant performance
The project team’s work demonstrates an understanding of the risk of insufficient usable cooling capacity to support cryomodule operation at a level meeting the objective KPPs. The project is formally tracking this risk in terms of underperformance of the two major cryosystem components inherited from LCLS-II (the cryoplants and the cryomodules), with a focus on the cryomodules.
The risk of insufficient usable cooling capacity is potentially aggravated by:
  Imbalance of the loads assigned to each plant
  Pressure drop along the subatmospheric return transfer line
  Static heat leak into the CDS

## Slide 63: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Balancing actual loads with actual plant performance
The team plans to mitigate the risk of insufficient usable cooling capacity by:
  Detailed process calculations leading to an optimized CDS reference design, including making the best initial guess at the location of the split between the L3 and L4 linacs.
  (Counterintuitively) Adding three more cryomodules to L4, enabling the CM gradients to be lowered overall.
  Adjusting the CM gradients throughout the facility as a means of balancing the loads assigned to each plant. Via simulation, the project team demonstrated the effectiveness of this approach.

## Slide 64: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Balancing actual loads with actual plant performance
The team plans to mitigate the risk of insufficient usable cooling capacity by:
  Reducing the pressure drop along the subatmospheric return transfer line by (a) enlarging Line B within the L4 surface transfer line and/or (b) iterating on the design of the 2K-4K heat exchanger within the Distribution Box. Frustratingly, increasing the diameter of Line B reduces the pressure drop while increasing the static heat leak.

## Slide 65: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Balancing actual loads with actual plant performance
The team plans to mitigate the risk of insufficient usable cooling capacity by:
  Adding a Tee section within the L4 linac, which allows deferral of the choice of L3/L4 split location until after the team has the benefit of the LCLS-II commissioning experience and as-installed performance data. The Tee section is expected to lengthen the L4 linac by 2.5m, and due to tunnel space constraints may eliminate the opportunity to add one of the 3 planned additional cryomodules.

## Slide 66: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Balancing actual loads with actual plant performance
The project team has engaged CF in evaluating the possibility of cutting some of the tunnel wall in the S10 area. This change would make the Tee proposal more desirable because all 23 CMs could be used with no cost to the maneuverability of a replacement CM.

## Slide 67: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Other CDS challenges
A modification to the end cap is planned to enable fast cooldowns (FCDs) of the L4 cryomodules in the downhill feed direction, using one or both of lines C and D as return paths to prevent inadvertent early cooldown of adjacent cryomodules due to the tunnel slope.

## Slide 68: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Maintenance configurations
The HE project removes cryoplant redundancy that was considered a benefit to LCLS-II.
The project team plans to incorporate crossover features into the CDS reference design which will enable either cryoplant to maintain the complete linac at 4K during extended maintenance activities at one plant.
In addition, the project team is considering proposals to incorporate crossover features which enable either cryoplant to provide a reduced amount of 2K cooling to the entire linac. This degraded operating mode could support limited physics activities, perhaps at 5 GeV.

## Slide 69: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Findings – Maintenance configurations
The L4/CP2 interface box reference design will include a large isolation valve in line B, and a corresponding bypass, to enable maintenance of the CP2 2K cold box while holding load at 4K, avoiding the need for 300K warmup of the linac. The valve is to have the lowest pressure drop feasible.

## Slide 70: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Comments
The cryogenic team should be commended for advancing the project in this challenging time. The large amount of work that is complete is impressive.
The Cryogenic Distribution System (CDS) reference design is advancing towards preliminary design; the team should be commended for evaluating many technical solutions towards finding optimal system architecture.

## Slide 71: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Comments
The project strategy is to utilize LCLS-II CDS components with minimal or no changes and to award design-build contracts to experienced vendors who have delivered these components to LCLS-II. The subcommittee would endorse the development and approval of an acquisition plan for CDS elements that supports this strategy.

## Slide 72: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Comments
The subcommittee would support adding a specific risk in the register for insufficient usable cooling capacity from the LCLS-II cryoplants. This risk could be considered equivalent to CM underperformance and would be mitigated the same way (i.e. by installing more cryomodules and lowering gradients which reduces overall heat load), and if so, the project should state that. Adding potential CMs should be reflected in an updated safety analysis including safety device sizing.

## Slide 73: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Comments
The subcommittee supports a decision to add the Tee element to the L4 CDS, and locate the distribution box in an optimal location near the Tee. This is considered an effective mitigation of the risk of suboptimal heat load distribution on the both cryoplants. Addition of the Tee enables deferral of the decision of where to locate the split between the L3 and L4 linacs until well after successful LCLS-II commissioning, enabling that decision to be made with the best possible information.

## Slide 74: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Comments
The required level of cryoplant redundancy to support HE operation should be defined; this requirement should be developed and supported with detailed case analyses. By way of this use case analyses, evaluate what physics objectives can be accomplished in the degraded operating mode with a single plant at 2K. Compare the downtime incurred by changing cryogenic jumper connections, changing plant controls, etc. with the downtime incurred by correcting the root cause failure of the tripped cryoplant.

## Slide 75: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Comments
Part of the LCLS-II HE CDS team is also committed to support the LCLS-II activities. Given this, the group appears under-resourced to complete the deliverables required for the April 2021 PDR for the CDS overall reference design. Consider having respective process and design resources work 100% on the required PDR documentation without being drawn into LCLS-II commissioning activities. The required deliverables for this review are well defined.

## Slide 76: 2.5 Cryogenics N. Laverdure, TJNAF / Subcommittee 5
Recommendations
1. Within six months, develop risk analysis and mitigation measures for a scenario in which cryogenic capacity from the LCLS-II cryogenic system is insufficient. Mitigations for each risk should be developed and may include adding more cryogenic capacity, lowering the average gradient of the entire linac by increasing the number of cryomodules, etc.
2. Within six months, develop cryogenic system availability analysis to assess critical elements and identify associated mitigation measures to meet the overall project availability requirement.
3. Within one month, identify and devote necessary resources to promptly complete the CDS system reference design.

## Slide 77: 2.6 Undulators J. Pflueger, DESY retired / Subcommittee 6
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? Are the risks associated with the LLP scope adequately addressed? Is the overall project scope properly defined to meet the preliminary KPPs? Is the proposed injector facility adequately defined and justified? Is the overall project technical progress to date appropriate at this stage of the project?
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? Is the overall project design maturity adequate at this point in the project?
Recommendations: Has the project responded appropriately to recommendations from the last DOE review?
Findings
Comments
Recommendations

## Slide 78: 2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
. Project Scope:
  Is there adequate technical progress on the long lead procurements (LLPs)? Yes
  Are the risks associated with the LLP scope adequately addressed? Is the overall project scope properly defined to meet the preliminary KPPs? Yes
  Is the overall project technical progress to date appropriate at this stage of the project? Yes
Design Maturity:
  Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? Yes
  Is the overall project design maturity adequate at this point in the project? Yes
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? There were none. This is the first review for the SXR undulator for LCLSII-HE

## Slide 79: 2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
Findings:
The 8GeV modifications only affects the SXR Undulator line not HXR.
The SXR Undulator line was originally optimized for 4GeV and will now be modified to operate at 8GeV. The photon energy range being the same. The LEX will be removed creating space for three additional crymodule.
At 8GeV now 30 SXR Undulator segments are required.
The 21 existing SXR Undulators will be reused but need reconstruction; Increased period length from 39 to 56mm. This requires new magnet structures for these devices.
The existing gap separation drive systems will be re-used with moderate modifications such as force compensation springs and absolute linear encoders.
9 new SXR undulators are needed in addition.
Finally the SXR will comprise 30 undulator segments .
All redesign work of the SXR undulators as well as the procurement of the new magnet structures will be handled through LBNL taking advantage of the LCLS II experience.

## Slide 80
2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
Findings cont‘d:
The magnet structures will be delivered to and mounted by LCLSII.
LCLSII-HE scope for SXR modifications includes:
  Exchange of the old magnet structures with against the new ones with
  Exchange of compensation springs,
  attachment of new absolute encoders will be done by LCLSII-HE. The magnet structures
  Magnetic measurements and tuning in the Magnetic Measurement Facility at SLAC,
29 Phase Shifters with increased Phase Integral are needed to match with the modified undulator segments.
The existing 20 Phase Shifters will be modified accordingly and equipped with modified new magnet structures.
9 new Phase Shifters need to be purchased in addition.
All phase shifter work will be taken care by LCLSll-HE/SLAC
The SXR (SXRSS ) self seeding chicane needs to be modified with stronger magnets and a new vacuum chamber with cryogenic crystal cooling, will be organized by LCLSII-HE/SLAC.
For LCLS II undulator vacuum chambers were prepared for water cooling. Cooling water is provided but at present chambers are not connected.
So far in the section for the new nine segments no cooling is foreseen so.

## Slide 81
2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
Findings cont‘d:
The exchange of the old vs. modified undulator segments will be done in maintenance breaks of a few days during operation. It exends over more than two years from Q1/24 to Q2/26.
The presented time schedule is challenging. De-installation Mechanic refurbisment , Magnetic measurement & tuning and re-installation as well as commissioning are closely entangled.
The capacity of the Magnetic Measurement Facility appears to be a Bottleneck.
For mitigation an extension of the lab to accomodate a second bench is discussed.
Water cooling of undulator chambers is already available for the installed 21 segments and is planned for the extension in SXRCELS17-25 as well.
For LCLSII-HE water cooling is considered essential.
Cooling water temperature in the vacuum chambers needs to be controlled. This is essential for FEL operation, however is so far not on the project scope.

## Slide 82
2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
Comments:
This is the first review of the LCLSII-HE SXR undulator system
There is rich experience from LCLS II which leverages the modifications and new production of SXR undulator systems and facilitates planning and cost estimates.
The exchange of the undulator segments extends over more than two years from Q1/24 to Q2/26. Exchange will be done in maintenance days in lots of 2-3 segments.
In this time new modified segments are merged and operated at 4GeV together with the old ones.
The exchange must be well synchronized with de-installation, mechanic modifications, magnetic measurements and tuning and re-installation. Could be a logistic challenge.
Short commissioning time of the SXR line after undulator exchange is of great importance. No experience exists so far exists with the sliding exchange and time requirement for commissioning of undulator segments.
  The exchange of undulator segments with against ones with with only minimum or no impact on FEL operation is of key importance of the installation extending ove more than two years.

## Slide 83
2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
Comments cont‘d :
  Magnetic measurements in the MMF at SLAC is a bottleneck and are a risk for installation schedule.
From operational experience with LCLSII fast re-commissioning afer a new installation of undulator segments should be doable without problems.
Temperatue control for vacuum chambers is essential for HE operation. So far it is not in the baseline. There are discussions between LCLSII and operations about responsibility.

## Slide 84
2.6 Undulators Joachim Pflueger, Dean Hidas / Subcommittee 6
Recommendations:
Make an assessment of the time needed for commissioning after undulator exchange. If needed make a Plan B if time gets too long. Date: By next review.
Set up a detailed plan for the entangled activities for the exchange of the undulator segments of the SXR considering all involved acivities: Deinstallation, transport, exchange of magnet structures, refurbishment of drive mechanics, magnetic measurements & tuning and re-installation in LCLS II. Date: By next review.
Develop a plan to mitigate the bottleneck for the magnetic measurements. Date: By next review.

## Slide 85: 2.3 X-ray Endstation J. Wang (ANL), W.-K. Lee (BNL) / Subcommittee 3
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature to support the approval of CD-3a and to authorize long-lead procurement? N/A Is the overall project design maturity adequate for this stage of the project? Yes
Technical: Is the technical progress to date sufficient to support the LLP execution? Are the proposed LLPs reasonable? Are the risks associated with the LLP scope adequately addressed? Is the overall project technical progress to date appropriate at this stage of the project? N/A
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Yes

## Slide 86: 2.3 X-ray Endstation J. Wang ANL, W.-K. Lee (BNL) / Subcommittee 3
2.3.1 Findings
The XES scope is significantly enhanced and broadened.
Correspondingly, the funding profile is modified to construct one new endstation (DXS) and upgrade four endstations XPP, CXI, NXI, MFX.
LCLS-II-HE delivers 100 kHz (up to 1 MHz), photon energy up to 20 keV, and femtosecond x-ray pulses to all the HXR endstations with an x-ray beam power up to 200 W.
All endstations are ‘Day-One’ ready (early finish CD-4a, FY26 Q4) for high-rate experiment.
New laser systems and infrastructure similar to the existing one in the NEH is included in the scope to provide pump laser pulses to all HXR stations. A new system will be installed in the NEH to serve XPP and another in the FEH to serve DXS, CXI, NXI, and MFX.
The plan is to repurpose the current MEC hutch for housing the new FEH laser system.
The e-pix based new detector systems are planned for all instruments in the endstations.

## Slide 87: 2.3 X-ray Endstation J. Wang, ANL, W.-K. Lee (BNL) / Subcommittee 3
2.3.1 Findings (continued)
The new DXS endstation has the inelastic x-ray scattering (IXS) instrument with world-leading spectral brightness. The current design specifies the x-ray photon energy resolution of 3 to 5 meV.
The upgraded XPP provides high-rep-rate (> 25 kHz) pump-probe scattering and spectroscopy instruments using optics compatible with two operation modes: mono (6 to 25 keV) or pink (5 to 25 keV).
The upgraded CXI and NXI provide the capability of ultrafast and high-rep-rate x-ray coherent scattering, diffraction, and imaging, crystallography, and spectroscopy. The beamline optics is capable of microfocusing and nanofocusing in a photon energy range of 7 to 25 keV.
The MFX upgrade enables high-rep-rate (100 kHz) liquid-phase scattering and spectroscopy, and serial femtosecond crystallography with a pink beam in the full LCLS-II-HE energy range.

## Slide 88: 2.3 X-ray Endstation J. Wang (ANL), W.-K. Lee (BNL) / Subcommittee 3
2.3.2. Comments
The XES team is commended for their comprehensive plan and diligent preparation for this review.
The new XES scope is comprehensive, and provides 5 endstations to meet the LCLS user community’s scientific requirements from ‘Day One’.
The funding is sufficient to achieve all the goals in the scope.
The instruments are of world-class quality.
Optimizing the integration of the high-rep-rate source, high-rep-rate pump laser systems, and high-rep-rate detectors is important.
The project uses a 100 kHz to 1 MHz source, 31/93/930 kHz lasers, and 25 kHz (goal) e-pix detector (being developed by LCLS L2S-I project) for high-rep-rate experiments.
Most beamline components will be duplicates of those developed for L2S-I and LCLS-II. Modifications are needed for some components to meet the requirement of higher photon energy. The schedule and budget estimate are accurate.
The installation and commissioning schedules seem to be tight, considering the interfacing with the LCLS-II beamline operation.
High-heat-load (HHL) optics will need to be fully developed for the project.

## Slide 89: 2.3 X-ray Endstation J. Wang (ANL), W.-K. Lee (BNL) / Subcommittee 3
2.3.2. Comments (continued)
For the DXS instruments, HHL and high-energy-resolution (HER) optics need to be fully developed to preserve the spectral brightness.
A wavefront propagation simulation considering both HHL and coherence for the IXS HER optics is underway but not fully implemented.
The current design schedule for IXS HER and HHL optics is very tight.
The 3-5 meV energy resolution of IXS is broader than that being pursued elsewhere, as a result of balancing the integration time and scientific needs.
Although XPCS is part of the DXS scope, the team did not focus on the XPCS instrument in the presentations.
The new laser systems are based on the LCLS-II NEH laser system designed in the L2S-I project. Experience from the NEH system will provide the baseline for the cost and schedule of the two new systems, one to be placed in the NEH laser room and the other in the new FEH laser room (repurposed MEC hutch).
Contingency plans should be developed in case the major upgrade of MEC endstation supported by external sources does not materialize.

## Slide 90: 2.3 X-ray Endstation J. Wang (ANL), W.-K. Lee (BNL) / Subcommittee 3
2.3.3. Recommendations
Develop a contingency plan for the new FEH laser system’s location by CD2 if the MEC move-out is still not confirmed..
Develop a full-wavefront-propagation-based optics simulation that includes simultaneously both the HHL and HER optics for DXS by next status review.
Develop a plan for HHL and HER optics (both R&D and the decision dates) by next status review.

## Slide 91: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? The Controls scope did not have any LLPs associated with the project’s CD-3A Approval. Are the risks associated with the LLP scope adequately addressed?- N/A. Is the overall project scope properly defined to meet the preliminary KPPs? Yes, indirectly. There are no KKP’s directly specified for Controls. Is the proposed injector facility adequately defined and justified?-N/A. Is the overall project technical progress to date appropriate at this stage of the project?-Yes.
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? –Yes, based on the current scope definition. Is the overall project design maturity adequate at this point in the project?-Yes
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Yes, one has been completed and two are currently ongoing.

## Slide 92: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
Findings:
Redefined Controls scope in support of project new scope:
  Provide controls to support 3 additional cryomodules for a total of 23 CM in part L4. new Low Emittance Injector
  Provide controls for new Cryogenic Distribution System.
  Provide controls for new injector including support for 1 injector cryomodule
  Reconfigure existing Sectors 7-10 cable tray and racks and install new racks, trays and cables
  Provide new controls for Upgraded 8GeV Spreader line
  Provide controls for new undulators, interspaces and associated controls
  Provide Safety Systems Controls for extended SRF region in sectors 7-10
  Provide controls for upgraded Hard X-ray Instruments and X-ray Transport in support high-rate operations.
Most Controls Design Complete by Q3FY22

## Slide 93: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
Controls Current Design Maturity:
  1.05.02 Accelerator 40%
  1.05.04 Experimental 38%
Detailed resource plans to be completed a long with revised cost estimates based on LCLS-II re-plan and actuals from LCLS-II/L2SI projects.
Response to Controls Systems CD-3A Review Recommendations:
  Risk Registry ID# RR64 added
  Risk Registry ID# RR73 added
The Control groups are in the process to identify additional resources that can execute HE without disruptions. Possibly hiring new personnel to supplement senior level staff’s efforts.
Approximately $15M of revised EAC is to account for lessons learned from LCLS-II.

## Slide 94: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
If SLAC management cannot provide cable plant design & management services at the time or on the scale that the project requires, then there will be cost impact to the project to contract for these services.
  This can be mitigated by bringing additional FTEs onboard to perform design and oversight to meet schedule. Use reference design from LCLS-II
If there are not enough qualified and well-trained personnel are available at the right time, then the project might be delayed or incur higher cost.
  This can be mitigated by bringing additional FTEs onboard to perform design and supplement team with controls contractors.
If electronics parts become obsolete and/or If there is a desire for performance improvements based on LCLS-II experience then some of the controls system components may require design changes, prototyping, and testing.
  Prototyping, re-design of impacted systems. (post mitigation, basis of impact). Faster production of LCLS-II designs would reduce risk of obsolescence.

## Slide 95: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
For the cryogenic controls there are two options for the design of the interface box (IB). The more complicated of the two options in an integrated IB design with CP1 and CP2 supplying gas to a single IB.
A safety analysis still needs to be performed for the ODH system L4 due to the additional 3 cryomodules.

## Slide 96: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
Comments:
We are pleased to hear from all speakers that the lessons learned from LCLS-II are being incorporated into LCLS-II-HE planning.
Approximately $15M of Controls’ revised EAC is to account for lessons learned from LCLS-II. This was determined by a top-down analysis. It would be prudent to perform a bottom-ups analysis because multiple iterations may be needed to refine this cost.
It is almost certain the Controls team will need additional FTEs to be brought onboard to perform design and prepare for the implementation phase of the project. The Controls team should bring on some percentage of these FTEs prior to CD-2 review. This will allow new Controls personnel to gain experience by working with the more experienced LCLS-II personnel on construction and commissioning activities.
We commend the Controls Safety System team for continuing to bring onboard new personnel, as needed. Four additional personnel since June 2020 .

## Slide 97: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
Scope creep and uncertainty in scope definition are potential concerns.
The selection for the cryo-plant interface box (IB) design options should be finalized and provided to the Controls personnel by March of 2021 to allow for completion of cryogenic controls PDR in the Summer of 2021.

## Slide 98: 2.8 Controls and Safety Systems R. Farnsworth, BNL & A. Coleman, ORNL / Subcommittee 8
Recommendations:
None.

## Slide 99: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Project Scope: Is there adequate technical progress on the long lead procurements (LLPs)? N/A Are the risks associated with the LLP scope adequately addressed? N/A Is the overall project scope properly defined to meet the preliminary KPPs? YES for baseline scope. Is the proposed injector facility adequately defined and justified? Qualified YES (in progress) Is the overall project technical progress to date appropriate at this stage of the project? YES for baseline scope.
Design Maturity: Are the designs, system specifications, and interfaces appropriately defined and sufficiently mature for this stage of the project? YES for baseline scope. Is the overall project design maturity adequate at this point in the project? YES for baseline scope.
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Qualified YES (in progress)

## Slide 100: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Findings
WBS 1.06 Infrastructure Systems scope includes the following:
  Linac Sectors 7-10 Modifications - Cryo Distribution modifications, penetration from Gallery to Tunnel, Cryo Equipment Distribution Pad, modify/raise Gallery Roof, modify PPS in Gallery and Tunnel, modify Air Monitoring in Gallery & Tunnel, modify/add Fire Protection and Fire Alarm Systems, Radiation Shielding for Linac penetrations, new general ventilation and lighting, LCW/Hx Systems & Electrical Upgrades (480V/208V)
  Linac Sector 4-6 Modifications - modify power & water
  Undulator Hall and Support B921 Modifications - expand and extend process water system, additional power for tech equip and controls, complete Dump/Rad System Water, Cable Tray Modifications

## Slide 101: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Findings (continued)
Recent scope additions in October 2020 increased Infrastructure Systems cost estimate from $21.02M to $48.9M:
  Low Emittance Injector Tunnel - Install New Power, Cooling & Infrastructure for New Injector Gun.
  Experimental Infrastructure - Install Power and Cooling Distribution to Support End Stations.
BCRs are planned to add the new scope to the Infrastructure Systems WBS.
Infrastructure Systems (WBS 1.06) currently is in the preliminary design phase and is planned to be at 70% design at CD-2/3.
Requirements development are in progress and planned to be completed by Q2FY21 to bring A/E on board.
A feasibility study has been performed (final received September 2020) for the new injector tunnel with three possible tunnel configurations and construction methods analyzed, with two tunnel alignments being viable. A geotechnical study is planned to start in January 2021 (pending BCR approval) to down select to the final tunnel configuration.

## Slide 102: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Findings (continued)
Injector tunnel construction is planned to coincide with downtime for the LCLS-II SC Linac planned from Q3FY25 through Q2FY26.
A Memorandum of Understanding (MOU) (LCLSII HE-1.1-PM-0920-R0) has been drafted to describe the project’s requirements for the use of SLAC resources and/or existing facilities, or any modifications to existing infrastructure to ensure the successful delivery of the project.

## Slide 103: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Comments
Adequate resources to perform the work according to the project’s schedule is a critical need, and it was stated that the LCLS-II project is still requiring resources including the Infrastructure Systems Manager and Deputy. Staffing plans are in progress and a high priority should be placed on filling those needed positions on schedule according to the need. A Service Level Agreement with SLAC Facilities & Operations for matrixed support is being drafted.
An additional CAM is planned to be brought on board for the new Injector tunnel scope by 2QFY21 and emphasis should be placed on filling that position.
Tunnel location and construction method decisions are upcoming and will be supported by the planned geotechnical study. Vibration considerations, means and methods, and risks all need to be thoroughly analyzed and not over simplified. The infrastructure team recognizes that the overall benefit to the project and technical success of the LCLS-II-HE project needs to be a primary driver for the final tunnel configuration decision rather than first cost of tunnel construction.
A communications strategy and plan for new tunnel construction is planned and will be very important for working with stakeholders including non-SLAC neighbors.

## Slide 104: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Comments (continued)
Soil sampling plans particularly with regards to spacing should be more aggressive (closer in proximity and frequency) than may statistically be required. A geological or hazardous material issue 5 ft from a well thought-out statistically placed sample hole can impact the project substantially.
Soil disposal options from the tunneling scope should be identified early on to identify any issues, challenges and costs.
Unknown underground utilities, ground contamination and/or cultural artifacts may impact the cost and schedule of the new injector tunnel and those risks should be taken into account.
A delay in the receipt of scientific equipment infrastructure requirements and completion of Room Data Sheets so that infrastructure design development can proceed is an identified and real risk. Change control of this information is also vital to minimize changes in the future.
To maximize work during the planned beam downtime in FY25-26, construction contract(s) should be awarded and all preconstruction work (submittals, safety plans, materials and equipment mobilized) should be completed and ready to work.
Coordination with the MEC Upgrade tunnel project could also be beneficial.

## Slide 105: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Comments (continued)
Leveraging experience and lessons learned from LCLS-II is a best practice, and the project team provided an insightful discussion on lessons learned, including adequate scope definition, design/constructability reviews, work planning control, quality control, partnering and transition to operations. Adapting those LL to HE is key.
Engaging stakeholders/F&O early and inviting them to weekly Owner, Architect, Contractor (OAC) meetings to aid in Transition to Operations planning and execution is a best practice.
The team provided a good discussion of interface/dependency projects between SLAC and the LCLS-II-HE project, including the K5B substation, CUIR (Critical Utilities Infrastructure) projects, and HE cryomodule storage. The MOU for off-project work and use of SLAC facilities/infrastructure should be finalized and approved as soon as possible.
Activity details, constraints and dependencies are being identified for the newly added scope, and this should continue to be developed to support the CD-2 baseline.
Continue to analyze tunnel construction costs, schedule duration and risks, in conjunction with the recent Director’s Review recommendation. The project team is well aware of this and schedule validation is high on their priority list.

## Slide 106: 3. Conventional Facilities J. Pittman, PNNL; J. Haslam, LLNL; W. Yuan, LLNL / Subcommittee 9
Recommendations
  Complete draft of MOU for interface/dependency infrastructure projects with SLAC and approve by the end of FY21, and then review annually thereafter.
  Hire Injector Infrastructure CAM and have on board by the end of 2QFY21, in conjunction with recent Director’s Review recommendation.
  Validate and approve Room Data Sheet input by the end of 2QFY21 to support the placement of A/E contract(s).
  Analyze tunnel construction costs, schedule duration and risks, prior to CD-2, in conjunction with the recent Director’s Review recommendation.

## Slide 107: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
ES&H: Are ES&H aspects properly addressed and are future plans sufficient given the project’s current stage of development? Yes Has the project considered COVID-19 related safety protocols in their plans? Yes
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Yes

## Slide 108: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
Findings
MOA’s and SOW are in place with all partner labs which includes ESH support
Conceptual Design Report (Chapter 13 & 14) addresses Radiological Considerations and ESH/QA
(PHAR) Preliminary Hazards Analysis Report (LCLSII-HE-PM-0004)
    Describes identified hazards & mitigations
    Heavily based on LCLS-II analysis
Safeguards and Security Requirements (LCLSII-HE-PM-0011-R0)
    Provides the path forward to the development of a Preliminary Security Vulnerability Assessment Report (PSVAR) due by CD-2
    SVAR established for LCLS-II
SLAC developed a COVID task force which defined guiding principles and a return to operation plan.
SLAC has developed a COVID-19 Resource page which provides key information to all SLAC staff and subcontractors.
A COVID-19 training matrix has been developed which includes on-line training prior to site access and in-person orientation upon arrival on site. Both communicating the COVID guidelines and face covering requirements.

## Slide 109: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
Findings
Job Safety Analysis (JSA) are utilized to integrate COVID precautions following ISM principles. JSAs define and document work scope and controls with input from all levels of the team.
The LCLS-II-HE Quality Management System is evolving with the development of the LCLS-II-HE Quality Assurance Plan which provides a graded approach and enhanced rigor to work planning and control
The Project document review process includes Partner Lab participation
Radiation protection analysis continues forward. Based on LCLS-II. This is an incremental change to the radiological risk. Resource needs are being carefully evaluated and is informed by lessons from LCLS II.
The current staffing levels for ESH is <0.5 FTE’s and the Quality Assurance staff is presently 2 FTE’s
The additional scope of the LEIT tunnel work will require the completion of a NEPA Supplement Analysis which will include evaluation of soil contamination.

## Slide 110: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
Comments
Project emphasis on ESH&Q is well demonstrated in all presentations
ESH program elements are well defined and communicated
The ESH&Q staff is experienced and has access to matrixed support from the SLAC ESH organization to support the project needs.
ESH&Q is fully integrated into all facets of the Project, both at SLAC and the Partner Labs.
Partner labs have experienced ESH&Q personnel in place to support LCLS-II-HE activities
Lessons learned have been developed and incorporated into the implementation of the SLAC WPC and ESH programs
The reorganization of the safety systems group has added experienced resources for which the LCLS-II-HE project has benefited as planning for safety system design and installation progresses.

## Slide 111: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
Comments
The project acknowledges the need for more analysis of ODH, PPS, and radiological risks. Consider including external design review for these systems
Safety System (PPS, BCS, ODH) design and installation planning has benefited from LCLS-II lessons learned process
COVID planning is well thought and appropriate to the present circumstances
  Masks, hand washing, health checks, contact tracing …
  Implemented through WP&C tools; JSAs
  Clear SLAC management priority for protecting people
  Communications and training is emphasized
  HPI emphasized; phased approach for return to operations
Return to operations planning is detailed and informative. The COVID tracking record on site is good and this reflects a caring staff behavior at home and at work
SLAC is benefiting from Stanford University Occupational Health COVID support. The University provides virus testing and contact tracing. On-site staff is tested weekly which provides reassurance to the staff and contributes to reduction in stress.

## Slide 112: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
Comments
Required project ESH documents are in place; however, updating is needed to reflect added scope
ESH&Q process development is comprehensive and informed by LCLS-II Lessons Learned. ESH&Q is well integrated to project planning.
ESH staffing should be evaluated and a plan for the future developed. Part time ESH staffing is adequate at present; however, the added scope, project progression, and increased staffing demands indicate that staffing needs should be re-evaluated.
The Project has identified the need to complete a NEPA Supplement Analysis (SA) for the proposed LEIT Facility. The plan to utilize the subcontractor that completed past project NEPA documentation will allow for consistency and completeness
The project would benefit from a review of lessons learned documentation from previous large excavation and tunneling activities which have occurred on the SLAC site and within the DOE complex
The ESH/QA path forward is appropriate for this phase of the project

## Slide 113: 4. Environment, Safety and Health M. Andrews, FNAL / A. Ackerman, BNL / Subcommittee 10
Recommendations
None

## Slide 114: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Cost and Schedule:
  Is the LLP cost and schedule performance, including contingency utilization, reasonable and properly managed based upon project performance to date? Yes
  Are the overall project cost and schedule estimates progressing adequately to support proposed CD-2 and CD-3 decisions as early as 2Q FY 2022? No. Project is now projecting a CD-2/3 in 4Q FY 2022.
  Is the increased preliminary point estimate adequately justified and credible for this stage of the project? In terms of cost and schedule, the point estimate of $640M is backed by credible basis of estimates that range from a Class 3 to Class 4/5 (AACEI scale) in maturity (answer is Yes) and appear to be justified.

## Slide 115: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Risk Management: Are risks being properly managed? Yes Is the overall risk registry sufficiently developed for this phase of the project? Yes
Recommendations: Has the project responded appropriately to recommendations from the last DOE review? Yes

## Slide 116: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Findings
The CD-3A scope was approved in May 2020 and project established the baseline for this scope in June 2020.
The TEC for CD-3A scope is $80.4M with $17.6M in contingency (22%) giving a TPC for 3A of $98M.
91% of the CD-3a procurements have been awarded and the remainder are projected to be done by the end of January 2021.
As of September 2020 the overall project has a BAC of $324.3M with contingency of $103.7M giving the Total Project Cost (TPC) is $428.0 million.
The project has been executing earned value management since July 2020. They are reporting earned value on the entire project but only reporting to PARS on 3A scope. We were provided data for three months (July, August and September) CPR. The project is currently reporting an overall project SPI: 0.96 and CPI: 1.03.

## Slide 117: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Findings (Cont’d):
The resource loaded schedule has approximately 5,745 activities, logically linked with tier milestones identified from Level 1 to Level 4.
A top-down estimate at completion (EAC) is underway that includes a new injector and end station upgrades that are not yet in the baseline.
The Project presented a proposed updated TPC, this included an updated BAC of $502M and $138M (30% on to-go) contingency giving an increased TPC $640M.
The increase in TPC is to include additional scope; End Station scope addition ($53.8M), Injector Scope Addition ($61.4M), scope addition contingency ($50.0M), and addition contingency requested ($46.8M). The new scope additions total $165M (incl. contingency) bringing the total updated to TPC to $640M.
The new point estimate ($640M) is an increase above the top end of the CD-1 cost range ($480M) by 33%.

## Slide 118: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Findings (Cont’d):
The new injector is a first of a kind (FOAK) component and has a contingency of 40%.
The project purchased niobium and a cryomodule from LCLS-II at a favorable cost that mitigated and retired an associated risk.
The project presented a Monte Carlo cost analysis both the 3A scope and the overall project. A schedule contingency MC was not presented.
The project presented the new use of Smartsheets and it seems to be a very easy accessible collaborative tool.

## Slide 119: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Comments:
GENERAL
The current EVMS process is a rigid and well developed collaborative process which seems to have good communication across the partner labs.
The project is being proactive to incorporate lessons learned from a recent root cause analysis on LCLS-II. Topics being reviewed and incorporated as appropriate include avoiding ineffective scope definition, inadequate cost estimating, inadequate work planning and control and ineffective design reviews and systems engineering. Maintaining vigilance to avoid these issues is essential for HE to be successful.
The project has been resource limited in that HE is not the top priority project at SLAC (currently). SLAC leadership has recently increased HE’s priority which is helping with technical resources and the outlook for maintaining schedule.

## Slide 120: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Comments:
SCHEDULE
The project is making reasonable progress on the CD-3A scope (SPI 0.99), given an approximate 5-month delay on the verification cryomodule and other impacts due to COVID.
The schedule is a work in progress; it has open ends, constraints, high float values, negative float values, and schedule gaps as they are still in the process of evaluating the full scope of the project .
The schedule provided a critical path for CD-3A scope but do not have a clear critical path for the overall project.
The current state of the schedule limits the ability to conduct sensitivity analysis, critical path analysis and determine the amount of contingency needed.

## Slide 121: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Comments (Cont’d):
COST
The new point estimate ($640M) is an increase above the top end of the CD-1 cost range ($480M) by 33%. If the point estimate exceeds $720M (50% increase over CD-1 high cost), then a CD-1(R) (refresh) would be required.
The project presented the BOE documents for the Injector and End Stations additional scope. These are progressing well and are leveraging previous experience.
The cost estimate for the injector scope is least mature but is sufficient for this stage of the project. A new systems manager will be onboard in January 2021 who will lead this effort. Special emphasis and resourcing may be needed in order to get the estimate to a sufficient level of maturity to incorporate into a resource loaded schedule within six months.

## Slide 122: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Comments (Cont’d):
The scope and cost estimate for the End Station upgrades is relatively mature for this stage of the project. Managing potential scope creep is essential to avoid significant cost increases.
The project should regularly reassess the probability that the planned cryogenic systems will be sufficient to operate HE as designed. This has the potential to be a significant cost driver if upgrades become a necessity.
Maintaining the same partner labs and potentially some of the same vendors as the LCLS-II project should result in stable and predictable cryomodule cost and schedule performance.
Defining what off-project work SLAC will perform sooner rather than later is important to ensure that cost and schedule implications are incorporated into the project for any work that will fall back on the project to perform.

## Slide 123: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Comments (Cont’d):
Change control is managed through a well defined and robust process that allows for several opportunities for vetting, both for technical need and cost/schedule implications.
The current pending BCR list is showing a net impact to Contingency of $186.4M, $115.2M of which is the proposed additional scope (Injector and End-Stations), ~$65.0M in changes resulting from the EAC exercise. All of these account for approx. 20 BCRs to process. There is a risk that these are underestimated as they are not fully burdened.

## Slide 124: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Project has developed a mature risk program that has held several risk workshops and is proactive in nature. They recently conducted a risk workshop in September 2020 which identified 259 risks which they are in the process of incorporating into the risk registry.
The project is taking advantage of lessons learned from the LCLS-II project. This is further enhanced by a number of staff who are joining the HE project with extensive first-hand experience from the LCLS-II project.
The project considers that the availability of technical resources at SLAC or its partner labs is the biggest risk to the project associated with COVID. This risk is addressed in the risk registry. Continuous monitoring of the probability and impact will be important in order to proactively manage potential cost and schedule impacts.

## Slide 125: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
Recommendations:
Incorporate all BCRs in time to support a resource loaded, logically linked schedule within six months.

## Slide 126: 5. Cost and Schedule H. Taaffe, ANL / Jeff Thomas, DOE Subcommittee 11
PROJECT STATUS |  | 
Project Type | MIE / Line Item / Cooperative Agreement | 
CD-1 | Planned: Oct 2018 | Actual: 10/02/18
CD-3A | Planned: Jan 2020 | Actual: 06/01/20
CD-2/3 | Planned: Q1 FY 2022 | Actual:
CD-4 | Planned: Q3 FY 2027 | Actual:
TPC Percent Complete | Planned: ___11.3__% | Actual: ___10.9__%
TPC Cost to Date | $34.2M | 
TPC Committed to Date | $40.1M | 
TPC | $428.0M | 
TEC | $309.1M | 
Contingency Cost (w/Mgmt Reserve) | $103.7M | ____35.9% to go
Contingency Schedule on CD-4 | ___6_months | __ 7.5%
CPI Cumulative | 1.03 | 
SPI Cumulative | 0.96 | 

## Slide 127: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Management:
Is the project being appropriately managed to advance the design effort and deliver the long lead procurements? Yes - Key people in place and processes are being followed or developed as appropriate for this stage of the project.
Does the project have the necessary resources to succeed? Maybe - The project acknowledges there are some known gaps and external dependencies (on LCLS-II in particular) that may impact the timely availability of resources.
Does the project team have sufficient expertise and experience to successfully execute the project? Yes - The expertise exists - timely deployment may be challenging.
Are the multi-laboratory partnerships functioning effectively? Yes - emphasis on collaborative development and adoption of processes is notable.

## Slide 128: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Management:
Are the work plans for the next fiscal year appropriate and complete? Yes - LLP plans in place while other work evolves as appropriate to this stage of the project development.
Recommendations:
Has the project responded appropriately to recommendations from the last DOE review? Yes

## Slide 129: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
  Overall Assessment
  The committee is favorably impressed with the status of the project. CD-3A work is proceeding well as are the preparations the project is making to attain CD-2 or 2/3 in FY22 with an expanded scope.
  The thoughtful assessment of prior lessons learned, and re-evaluation of processes is commendable, as is the work to improve communication and coordination across the multi-laboratory collaboration.
  Success will in part depend upon timely development and adoption of plans for the expanded scope of the project and coordination with the rest of SLAC and in particular the LCLS-II project to obtain timely access to resources that are required by the project. This underscores the need for getting a working plan in place as part of the suite of communications tools both within and outside of the LCLS-II HE Project.

## Slide 130: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Findings
The project attained CD-3A in May 2020 and has started execution of the long lead procurement scope, with 91% already placed and the balance scheduled to be placed by the end of January 2021.
The project has adopted a collaborative tool for the capture and tracking of project risks and outlined a process for developing and understanding the risk exposure including past risk workshops and planned targeted risk workshops in the near future.
The project has also developed revised systems engineering and requirements capture processes and procedures.

## Slide 131: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Findings
The project has adopted a collaborative approach to working with the partner laboratories and gaining their input and buy in for the project plan and working procedures.
Project management has assessed LCLS-II root causes for cost and schedule overruns, hired outside QA and system engineering expertise, and is performing staffing plans and assessing critical skills needs
The scope has recently been expanded, including 2 new end-stations, a new low emittance injector and tunnel, and 5 additional cryomodules.
A new partner lab has been added (LBNL) for accelerator physics and undulator support.
There are currently 28 Baseline Change Requests in the pipeline for review. The project estimated these would be 'in the schedule' in one year or so.

## Slide 132: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Comments
The LLP procurement awards have gone well.
The partner lab collaboration seems to be working well; maintaining the cryomodule production capability without major disruption seems feasible.
The increased Project Management staff level, increased attention to QA and systems engineering is commendable.
The process outlined for establishing the risk exposure and mitigation posture by the project is well thought out and appropriate for this stage of the project development.

## Slide 133: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Comments
The expanded project scope, reduces risk exposure from LCLS-II performance demands, simplifies installation, adds operational flexibility, and should provide a stronger initial science output at CD-4. The committee feels that overall these additions will more capably address the mission need and are a justified investment.
The project needs to complete the BCRs associated with the expanded scope including WBS changes, schedule and cost updates. This updated schedule can then be used to assess the required staff levels and refine coordination with LCLS-II where needed.
To succeed in achieving readiness for CD-2, the project must get to a working resource loaded schedule as soon as practical.

## Slide 134: 6. Project Management E. Johnson, BNL; J. Diehl, BHSO; J. Galambos, ORNL / Subcommittee 12
Recommendations
Within six months, the project should develop a resource loaded schedule that includes the expanded scope.