## Sheet1
Remaining tasks for LCLS-II Cryomodule testing
Kevin Jordan 7/26/2018
System | Task | Group Responsible | Notes
Installation / Pipe fitting / Welding PRIOR to testing
Transferline
| Confirm/Prep both transferline sections have proper weld prep | Cryo
| Locate and affix to floor short piece | Installation
| Locate and affix to floor "L" piece | Installation
| Position/align both sections with ruler and level bar | Cryo
| Cut, prep, & weld field fit joints per weld spec - w/M. Martin advice | Cryo
| Leak check innner connections prior to SI wrap | Cryo/SRF?
| Cut/prep & weld clam shells | Cryo
Warm Helium Piping
| Prep, mount, and weld sections of warm piping per spec & drawings | Cryo | Much of this is to be done after the cryo-can is located & grouted
Cryo-Can
| Remove/install equipment that is too tall for cable tray/waveguide | Gubeli | Ensure that it can be moved into place w/o hight restrictions like relief stack
| Confirm/Prep the weld joints have proper weld prep | Cryo
| Locate Cryo-can per surveyed drill locations | Installation
| Confirm alignment to field fit transferline | Survey/Gubeli
| Drill, mount/level can, grout base plate | Installation
| Cut to fit, weld & leak check inner Helium piping | Cryo
| Wrap SI insulation | Cryo/SRF
| Cut to fit & weld outer clam shells | Cryo
Clean Room Assembly
| Unpack & assemble | Electricians | This can be done once the cryo-Can has been moved into place
| Install AC power and lights | Electricians
Work to move, locate, and join 2 cryomodules prior to testing
Movement
| Arrange for crane at LERF to Lower/Raise CMs | Installation
| Move to/from Test Lab | SRF
| Wheel in/out LERF | SFR/Installation
| Locate/position CMs | SFR/Survey | This will likely be done wioth plumb bobs
Cleanroom beam tube connection
| Prepare & execute center beam tube connections in cleam room per procedures | SRF/Vac | This is the effort to join two modules together
| Insulate | SRF
Cryo-Can & Center Bellows | * these details are TBD *
| Affix the bellows to cart | Installation (?) | The cryo-can bellows may arrive on the end of the CM - TBD
| Position cryo-can bellows | SRF | The cart enables ease of installation in the joining region
| Secure cryo-can bellows | SRF
| Position center bellows |  | These connect the vacuum space of the two CMs together
Secure center bellows
Cooldown
Follow Mike Drury's proceedures