## Slide 1: LERF Update April 28, 2021 (1/3)
Isotopes:
  Enough funding is left to remove Beryllium vacuum window
  Andrew has call today with Ethan Balkin at 11:30 today to find out if there will be another FOA this summer.
  We would not be eligible to participate in the recently announced FOA, and without further funding, the isotope program will have hibernate for at least a year.
LCLS-II HE:
  Verification module is being tested now at Fermilab and will be shipped here in September for retest
  SSAs need to be tested into shorts
  Blocks will need to removed/replaced
Magnetron project:
  Need final water connections – booster pump has failed (old Antares Laser chiller) and is being replaced
  Haipeng is wrapping up safety documents then commissioning will begin, a second 75kWatt will be procured next FY

## Slide 2: LERF Update April 28, 2021 (2/3)
LERF status:
  AC is off to the clean room – related to booster pump repair
  Vacuum window needs to be removed and vacuum restored to 1X & 1F regions
  The cryomodule needs, at least, to have gradients checked after vacuum incident
  Building AC chiller replacement – begins in late summer
  Hampton U. students need to finish GEM detector work when allowed back on site
  Shukui has laser work in Lab 5 that will start soon
GTS:
  Reassembling the HV & beamline
  Bakeout & make photo-cathode
  Start running beam ~ July 1
  Examine new photo-cathode recipes
  https://wiki.jlab.org/ciswiki/index.php/GTS_meeting_4_12_21

## Slide 3: LERF Rough Timeline (3/3)
May
  Commission Magnetron
  Beamline work in the GTS
  Remove Beryllium window & restore vacuum in 1X & 1F
June
  Magnetron phase locking studies
  Complete GTS beamline
  Shukui will be doing laser work in Lab 5
July / August
  Begin running beam in the GTS
  Continue with Magnetron studies
  Begin LERF building AC/chilled water system replacement
  Commission LCLS-II HE SSAs (SLAC did have a failure of one of these higher power units)
  Check FL02 cryomodule gradients
September
  Remove shielding blocks & install LCLS-II HE verification module & restore blocks
  Begin test cycle for VCM, lasts ~ 2 months