## Slide 1
Closeout Report on the
DOE/SC Status Review of the
Measurement of a Lepton-Lepton Electroweak Reaction (MOLLER) Project
Thomas Jefferson National Accelerator Facility
November 2-4, 2021
Ethan Merrill
Committee Chair
Office of Science, U.S. Department of Energy
http://www.science.doe.gov/opa/

## Slide 2: Review Committee Participants
Ethan Merrill, DOE/SC, Chairperson

## Slide 3: Charge Questions
Is the MOLLER team effectively executing the work? Is the design progressing satisfactorily and are technical issues appropriately and proactively being addressed?
Are the cost and schedule estimates credible? Do they include adequate scope, cost and schedule contingency?
Is ES&H and quality being properly addressed given the project’s current stage of development?
Is MOLLER being properly managed, including the interfaces with in-kind contributions? Is risk planning adequate and comprehensive given the project’s current stage of development?
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews?

## Slide 4: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
Is the MOLLER team effectively executing the work? YES Is the design progressing satisfactorily and are technical issues appropriately and proactively being addressed? YES
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews? YES

## Slide 5: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
1. General:
The Moller project is planning for a CD2/3 review in early FY23.
The project has refined their simulation tools to guide the determination of requirements for the target and spectrometer. Very detailed collimation studies have been performed optimizing placement of coils and shielding relative to target and detector.
The project will be preparing a system for how to track state and progress of documentation (Specification -, interface - documents, drawings etc.)
Extensive studies of radiation levels inside and outside of Hall A have been performed and are ongoing, incorporating new material layouts as they are developing.
Findings

## Slide 6: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
2. Target:
Several components of the target subsystems have moved to other WBS: installation and alignment to WBS 1.08, while the target window has been moved into WBS 1.02.
Target cell performance is being optimized by CFD simulations. The CFD calculations are almost complete for the steady-state simulations, while the time-dependent calculations are still ongoing. Completion of the target cell design is necessary to finish the target loop and the target motion design.
Much of the target design is based on components similar to those used in previous LH2 targets at JLab.
The new target elements are the room-temperature liquid LH2 pump and the increased volume of LH2, which is a factor of four larger than that used previously.
The project has contracted with an outside firm to assist with development of the safety systems needed for the LH2 target.
Findings

## Slide 7: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
3. Spectrometer:
The spectrometer design down select resulted in a decision to use a segmented design based on physics performance and magnet fabrication/assembly considerations.
A prototype coil will be fabricated and tested for each of the sections of the downstream toroid prior to fabrication of the production coils.
The project does not plan to test the magnet assembly at full current prior to final installation and therefore will entirely rely on design calculations to estimate the dimensional changes due to thermal expansion and electromagnetic forces. Individual prototype coils will be tested to check their performance prior to magnet assembly.
The current spectrometer shielding design is based on 37 MGy predicted by GEANT with a safety factor of 2. There is still some uncertainty regarding the maximum allowed dose for the epoxy resin and a test contract is underway.
Findings

## Slide 8: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
Comments
1. General:
The Moller team made good progress in the design of the apparatus and planning for the next CD review. Many specification and interface documents are in preparation or are well advanced for the present state of the project.
The project has a sound plan for design reviews. Adding experts from outside of JLab for review of some of the more challenging, complex systems, particularly for early reviews, is an opportunity for fresh eyes and expanded expertise.

## Slide 9: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
Comments
2. Target:
The design of the target LH2 pump is relatively late due to a specific resource overload. The project should find means to accelerate this design.
3. Spectrometer:
An initial test plan for prototype coils was presented. The project should further develop this plan and contract with the vendor to monitor intermediate magnet fabrication steps and ensure that feedback from the prototype coils can be incorporated in the production.
Radiation testing of epoxy samples should be completed on a timely basis in order to confirm the magnet shielding requirements and design, which is closely coupled to the overall experiment design and backgrounds.

## Slide 10: 1 Target and Spectrometer G. Sabbi, LBNL, C. Hast, SLAC, W. Lorenzon, U of Mich, P. Wanderer, BNL - Retired Subcommittee 1
Recommendations
Develop a process to track project documentation/specification/drawing progress by Q2FY22.

## Slide 11: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Is the MOLLER team effectively executing the work? Is the design progressing satisfactorily and are technical issues appropriately and proactively being addressed?
YES & YES
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews?
YES

## Slide 12: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Findings (1 of 2):
The following System Requirements Document (SRD) are still in draft
  1.04 Integrating Detectors
  1.05 Tracking Detectors
  1.06 Hall Infrastructure
  1.07 DAQ/Trigger
Preliminary Design Review (PDR) for DAQ and Infrastructure has been completed
  Detectors PDR scheduled for January 12-13, 2022
Infrastructure:
  Integration with fire protection is a work in progress
    Mason and Hanger have been contracted to consult as Fire Protection Engineer
  Hall A electrical power capacity has been increased since CD-1
  Hall A Low Conductivity Water (LCW) has been increased since CD-1
  Radiation shielding is being designed such that the electronics can survive the entire experiment lifetime

## Slide 13: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Findings (2 of 2):
Detectors:
  Pre-production prototyping of all four detector types is scheduled to be completed in FY22.
  The full “PMT + pre-AMP + ADC” signal chain was tested at a beam test in Germany in Oct. 2021.
    Beam test data is still being analyzed and results not presented in this review
  5 different quartz types are being evaluated for their transmission loss with respect to irradiation
DAQ:
  Prototype ADC boards are already in production
  Both integrating and counting mode FPGA firmware are 70% complete
  Software control system design is 80% complete

## Slide 14: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Comments (1 of 3):
Supply chain issues and lead times are being closely monitored by all sub-groups. Sub-groups should consider doing formal quarterly reviews of supply chains and lead times until global supply chains become stable.
DAQ:
  Leveraging the existing JLAB DAQ technology (CODA, BPM, BCM, etc) is helping MOLLER reduce the project scope and risks
  Online monitoring software for the DAQ is not in scope. But some amount of monitoring software is likely necessary to be developed during commissioning.
Infrastructure:
  Cost table of labor and materials presented by infrastructure was not up-to-date
  GEM cabling design is not very mature. The sooner that the GEM cabling assembly is prototyped the sooner that issues can be identified and resolved.

## Slide 15: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Comments (2 of 3):
Detectors:
  Finishing the down selection or qualification of the 5 quartz types before CD-2/3 will help with planning procurement
  The barrel segment patch panel will likely require multiple insertions during the initial detector commissioning. It would be wise to understand the expected number of connect/disconnect cycles and how much design margin with respect to each patch panel connector.
  Magnetic relays are used for the low/high gain switching on the PMT base. But while the relays are active, the stray magnetic field might have unintended effects (e.g. change in PMT gain or system error on particle tracks)

## Slide 16: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Comments (3 of 3):
Detectors (continue):
  It was confirmed that the fabrication of 2D readout layers are also carried out at CERN, besides the fabrication of GEM foils. It was stated that the UVA group is in contact with Rui Oliveira (CERN) about costing and scheduling.
  It is crucial that the production schedule at CERN is well understood, in order to avoid re-prioritization due to CERN internal priorities.
  It was stated that the required radial accuracy is 1 mm. Generally, moving tracking detector elements during the operation of an experiment does not come without challenges. It is crucial that the reproducibility is well understood. Preparing a prototype and test is critical.
  It is understood that APV chips are being used from a prior experiment at SBS. This has been stated at a prior review. The choice is understandable but relies on well-functioning readout chips after being exposed to beam operation.

## Slide 17: 2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC, B. Surrow, Temple U., G. Young, BNL Subcommittee 2
Recommendations (complete all these before CD-2/3 review):
Finalize the SRDs and ICDs for Detectors, DAQ, and Infrastructure
Complete the Detectors PDR
Infrastructure update their cost table
Perform a “number of insertions” study on the barrel segment patch panel
Perform a stray magnetic field study on the PMT base when relays are active
Report on number of spare APV chips and experience of radiation tolerance. The project should monitor exposure of the chips during SBS operations to ensure adequate lifetime margin for the MOLLER project.

## Slide 18: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Are the cost and schedule estimates credible? Do they include adequate scope, cost and schedule contingency?
Is ES&H and quality being properly addressed given the project’s current stage of development?
Is MOLLER being properly managed, including the interfaces with in-kind contributions? Is risk planning adequate and comprehensive given the project’s current stage of development?
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews?

## Slide 19: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Are the cost and schedule estimates credible? Do they include adequate scope, cost and schedule contingency?
Is ES&H and quality being properly addressed given the project’s current stage of development? YES, the program is progressing appropriately for this stage of the Project
Is MOLLER being properly managed, including the interfaces with in-kind contributions? Is risk planning adequate and comprehensive given the project’s current stage of development?
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews?

## Slide 20: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings – Environment, Safety, and Health
NEPA Categorical Exclusion (CX) approved by TJSO on June 29, 2020
Project utilizing the Jlab ISM plan as documented in Section 8.8 of the PPEP
Project ESH Lead is defined within the project management team at an effort level of .25 FTE
PHAR updated to reflect new Jlab electrical safety processes. COVID-19 hazard to be addressed in future update
ESH & QA expectations flowed down to collaborating institutions through subcontracts, MOU’s, and iCRADA
Jlab radiation safety support integrated into the shielding design process
ESH risks have been addressed within the Project Risk Register including the occurrence of a safety incident and COVID-19 pandemic
Quality assurance plan defines the project specific QA requirements and processes. Currently recruiting a QA Lead
The Project is currently utilizing an external consultant to evaluate fire and life safety requirements relating to the use of liquid hydrogen

## Slide 21: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Comments – Environment, Safety, and Health
The ES&H lead assigned to the project is experienced and competent. As the project progresses the need for additional ESH resources should be evaluated
ESH is being integrated into all elements of the project
Project has developed a flow chart to address the design, fabrication, procurement and shipping of equipment for use at Jlab which is well written and a good communication tool for collaborating institutions. Consider including a reference to this document in the subcontract, MOU and iCRADA process
The baseline hazards list (Table 1) within the PHAR is currently incomplete. Key hazard areas like construction, installation, chemical, environmental, fire, and flammable liquids, etc. have not been identified. A comprehensive baseline hazard list is critical to completion of the risk assessment process for the HAR
Evaluate the opportunity for iCRADA and MOU documentation to include the name and contact information for collaboration ESH oversight representatives. Additionally, a requirement for reporting ESH issues including injuries or near misses to the Project ESH Lead keeps the project informed.

## Slide 22: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Comments – Environment, Safety, and Health
The utilization of the external Fire Protection consultant will provide credibility to the development of requirements to support the use of liquid hydrogen
Review the requirements and continue to progress with development of the first draft of the Preliminary Security Vulnerability Assessment for CD-2

## Slide 23: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Recommendations – Environment, Safety, and Health
None

## Slide 24: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Are the cost and schedule estimates credible? Yes Do they include adequate scope, cost and schedule contingency? Yes
Is ES&H and quality being properly addressed given the project’s current stage of development?
Is MOLLER being properly managed, including the interfaces with in-kind contributions? Is risk planning adequate and comprehensive given the project’s current stage of development?
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews?

## Slide 25: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings – Cost and Schedule
Project has a TPC of $48.2M with contingency of $12.4M, 35% of TPC
Cost range is $45.8M - $56.6M, -5% to +15%
The upper range includes prolonged COVID-19 work restrictions, a potential 6-month schedule delay
The project received CD-1 is FY21 and is scheduled for CD-2/3 in Q2 of FY23
The MIE cost profile is made up of $18.3M Material, $16.9M Labor, and $.57M Non-Labor.
Funding was secured with NSF and CFI
MIE scope from WBS elements 1.04, 1.05 and 1.07 was transitioned to new WBS elements 2.0 NSF Midscale Project and 3.0 CFI/RM Project
NSF and CFI scope has been integrated into P6. The project is currently working towards the integration to Cobra.
Installation of each system was moved to new WBS 1.08 Installation
The project is being statused on a monthly basis, utilizing EVMS-lite reporting

## Slide 26: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings – Cost and Schedule
The current critical path runs through downstream spectrometer fabrication
The PMB was initially established with PB-001
8 pre-baseline change requests have been issued for the project, a cumulative change in MIE cost estimate of ~$700K.
The project utilizes Acumen Fuse and P6 log data to examine schedule health
The current schedule has 1806 activities, no lags or leads, and only 1 hard constraint (CD-4 milestone)
CD-2/3 Early finish has slipped ~2 months relative to the CD-1 forecast. CD-4 Early finish has slipped ~4 months relative to the CD-1 forecast.
Resource rates have been updated to FY21 rates, with escalation of 3% for outyears
CAMs or the PM can initiate a BCR by filling out the baseline change request form
Project recently went from using Primavera Risk analysis software to Safran
The project has 81 risks, 66 open, 13 retired, and 2 closed. Monte Carlo analysis of the project risks has been performed.

## Slide 27: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Comments – Cost and Schedule
The project is proactively working towards updating their documentation, project schedule, and resource level loading.
WBS 1.06 Hall A Infrastructure BOE needs to updated. The project plans to do this in November.
With the incorporation of the NSF and CFI scope the project well thought out the WBS structure considering only the MIE scope will be performing PARS reporting. Reporting of the project can be performed separately to collectively.
The interim CAM position for the installation should be appointed in the near future. The project team has a plan to fill the open CAM role.
The current critical path runs through fabrication of the downstream coils. The current contract with Everson Tesla for the fabrication of the coils should be reviewed to keep current pricing proposal or see if needs to be modified.
Continue progressing towards CD-2/3

## Slide 28: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Recommendations – Cost and Schedule
None

## Slide 29: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
MOLLER Project Status – August 2021 |  | 
Project Type | MIE | 
CD-1 | Planned: Q1 FY21 | Actual: Q1 FY21
CD-2 | Planned: Q3 FY23 | Actual:
CD-3 | Planned: Q3 FY23 | Actual:
CD-4 | Planned: Q4 FY27 | Actual:
TPC Percent Complete | Planned 11.6% | Actual 9.8%
TPC Cost to Date | $3.49M | 
TPC Committed to Date | $4.09M | 
TPC | $48.2M | 
TEC | $46.6M | 
Contingency Cost (w/ Mgmt Reserve) | $12.4M | 100% to Go
Contingency Schedule on CD-4 | 19 months | 
CPI Cumulative | 1.03 | 
SPI Cumulative | 0.86 | 

## Slide 30: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
MOLLER Project Status – September 2021 |  | 
Project Type | MIE | 
CD-1 | Planned: Q1 FY21 | Actual: Q1 FY21
CD-2 | Planned: Q3 FY23 | Actual:
CD-3 | Planned: Q3 FY23 | Actual:
CD-4 | Planned: Q4 FY27 | Actual:
TPC Percent Complete | Planned 12.8% | Actual 10.7%
TPC Cost to Date | $3.89M | 
TPC Committed to Date | $5.22M | 
TPC | $48.2M | 
TEC | $46.6M | 
Contingency Cost (w/ Mgmt Reserve) | $12.4M | 100% to Go
Contingency Schedule on CD-4 | 19 months | 
CPI Cumulative | 1.00 | 
SPI Cumulative | 0.84 | 

## Slide 31: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Is MOLLER being properly managed, including the interfaces with in-kind contributions? Is risk planning adequate and comprehensive given the project’s current stage of development?
  Yes, the project is being well managed.
Is the MOLLER team appropriately addressing the recommendations from prior DOE SC reviews?
  Yes. A Quality Assurance Professional will soon be onboarded to close out all recommendations from the 2020 CD-1 IPR.
Findings – Project Management
  MOLLER is a Major Item of Equipment Project (MIE) in the Office of Nuclear Physics, to be performed at TJNAF. The project has a functioning Integrated Project Team, a Federal Project Director and the project is nearly fully staffed.
  CD-0 was approved in November 2016 and CD-1 was approved in December 2020.

## Slide 32: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings (cont.) – Project Management
  Since CD-1, the US NSF and the Canadian CFI/RM have committed to provide funding for MOLLER, primarily to supply electronics and detectors. The project moved this scope, that was previously assigned to DOE, to two different WBSs, 2.0 NSF Midscale Project and WBS 3.0 CFI/RM Project, and the funding has been separated in P6 from DOE funds.
  The project cost range has been updated since CD-1 to $45.8M – 56.6M and the updated point estimate is $48.2M. The updates were prompted by transfer of DOE scope to NSF and CFI.
  The DOE, NSF and CFI elements of the program are fully integrated as a unified program. NSF and CFI scope remove about $7M from the DOE project scope. The DOE cost range narrowed as a result, but the point estimate increased slightly due to cost increases across the various systems.
  There are monthly telecoms with DOE and NSF Program Managers, DOE Federal Project Director, MIE Project Manager and NSF Project Manager to facilitate communication and coordination. There are weekly meetings between the MOLLER Project Manager and Collaboration leadership.

## Slide 33: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings (cont.) – Project Management
  The project team developed a Work Breakdown Structure (WBS) that includes all required project scope. Since CD-1, Installation activities have been pulled from the various WBS subsystems and collected into a new Installation WBS subsystem.
  The current funding profile has $13.25M in FY22, but the President’s request is only $7M for FY22. This provides sufficient funds to complete design activities but requires procurements to be pushed out. The biggest risk is an extended Continuing Resolution in FY23 that would further delay critical procurements.
  Originally, the project was planned with a CD-3a for the early procurement of the spectrometer coils, scheduled approximately 6 months before CD-3. Due to some delays of the spectrometer design, this time difference had decreased to approximately 3 months. Eventually, the project decided to fold CD-3a into CD-2/3.
  The CD-2/3 early finish date has slid about 2 months to Q1 FY23 since CD-1 due to Toroid delays and incorporation of NSF scope. CD-2/3 is now on the critical path.

## Slide 34: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings (cont.) – Project Management
  The project critical path runs through design, CD-2/3, then downstream spectrometer fabrication. It then follows the installation sequence starting at prep of Hall A for MOLLER through shielding installation, utility work and platform installation, spectrometer installation and testing and, finally detector installation and KPP validation.
  Preliminary and Final Design Reviews are scheduled for major systems and components. Reviewers are generally from JLab but from outside the Project. Subsystem preliminary design reviews have started, and final design reviews are scheduled prior to CD-2/3. A full Final Design Review will be conducted prior to the CD-2/3 IPR.
  An interface matrix has been developed and Interface Control Documents are all in at least a draft form.

## Slide 35: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Findings (cont.) – Project Management
  The project Risk Register and estimation uncertainties are reviewed at least quarterly. A Monte Carlo of the estimate uncertainty and risks has been performed and results in an estimated contingency need of $7.87M (22%). The project currently has $12.4M (35%) of contingency.
  The risk register contains 66 open risks, 5, high, 28 medium, and 33 low. 13 risks have been retired and 2 risks have been closed.
  The project team has developed KPPs including threshold and objective criteria and has also identified UPPs for full scientific discovery potential.
  The Project Manager is currently serving as the Project Quality Manager. A new hire into this position is imminent.
  The CD-4 early finish date has slipped 4 months to Q1 FY26 since CD-1. About 22 months of float remain.

## Slide 36: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Comments – Project Management
  The project is well managed by a competent project team.
  The KPPs are well defined.
  There appears to be good communication between the Project and the various partners and stakeholders.
  The project has a sound plan for design reviews. Adding experts from outside of JLab for review of some of the most challenging, complex systems, particularly for early reviews, is an opportunity for fresh eyes and expanded expertise.
  Installation activities have all been collected into a new Installation WBS subsystem to facilitate coordination. The project appears to understand that close coordination with the other WBS subsystems will be required to make sure that designs and fabricated components align with installation team expectations.
  The state of the Project Management documentation (PPEP, Acquisition Strategy, Risk Management Plan, Quality Plan, Hazard Analysis) is relatively mature and can be completed prior to CD-2/3.

## Slide 37: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Comments (cont.) – Project Management
  It was a reasonable decision to fold CD-3a into CD-2/3, since they would occur just a few months apart and require two DOE independent reviews.
  Though the project is progressing well, the schedule contingency between the CD-2/3 early finish and the Level 1 milestone is small, now approximately 3-4 months. The Project Manager recognized that this may not be adequate contingency but didn’t want to update the Level 1 milestone date because the project is not yet baselined.
  There remain a few areas in the resource-loaded schedule where resource leveling is still required. In advance of the CD-2/3 review, the project should ensure that spikes in the resource profile have been leveled and the project understands where the resources will come from.
  Currently the project does not include un-costed labor in the P6 schedule, as the bulk of un-costed personnel are from university groups funded by NSF and CFI. However, for the installation phase (WBS 1.08), the project team should consider including the un-costed effort. This will be useful to understand the overall picture of this critical and time sensitive effort and can provide input to university grant renewals.

## Slide 38: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL, S. Zimmerman, LBNL, W. Hughes, PNNL, M. Andrews, FNAL, D. Newhart, FNAL Subcommittee 3
Recommendations – Project Management
  None