## Slide 1: MOLLER Review Schedule
Prep, dry runs and reviews
Jim Fast

## Slide 2: Annual Status and CD-3a Reviews
September Status – P6 data freeze for status review
Oct 3 – PMO provides updated data (PB-018) for Cost Books to CAMs
Oct 7 – CAMs and L2 managers update Risk Register
Oct 14 – Cost Book updates by CAMs complete (updated to match latest PB-018)
Oct 17 – Updated risk analysis complete – L2 and L1 milestone SVTs updated to reflect schedule risk
Oct 21 – Drafts of all presentations complete
Oct 24 – Nov 2 – Dry Runs of Director’s Review Presentations
Oct 26-30 – DNP Fall Meeting and NSAC pre-meeting
Nov 1 – Supporting documents for review on SharePoint
Nov 4 – Final presentations due
Nov 7 – Final review of review Web Site (admins and CAMs)
Nov 8 – All materials posted for Director’s Review
Nov 15-17 – Director’s Review
Dec 9 – Responses to DR Recommendations complete
Dec 7-16 – Dry runs of OPA presentations
Dec 13-15 Fundamental Symmetries Town Hall for NSAC
Dec 18 – Final presentations due
Dec 19-20 – Final review of review Web Site (admins and CAMs)
Dec 23 – All materials posted for OPA review
Jan 10-12 – OPA Review
March – DOE CD-3a approval

## Slide 3: Final Design Reviews
Sep 30 – TDR draft complete
Nov 18 – TDR final version frozen for all time
Dec 5-8 (tentative) – Internal FDR for all of MOLLER systems
Jan 12 – Independent Final Design Review (IFDR) materials posted for remote review
Feb 6-8 (tentative) – IFDR in-person presentations, Q&A, closeout

## Slide 4: CD-2/CD-3 Reviews (tentative dates)
November BCRs – P6 Performance Management Baseline (PMB) freeze for CD-2/CD-3 Director’s Review
  No BCRs will be entertained December other than administrative ones (e.g. contract awards)
Dec 20 – Risk analysis updated
Jan 6 – PMO provides updated data (November BCRs) for Cost Books to CAMs
Jan-Mar – Clean cost/schedule data period for Director’s Review
Feb 24 – Cost Book updates by CAMs complete (updated to match November BCRs data)
Apr 12 – March month end data available for presentations
Apr 14 – Drafts of all presentations complete
Apr 17-21 – Dry Runs of Director’s Review Presentations
Apr 21 – Supporting documents for review on SharePoint
Apr 27 – Final presentations due
May 1 – Final review of review Web Site (admins and CAMs)
May 2 – All materials posted for Director’s Review
May 9-12– Director’s Review
February BCRs – P6 PMB freeze for CD-2/CD-3
  Intent is to respond to January IPR feedback only
Mar 10 – PMO provides updated data (Feb BCRs) for Cost Books
Mar-May – Clean cost/schedule data period for OPA Review
Mar 31 – Cost Book updates by CAMs complete (updated to match February BCRs data)
May 15 – April month end data available for presentations (this will be final data for OPA review)
May 26 – Drafts of all presentations complete
May 26 – Responses to DR Recommendations complete
May 29-Jun 2 – Dry runs of OPA presentations
Jun 7 – Final presentations due
Jun 8-9 – Final review of review Web Site (admins and CAMs)
Jun 13 – All materials posted for OPA review
Jun 27-30 – OPA Review
August – DOE ESAAB approval