## Sheet1
MOLLER Design Review Schedule | time axis 2021-01-01 to 2024-12-01
MOLLER Schedule |  |  | 2021-01-01: 2021; 2022-01-01: 2022; 2023-01-01: 2023; 2024-01-01: 2024
Review | Start | End | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PDR - Downsteam Toroid | 2021-03-29 | 2021-03-29 | bar: 2021 Mar
PDR - Trigger and DAQ | 2021-03-18 | 2021-03-18 | bar: 2021 Mar
PDR - Magnet Power Supplies, Leads, Jumpers | 2021-04-30 | 2021-04-30 | bar: 2021 Apr
PDR - Beam Pipes, Bellows and Windows | 2021-07-12 | 2021-07-12 | bar: 2021 Jul
PDR - GEM Modules | 2021-09-14 | 2021-09-14 | bar: 2021 Sep
PDR - Detector Systems (except GEMs) | 2022-01-12 | 2022-01-14 | bar: 2022 Jan
PDR - Hydrogen Target | 2022-01-20 | 2022-01-20 | bar: 2022 Jan
PDR - Spectrometers | 2022-05-23 | 2022-05-24 | bar: 2022 May
PDR - Shielding and Utilties | 2022-06-01 | 2022-06-01 02:24 | bar: 2022 Jun
FDR - All Systems | 2022-12-05 | 2022-12-08 | bar: 2022 Dec
CD-3a Directors Review | 2022-11-15 | 2022-11-17 | bar: 2022 Nov
CD-3a Independent Project Review | 2023-01-10 | 2023-01-12 | bar: 2023 Jan
CD-3a Approval | 2023-02-12 | 2023-02-12 | bar: 2023 Feb
Independent Final Design Review (doc review) | 2023-01-12 | 2023-02-05 | bar: 2023 Jan to 2023 Feb
Independent Final Design Review (in-person) | 2023-02-06 | 2023-02-08 | bar: 2023 Feb
CD-2/CD-3 Directors Review | 2023-05-09 | 2023-05-12 | bar: 2023 May
CD-2/CD-3 Independent Project Review | 2023-06-27 | 2023-06-30 | bar: 2023 Jun
CD-2/CD-3 ESAAB Approval | 2023-07-20 | 2023-07-20 | bar: 2023 Jul
Long-Lead procurements | 2023-02-13 | 2024-01-29 | bar: 2023 Feb to 2024 Jan
Construction | 2023-07-21 | 2024-09-03 15:00 | bar: 2023 Jul to 2024 Sep
Installation | 2024-09-04 15:00 | 2025-12-15 | bar: 2024 Sep to 2024 Nov
Formulas:
End = [Start]+1
End = [Start]+0.1
Start = [End, row above]+3+4*7
Start = [End, row above]+1