## Slide 1
DOE/SC CD-3A/Status Review
of the
Measurement of a Lepton-Lepton Electroweak Reaction (MOLLER) Project
Thomas Jefferson National Accelerator Facility
January 10-12, 2023
Alex Bachowski
Committee Chair
Office of Science, U.S. Department of Energy
http://www.science.doe.gov/opa/

## Slide 2: Review Committee Participants
Alex Bachowski, DOE/SC, Chairperson

## Slide 3: Charge Questions
Is the project team effectively executing the work? Are technical issues appropriately and proactively being addressed? Are the proposed CD-3A long-lead procurements appropriate?
Are the cost and schedule estimates credible? Do they include adequate scope, cost, and schedule contingency? Are the estimates for the proposed CD-3A long-lead procurements appropriate and can these procurements be properly tracked?
Is environment, safety, and health (ES&H) and quality being properly addressed given the project’s current stage of development?
Is the project being properly managed? Are risks being effectively managed? Is the management team in place to successfully execute the CD-3A scope?
Is the project appropriately addressing the recommendations from the prior DOE SC reviews?
Is the project ready for CD-3A approval?

## Slide 4: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
Is the project team effectively executing the work? YES Are technical issues appropriately and proactively being addressed? YES Are the proposed CD-3A long-lead procurements appropriate? YES
Is the project appropriately addressing the recommendations from the prior DOE SC reviews? YES
Is the project ready for CD-3A approval? YES

## Slide 5: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
A list of CD-3a items were shown and their relevance discussed: Toroid Magnets; Magnet Power Supplies; Beam Pipes and Bellows; Liquid Hydrogen Target Chamber; Moller Polarimeter Collimator. Main justification for CD-3A procurements is risk reduction for potential extended vendor production schedules for the majority of items.
Findings
Target
Time-depended target flow simulations were shown. Using improved HPC resources 18 seconds of beam time have been simulated. Results show that the optimized design meets requirements. Qweak measurements are being used to validate the design and simulations.
The target chamber design is being revised for value engineering, using two half-length sections, avoiding the need for new expensive tooling at the vendor. Review of design calculations to incorporate this change is expected to be completed shortly.
Current cryoplant only supports 1.4kW cooling power, plant 2 needed for beam operation at full power. A second unit, built by JLAB, is expected to be available from September 2024.

## Slide 6: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
Target is designed following a standard JLAB process
  JLAB Pressure Safety Supplement
  Independent review of fire protection was performed
  Custom lifting fixtures are done to code
  Detailed QA requirements
  Safety Systems are specified
Most designs are finished including 2D fabrication drawings.
Drawings are kept in TeamCenter and UpChain.
The Qweak heat exchanger will be reused.
The H2 pump is based on the Qweak design. The drive motor will be outside of the cryostat.
Slow Control system design is 90% complete.
Findings
Target (cont.)

## Slide 7: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
A new CAM will be joining the project in January 2023.
The present design fulfills the physics requirements. Key design requirements and fabrication/installation tolerances are derived from the physics simulations.
Tracking studies through the magnetic field were performed. Minor tweaks resulting from features of the coil prototypes will be included in a later iteration. No changes to the results are expected.
Alignment tolerances were studied, and the design is acceptable even in worst case scenarios of correlated misalignment of 3 mm. The expected alignment is better than +/- 0.5 mm.
Radiation tests of epoxy resin (CTD 403) were completed. Results show that the epoxy system is adequate in the operating temperature range of interest. Further cross-checking dose calculations from FLUKA vs GEANT is planned to confirm that irradiation levels applied during the test are well understood.
Findings
Spectrometer

## Slide 8: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
A new CAM for 1.08 Installation joined the project recently.
A draft Installation System Requirements Document was recently revised.
The installation schedule of linked planning packages in P6 was shown.
Risk 8.01 Staging space for pre-assembly and survey of equipment remains “high” though spaces have been identified which could alleviate the problem.
Risk 8.02 Installation Manpower Deficit remains “medium.”
Findings
Installation

## Slide 9: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
The project made significant progress in spectrometer and target, and window design, with various prototypes under test with promising results.
All design aspects, and in particular those relevant to the CD-3A scope, were covered in detail at the Final Design Review (FDR) held in December 2022.
The project provided a strong justification for planned CD-3A advance procurements in terms of schedule, cost and risk.
The project incorporated recommendations from CD-3A Director’s Review, in particular by adding power supplies to the CD-3A scope.
Comments and recommendations from the recent FDR are being addressed.
Following the significant progress in the design and completion of FDR, the project is ready to proceed with the proposed CD-3A scope.
Comments (1 of 2)

## Slide 10: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
Several steps need to be completed in the next 2-3 months (by end of March) before proceeding with CD-3A procurement contracts: approve and release remaining drawings, complete test of prototype power supply, complete characterization and preliminary testing of prototype coils.
In consultation with vendors, the project should consider adjusting the deadlines to exercise fixed price options for spectrometer coils and power supplies to reflect timeline of prototype fabrication and testing.
The installation schedule of linked planning packages in P6 was shown. This is sufficient for the present state of the project. For CD-2/3 a more granular, resource loaded schedule with staffing plan needs to be developed. This would include installation drawings. The present workforce allocation in this area appears light.
Comments (2 of 2)

## Slide 11: 2.1 Target and Spectrometer G. Sabbi, LBNL / Subcommittee 1
Proceed to CD-3A.
Before CD-2/3:
  Develop a more granular, resource loaded installation schedule including staffing plan.
  Provide preliminary installation drawings.
Recommendations

## Slide 12: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Is the project team effectively executing the work? Are technical issues appropriately and proactively being addressed? Are the proposed CD-3A long-lead procurements appropriate?
YES & YES & YES
Is the project appropriately addressing the recommendations from the prior DOE SC reviews?
YES
Is the project ready for CD-3A approval?
YES

## Slide 13: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Findings (1 of 3):
Detectors (mostly NSF and CFI scope):
  The Gas Electron Multiplier (GEM) production orders have not been placed yet. UVa and SBU have places “in the queue” with CERN and have prior experience obtaining GEMs from CERN and building detectors from them.
  GEM electronics in SBS are being actively monitored for failure rate.
  GEM support structure is still in design phase. Stiffness is improved.
  Pion detector has gone through a significant redesign. Segmentation now matches that of ShowerMax, aiding background reduction. The timeline to have a final pion detector design is late spring 2023.
  Materials for light guides are tested and preferred type selected.
  Materials for long pass filters on PMTs selected and rad-qualified, but still need to make final wavelength pass-band choice.
  Integrating detectors are testing pre-production model. All different type shapes have been built. PMT lifetime (total charge at anode) is within acceptable limits for the duration of the experiment.
  ShowerMax detectors are at the stage of testing prototypes.
  Trigger detectors have chosen scintillator and WLS readout, PMT and base design, and are assembling prototype.

## Slide 14: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Findings (2 of 3):
DAQ (mostly NSF and CFI scope):
  FPGA firmware to readout the ADC and Trigger Interface (TI) is 90% complete.
  Full DAQ chain testing has not started yet, but MOLLER team plan to start it in the next 6 months.
  Full 16-channel Integrating ADC board is now available.
  Noise study of long ADC cabling has been done at U. Manitoba.
  Pre-baseline schedule and cost variances are due to shortage of DAQ staff at JLab
  The baseline Beam Charge Monitor (BCM) electronics is the legacy JLab design. New BCM electronics are being designed by JLab and not in scope of MOLLER.
  U. Manitoba already has all the ADCs and FPGAs parts in hand.
  HVMAP DAQ integration work has not started yet.

## Slide 15: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Findings (3 of 3):
Infrastructure:
  One of the three identified barite loaded concrete vendors has informed the project that they will provide a budgetary quote by the end of January 2023
  Electrical work in Hall A is required to provide additional distribution of power.
  Most of the infrastructure cost is shielding.
  Cable tray and cable support designs are still in progress. Cables and connectors are expected to be regular stock items with normal delivery times.
General:
  First revision of all System Requirement Documents (SRDs) and Interface Control Documents (ICDs) have been completed and signed.
  The Bill of Materials (BOMs), both JLab and non-JLab designs, are being periodically reviewed for lead times and obsolescence.

## Slide 16: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Comments (1 of 2):
General:
  Independent Final Design Review (FDR) conducted in December 2023 was very thorough.
  Some of the recommendation tracker’s deadlines and estimated completion dates that were well past due and would benefit from a review.
  All groups demonstrated cognizance of JLab ES&H and QA/QC expectations.
  Staging detectors at William&Mary Hi-Bay will help with overall schedule risk.
Detectors:
  The strong relationship with Idaho State University has made the radiation testing go smoothly. Access to the Idaho Accelerator 8 MeV electron beam has been a significant help. Extensive spectrometer data on wavelength dependence at various radiation dose levels has been obtained and analyzed.
  The strong relationship with U. Manitoba electronics group is important for electronics work and HVMAPS implementation.
  Good progress on the main detector mechanical structure has been made. The latest revision of the structure still needs to get simulated.
  Lead times for GEM frames were not clear.

## Slide 17: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Comments (2 of 2):
DAQ:
  The FPGA has significant headroom with respect to resource utilization to support any new minor features that might arise.
  Since the funding is available and to reduce supply chain risks, the project would benefit from purchasing as much of electronic parts as possible and as soon as possible. BOMs are being monitored regularly for lead times, but industry-wide these lead times remain uncertain.
  Leveraging the existing DAQ architectures from Parity and SBS experiments has significantly reduce a lot of design risk.
Infrastructure:
  Establishing a permanent, non-interim CAM before procurement starts is going to be critical.
  Infrastructure to finish all drawings by early summer 2023 appears doable.
  RadCon is very much involved in the shield design process. Shielding physics design makes good & extensive use of knowledge base from PREX/CREX series.

## Slide 18: 2.2 Detectors, DAQ, and Infrastructure L. Ruckman, SLAC / Subcommittee 2
Recommendations (complete all these before CD-2/3 review):
Complete the planned prototype detector tests.
Proceed with hire(s) into the DAQ group.
Develop further the Installation plan with finer granularity.
Proceed to CD-3A.

## Slide 19: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
The ES&H, Cost and Schedule and Project Management Subcommittee
Ron Ray – Fermilab
Kurt Fisher - DOE/OPA
Sergio Zimmerman – LBNL
Whitney Hughes - PNNL
Jim Niehoff – Fermilab
Thank you to the project team for your on-target presentations and helpful discussions!

## Slide 20: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Are the cost and schedule estimates credible? Do they include adequate scope, cost, and schedule contingency? Are the estimates for the proposed CD-3A long-lead procurements appropriate and can these procurements be properly tracked? Yes.
Is environment, safety, and health (ES&H) and quality being properly addressed given the project’s current stage of development? Yes.
Is the project being properly managed? Yes. Are risks being effectively managed? Yes. Is the management team in place to successfully execute the CD-3A scope? Yes, but some work remains to fill out the project team to execute the full project scope. The project is aware of this and is working with the Lab to fill open positions.
Is the project appropriately addressing the recommendations from the prior DOE SC reviews? Yes.
Is the project ready for CD-3A approval? Yes, after updating CD-3A contingency analysis.

## Slide 21: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings ES&H and Quality
The Hazard Analysis Report (HAR) was updated in October 2022 to include the electrical program updates, address the COVID-19 pandemic, and the 2021 IPR review comments.
The HAR references and links to ES&H Manual Chapter 3210 Work Planning, Control, and Authorization Process including the Task Hazard Analysis Worksheet.
The HAR indicates an outside Fire Protection consultant was retained to analyze the hydrogen target.
The HAR addresses beamline reconfiguration in Hall A.
The HAR indicates that a Hydrogen leak could possibly create an oxygen deficiency hazard. This risk is identified in the Table 1 MOLLER IE Hazard Assessment Matrix.
The ES&H presentation included a link to a flow chart for Designing, Fabricating, Procuring and Shipping equipment for use at Jefferson Lab.
The ES&H presentation addressed the laboratory’s process for accepting non-NTRL equipment.
The Quality Assurance Program (QAP) defines performance/inspection and acceptance testing and provides several criterions.
The QAP addresses design control, reviews, interfaces and verification.

## Slide 22: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings
The management team has experienced some turnover. A few acting CAMs remain.
The project cost range is $45.8M to $55.4M.
The project is currently funded at $48.66M and has a point estimate of $37.3M.
The Project benefitted with forward funding of $31.12M through the Inflation Reduction Act (IRA).​
The project has a funding profile that was significantly improved thanks to forward funding of $31.12M through the Inflation Reduction Act (IRA). FY23 is the last year of funding, with the project expecting $4M.
Cost contingency has increased from the CD-1 value of $10.9M to $11.4M, which is 32% of the TEC or 38% of the TEC to go. ​

## Slide 23: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings
The presented cost of the CD-3a scope is $5.8M. The cost breakdown is:
  Toroid Magnets ($2.88M)
    Upstream magnet conductor and coil fabrication with associated hardware
    Upstream collimators, blocker and two-bounce shield (tungsten)
    Downstream magnet coils and associated hardware
    Downstream collimators (tungsten)
    Downstream magnet enclosure
  Magnet Power Supplies ($1.00M)
  Beam Pipes and Bellows ($1.08M)
  Liquid Hydrogen Target Chamber ($0.56M) 5. Moller Polarimeter Collimator ($0.02M)
  Contingency ($0.26M)
The presented contingency on the CD-3A scope is about 5%.
Justification for CD-3A scope is to reduce schedule risk to ensure physics results on a competitive schedule and to fit into the CEBAF accelerator schedule.
The project plans to implement L2 milestones for completion of CD-3A scope, as well as charge codes for each control account.
CD-3A is expected to be achieved by 3QFY23, CD-2/3 by 1QFY24 and CD-4 by 4QFY27.

## Slide 24: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings
MOLLER has two significant in-kind contributions from NSF and a grant from the Canadian Foundation for Innovation (CFI). These are providing funding for many of the detectors and the data acquisition system. The equipment grants represent about 20% of the cost of the MOLLER equipment.
Both grants are fully funded and allow these scope elements to advance to construction independent of DOE funding authorization.
An ICRADA exists between JLab and University of Manitoba.
MOUs between JLab and the various Universities doing project work exist and have all been signed by the project. About half have been signed by the Universities.
NSF is providing reporting on university progress to DOE which allows the project team to properly track the MIE CPI and SPI.​
The project team has processed 20 Baseline Change Proposals to date. And 13 in the past year.
BCRs are initiated by the CAM or PM. All BCRs are tracked in the change request log.
A BCR was implemented to account for the increased rates of material costs in FY23$. The project plans to issue a BCR to update the labor rates to FY23 in the near future. Currently the plan reflects FY19 labor rates.

## Slide 25: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings
The project expects to have a budgetary estimate for the barite concrete by the end of January after receiving information back on the RFI.
Certified EVMS system and change control process have been in use for over a year.
The project utilizes P6 as their scheduling software. P6 and the lab’s cost system, Costpoint, are integrated into Deltek Cobra.
NSF scope has been integrated into P6 and status meetings are held monthly. CFI scope is not fully integrated into P6. The project plans to complete integration of the scope into P6 in FY23.
JLab provides a project management qualification course to new CAMs.
Currently there is 1 project controls professional who supports the project.
Two contract specialists are assigned to the project, as well as the contracts lead.
The remaining individual project procurements are all estimated to be < $1M, below the $3M threshold for site office review.
Contracts and project controls take part in updating the procurement register.
A CAM was hired for WBS 1.03 with an expected start date of January 17th, 2023. There is still a CAM opening for WBS 1.06 Infrastructure. The project plans to hire a QA lead and Risk lead to fill open positions prior to CD-2/3.
Requirements and Interfaces are complete and under revision control.

## Slide 26: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings
The Technical Design Report is complete. The last FDR was completed in December 2022. The project team has requested that the committee evaluate the FDR review committee makeup and results to offer thoughts concerning perceived independence and whether another review is needed prior to CD-2/3.
Overall design maturity is > 90%.
HAR, QAP, RMP and SVAR have been updated, reviewed and approved.
KPPs are fully defined.
Critical path for construction runs through toroid procurement.
Critical path from start of installation flows through infrastructure and target.
The DOE project is responsible for installation of the full project scope including in-kind contributions.
Installation depends on completion of the existing Hall A physics program. The project team has identified 3 months float between MOLLER readiness and SBS Hall A clean out.​
JLAB will be implementing the Experimental Readiness Review (ERR) process for the Installation Planning in Hall A.​
The project currently has 17 months of schedule contingency to CD-4.

## Slide 27: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings
The Project Manager flashed through the installation sections of the P6 schedule to demonstrate the level of detail.
The Lab has a lessons learned database that is shared with other labs.
Project risk registers captures high-level risks from in-kind partners. Risks are mapped to individual activities in P6.
Safran is utilized to perform project risk analysis.
The P80 risk value yields a finish date of March 2027 and a cost value of $44.7M.
The MOLLER project plan includes features to protect equipment, however, this is not documented in an Equipment Protection Plan.

## Slide 28: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Findings

## Slide 29: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Comments – ES&H and Quality (1 of 4)
The project should verify if there is a risk of fire or explosion from a release of hydrogen in the HAR Table 1 Hazard Assessment Matrix. If this is addressed in the Fire Protection consultant’s analysis then, suggest this be added into the HAR or as an attachment (appendix). This should be addressed prior to the CD-2/3 IPR.
The project should modify the HAR to address Natural Phenomena as listed in the DOE Guide 413.3-12, Chg. 1 prior to the CD-2/3 IPR.
The project should verify that the Fire Protection Consultant’s analysis does or does not need to be addressed in the SAD as part of the Hall A beamline reconfiguration. This should be addressed prior to the CD-2/3 IPR.
The project should verify that the HAR does in fact have the COVID-19 paragraph as stated in the change log revision table.
The project should consider referencing As Low As Reasonably Achievable (ALARA) standards. Neither the Shielding Engineering presentation nor the HAR addressed ALARA. This should be addressed prior to the CD-2/3 IPR.
In lieu of the Construction Project Safety and Health Plan, the project should consider an ES&H installation Plan for the beamline and Detector prior to the CD-2/3 IPR.
The project should consider separate presentations dedicated to Quality Assurance and incorporation of Lessons Learned prior to the CD-2/3 IPR.

## Slide 30: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Comments (2 of 4)
MOLLER has a strong team that can deliver the project, however, the bench is not deep. The project and the Lab would benefit from a full-time, experienced deputy PM.
Communication across the institutions contributing to the project is effective. The project benefits from a committed group of collaborators.
The contingency assigned to the CD-3A scope is not adequate. The cost and schedule uncertainty that is associated with part of the CD-3a scope should be evaluated and appropriately accounted for in the project’s risk register. A bottom-up, risk-based contingency should then be developed for the CD-3a scope.
The float to CD-4 should be evaluated based on a risk analysis and set prior to the CD-2 baseline.
A separate presentation describing the installation plan should be part of the agenda at the CD-2/3 IPR.
The project would be wise to plan for an independent review of the installation plan at an appropriate time.
Filling out the project team (DPM, Infrastructure CAM, Risk Manager, QA Manager) to execute the construction phase is critical for CD-2/CD-3 readiness.
The University MOUs should all be signed by the CD-2/3 IPR.

## Slide 31: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Comments (3 of 4)
The KPPs are fully defined and mature, but they depend on delivery of in-kind contributions and scope from Lab infrastructure projects. These risks should be appropriately reflected in the project’s schedule risk analysis and should be documented in an assumptions document.
A formal agreement with the Lab could provide a means of formalizing roles and responsibilities for contributions from the Lab that are necessary to successfully complete the project.
Detailed plans for removing the existing experiment in Hall A do not yet exist, but the Lab has experience in this area.
The project team has implemented an effective EVMS system that allows them to track progress. This is commendable at this phase of the project.​
The project team is dealing with longer than normal lead times and limited vendors. These risks must be appropriately accounted for in project planning.
The Inflation Reduction Act (IRA) has benefited the project by improving the available funding and improving the schedule by one year, however, the project team needs to continue to refine cost and schedule estimates to be ready for CD-2/3.​

## Slide 32: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Comments (4 of 4)
A draft of a Transition to Operations plan should be available by the CD-2/3 IPR.
The project risk register needs to be updated on a reoccurring basis.
The risk register has a few open cells and should be reviewed and updated prior to CD-2/3.
A rigorous risk workshop should be held prior to the CD-2/3 IPR.
MOLLER can profit from an Equipment Protection Plan document. Such a document could reveal aspects associated with ES&H that were not previously considered.

## Slide 33: 3. Environment, Safety and Health, Cost and Schedule, Project Management R. Ray, FNAL / Subcommittee 3
Recommendations
Update the cost estimates, risks and contingency analysis for the CD-3A scope prior to ESAAB.
Prepare an assumptions document by the CD-2/3 IPR.
Work with Lab management to identify a full-time, experienced deputy Project Manager as soon as possible and also address the other open positions. Report on progress to the DOE Nuclear Physics Program Office by April 2023.
Proceed to CD-3A after updating the contingency analysis.