## Sheet1
IPR OCT 03rd to 05th - Preparation and Timeline | [32 empty] | All | Review |  | Review | Dry runs for presentations
Version No. | 1 | [31 empty] | Actions | and upload |  | Website | and CAM interviews
Date | 08.16.23 | [31 empty] | Complete | all docs |  | LIVE | and drill downs | IPR
PM | R. Fair |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | T | W | T
|  |  | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-10-03 | 2023-10-04 | 2023-10-05
No. | Task | Owner
Rec #1 | Project CAMs and engineers should work with procurement staff to get as much of the CD-3A scope as possible assigned to buyers, out for bid, and awarded prior to the CD-2/3 review. | CAMs
Rec #2 | Complete the prototype power supply Factory Acceptance Test (FAT) as quickly as possible. | M. Dion
Rec #3 | Assess cost/schedule impacts from JLab safety related delays impacting MOLLER installation schedule and incorporate into the baseline before the CD-2/3 OPA Review | R. Fair / L. Louwes
Rec #4 | The following documents need to be revisited and updated: Draft PEP ready for signature after CD 2/3 Review; Acquisition Strategy if any major changes since last approval; Project Management Plan needs CFI/RM signature; schedule EVMS review for Fall 2023; update Hazard Analysis Report for electrical work and other potential hazardous activities; complete a Construction Project and Safety Health Plan prior to CD-2/CD-3.
| Draft PEP ready for signature after CD 2/3 Review | R. Fair | bar: 2023-08-30
| Acquisition Strategy if any major changes since last approval; | R. Fair, M. Laney | bar: 2023-08-28
| Project Management Plan needs CFI/RM signature | R. Fair, M. Gericke | bar: 2023-08-29
| schedule EVMS review for Fall 2023; | A. Lung
| update Hazard Analysis Report for electrical work and other potential hazardous activities | B. Rainey | [38 empty] | Request sent to Bill to update HAR by Aug 30th | bar: 2023-08-30
| complete a Construction Project and Safety Health Plan prior to CD-2/CD-3. | B. Rainey | [38 empty] | Request sent to Bill to produce CSHP by Aug 30th | bar: 2023-09-01
Rec #5 | Revisit the Risk Analysis and update the Risk Register with current risks since CD-3A Approval and prior to CD-2/CD-3. | K. Demhelt, R. Fair, CAMs | bar: 2023-09-07
Rec #6 | Revisit the L2 and L3 Milestones chart to reflect current actual dates in preparation for the CD-2/CD-3 Review. | R. Fair | bar: 2023-09-04
Rec #7 | Update the Cost Book to include the assumptions and methodology used for deriving labor estimates for the CD-2/CD-3 Review | R. Fair/CAMs | bar: 2023-09-08
Rec #8 | Add a CD-3A slide on status of the long lead procurements in each L2 talk where applicable. | CAMs | bar: 2023-09-01
Rec #9 | Include the total cost and schedule contingency for the project, a summary of the method used to obtain them, and how they relate to project risks in the Project Manager presentation on the first day of the review. | R. Fair | bar: 2023-09-01
Rec #10 | In the science overview talk, include a one-slide summary of all the improvements relative to E158 that make MOLLER possible. | K. Kumar | bar: 2023-09-01
Rec #11 | Proceed to the DOE CD-2/3 review. | All
| Update WBS dictionary | R. Fair
| Update slides for IPR | CAMs / Tech Leads | bar: 2023-09-01
| Update cost books for IPR | CAMs | bar: 2023-09-08
| Prepare additional slide pack for CAM interview and drill down (Not to be uploaded to review website) | CAMs | bar: 2023-09-12
| Collect and upload all supporting information to website | CAMs | bar: 2023-09-14
| IPR review website | Admins | bar: 2023-09-08