## NCR Descriptions
TravelerId/Part Info | Description
Coupler modified conflat gasket | Please see inspection traveler # SNS-CMM-CST-FPC-MODG, sequence # 2
Coupler outer conductors | Please see Outer conductor inspection traveler sequence # 1
CRM9005020-1001 | According to the part list in the traveler I am missing (2)CRM9005020-1001 Patch 1A Parts have been shipped by vendor and stored with rest of assembly.
CRM9005020-1003 | Through an incoming inspection I discovered that two panels were missing to have a full assembly. Parts have been shipped by vendor and stored with rest of assembly.
FPC 6.75 | Please see inspection summary report, SNS-INSR, sequence number 39
FPC Bellows Assy. | Twelve of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .003-.015 out of true position tolerance.
FPC Bellows Assy. | Fourteen of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.022 out of true position tolerance.
FPC Bellows Assy. | Nine of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.008 out of true position tolerance.
FPC Bellows Assy. | Fourteen of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.031 out of true position tolerance.
FPC Bellows Assy. | Eleven of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.018 out of true position tolerance.
FPC Bellows Assy. | Eight of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .002-.016 out of true position tolerance.
FPC Bellows Assy. | Eleven of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.015 out of true position tolerance.
FPC Bellows Assy. | Eleven of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .002-.022 out of true position tolerance.
FPC Bellows Assy. | Eleven of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.021 out of true position tolerance.
FPC Bellows Assy. | Seven of the sixteen .250-20UNC-2Btapped holes on the 12.105 bolt circle are out of the allowable +/-.010 true position tolerance referenced on DWG.# CRM-900-6000-0031.Descrepancies range from .001-.011 out of true position tolerance.
HOM Probe Tip | 0.100 +/-0.005 Actual 0.0935
HVA warm bl valve | Valve was evaluated during the particulate study. It had a leak across the gate.
MB cavity | Please see inspection traveler sequence # 5
MB cavity | Please see inspection traveler sequence # 6
MB cavity | Please see inspection traveler sequence # 7
Medium Beta cavity | Please see inspection traveler # SNS-CMM-CST-CAV-CMM sequence # 11
SNS FPC Window | Window tip length.Nom:12.165 Act:12.15386
SNS FPC Window | Windoe tip length. Nom:12.165 Act:12.17133
SNS FPC Window | Window tip length. Nom:12.165 Act:12.17565
SNS FPC Window | Window tip length. Nom:12.165 Act:12.15329
SNS FPC Window | Window tip length. Nom:12.165 Act:12.17581
SNS FPC Window | Window tip length. Nom:12.165 Act:12.17253
SNS High Beta Inner Magnetic Shield | The nonconforming items are specified on Inspection Summary Report #33.
SNS High Beta Inner Magnetic Shield | The nonconforming items are listed on Inspection Summary Report #35
SNS High Beta Inner Magnetic Shield | The nonconforming items are specified on Inspection Summary Report #36
SNS High Beta Outer Magnetic Shield | The nonconforming items are specified on Inspection Summary Report # 34.
SNS High Beta Outer Magnetic Shield | The nonconforming items are specified on Inspection Summary Report #37
SNS High Beta Outer Magnetic Shield | The nonconforming items are specified on Inspection Summary Report #38
SNS MB Vacuum Vessel | The following items have been found to be out of tolerance. See inspection traveler SNS-CMM-CRY-VAC-INSP,sequence #3 for as found dimensions.1)Size and location of reinforcing rings.2)Support block locations.3)Tophat flange locations.4)Rail
SNS MB Vacuum Vessel | The following items have been found to be out of tolerance. See inspection traveler SNS-CMM-CRY-VAC-INSP,sequence #2 for as found dimensions.1)Size and location of reinforcing rings.2)Support block locations.3)Tophat flange locations.4)Rail
SNS MB-08 Cavity | Please refer to machanical inspection traveler SNS-CMM-CST-CAV-CMM-Rev 3 (Sequence #12).
SNS Outer Conductor | Please refer to inspection traveler SNS-CMH-CST-FPC-OUTC Seq.# 6 for inspection data.
SNS RETURN END CAN | 5X10-8 leak was found in the ceramic feed through. Part returned to vendor.
SNS Supply end can | The following dimensions were found out of tolerance.See traveler # SNS-CMM-CRY-SENC-INSP,sequence # 2 for data.1) Bayonet locations2) Bayonet box offset3) Endplate and beampipe sealing surface flatness.4) Bridging ring diameter
SNS-Cryomodule Saddle | 19.62
SNS-MB Prototype cavity | .625-11UNC threads are .38
SNS-MB Prototype cavity | .625-11UNC threads are .38 USE AS ISTooling changed to accommodate.Tim Whitlatch 12/16/02
SNS-MB Prototype cavity | .625-11UNC threads are .38 USE AS ISToling modified to accommodateTim Whitlatch 12/16/02
Vacuum Vessel Tophjat Assy. | Please refer to Inspection traveler\r\nSNS-CMM-CRY-VAC-INSP (Seq. # 7) for CMM data associated with Vacuum Vessel Tophat (Assy.# 6).
SNS-MB cavity | Please see inspection traveler # SNS-CMM-CST-CAV-CMM sequence #14.
SNS Cavity (MB-04) | Please refer to traveler SNS-CMM-CST-CAV-CMM (Sequence #15)for CMM inspection data.
Vacuum Vessel Tophat Assy. | Please refer to Inspection TravelerSNS-CMM-CRY-VAC-INSP (Seq.# 8) for CMM inspection data associated with Vacuum Vessel Tophat (Assy.# 007).
Vacuum Vessel Tophat Assy. # 005 | Please refer to Inspection TravelerSNS-CMM-CRY-VAC-INSP (Seq.#6)for CMM data associated with Vacuum Vessel Tophat (Assy.#005)
Coupler outer conductor | Please see inspection traveler sequence # 2
Coupler outer conductor | Please see inspection traveler sequence # 4
Coupler outer conductors | Please see inspection traveler sequence # 3
FPC Doorknob Assy.
FPC Doorknob Assy.
FPC Doorknob Assy.
FPC Doorknob Assy.
H-3 | Leak in the metal seal gasket on bridging bellows. Location is between cavity HB-12 & HB-13. Leak is on the Supply side of the bellows. Leak size is 1.52e-9. See chart in e-log.
H-3 | Leak in the metal seal gasket on bridging bellows. Location is between cavity HB-12 & HB-13. Leak is on the Supply side of the bellows. Leak size is 1.52e-9. See chart in e-log.
MB- Helium vessel | Please see inspection traveler # SNS-CMM-CST-HELV-INSP sequence # 2
Med. Beta Inner Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-IMAG-INSP sequence #8.
Med. Beta Inner Magnetic Shield | The nonconforming items have been specified on traveler SNS-CMM-CRY-IMAG-INSP sequence #7.
Med. Beta Inner Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-IMAG-INSP sequence #10.
Med. Beta Inner Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-IMAG-INSP sequence #11
Med. Beta Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-IMAG-INSP sequence #9
Med. Beta Outer Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-OMAG-INSP sequence #7.
Med. Beta Outer Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-INSP sequence #8.
Med. Beta Outer Magnetic Shield | The nonconforming items have been specified on traveler SNS-CMM-CRY-INSP sequence #9.
Med. Beta Outer Magnetic Shield | Nonconforming items are specified on traveler SNS-CMM-CRY-OMAG-INSP sequence #10.
Med. Beta Outer Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-OMAG-INSP sequence #11.
Med. Beta Outer Magnetic Shield | The nonconforming items are specified on traveler SNS-CMM-CRY-OMAG-INSP sequence #12.
SNS FPC Outer Conductor | Please refer to traveler SNS-CMH-CST-FPC-OUTC (Seq. # 5) for details.
SNS FPC Window | Window tip length. Nom:12.165 Act:12.15610
SNS FPC Window | Window tip length. Nom:12.165 Act:12.17173
SNS FPC Window | Window tip length. Nom:12.165 Act:12.17003
SNS FPC Window | The Window tip length is out of tolerance . Nom:12.165 Act:12.19743
SNS FPC Window | Window tip length. Nom:12.165 Act:12.1730
SNS Outer Conductor | Please refer to inspection travelerSNS-CMH-CST-FPC-OUTC Seq.# 7 for inspection data.
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-RENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CRY-SENC-INSP
SNS-CM-CST-FLNG-INSP
SNS-CM-CST-FLNG-INSP | See travler for pictures of defects
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB | Locking Helicoils installed on assembly.
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB | See Traveler!
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB | Silver plated bolt galled during doorknob installation. The bolt broke and needs to be removed. Helicoil was a locking helicoil.
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-DKNB | Helicoils reworked and found to be ok.BCC 01/06/05
SNS-CM-CST-FPC-DKNB | See pg 2.BCC
SNS-CM-CST-FPC-DKNB
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler! "BRAZING"
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler! "BRAZING"
SNS-CM-CST-FPC-INNX | See Traveler! "BRAZING"
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!Small dimensional descrepencies.
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler! "BRAZING"
SNS-CM-CST-FPC-INNX | See Traveler for details!
SNS-CM-CST-FPC-INNX | See Traveler! "BRAZING"
SNS-CM-CST-FPC-INNX | See Traveler! "BRAZING"
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX | See Traveler!
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-INNX
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC | Copper on 6.75" flange near instrumentation tube is flaking off. Copper near DESY seal is not uniform and is flaking as well.
SNS-CM-CST-FPC-OUTC | Copper was removed during HP rinse. Small area on the 6.75" flange end is missing copper. This area is directly over one of the welds.
SNS-CM-CST-FPC-OUTC | See Traveler!
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC | Some small protrusions in copper plating in various areas too numerous to describe. Most of these protrusions are in the bore of the component. One of the larger protrusions are evident on the DESY end, inside the bore. Small slivers of tape are present
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTC
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | Part looks fine dimensionally and visually but did not see blister test data in delivery packet for this particular part.
SNS-CM-CST-FPC-OUTX | Dimensionally & Visually fine, just missing blister Test Documentation.
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX | See Traveler!
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-OUTX
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGCV
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD | See Traveler!
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD | See Traveler! Fit tested sucessfully with outer ext. on 09/21/04, also see step 5. BCC
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CM-CST-FPC-WGD
SNS-CMH-CRY-IMAG-INSP
SNS-CMH-CRY-IMAG-INSP | see traveler
SNS-CMH-CRY-IMAG-INSP
SNS-CMH-CRY-IMAG-INSP
SNS-CMH-CRY-IMAG-INSP
SNS-CMH-CRY-IMAG-INSP | See traveler
SNS-CMH-CRY-IMAG-INSP
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-OMAG-INSP | see traveler
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-OMAG-INSP
SNS-CMH-CRY-SFR-INSP
SNS-CMH-CRY-SFR-INSP
SNS-CMH-CRY-SFR-INSP
SNS-CMH-CRY-SFR-INSP
SNS-CMH-CRY-THRM-INSP
SNS-CMH-CRY-THRM-INSP
SNS-CMH-CRY-VAC-INSP
SNS-CMH-CRY-VAC-INSP
SNS-CMH-CST-CAV-CMM | See Traveler
SNS-CMH-CST-CAV-CMM
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-CMM | See Traveler!
SNS-CMH-CST-CAV-INSP | Pits on FCP flange see travler. Pictures available.
SNS-CMH-CST-CAV-INSP | Scratch on HOM flange. See travler.
SNS-CMH-CST-CAV-INSP | Pits on HOM FP flange. See travler. A flange inspection travler will be filled out.
SNS-CMH-CST-CAV-INSP
SNS-CMH-CST-CAV-VTRF | Cavity did not meet performance specs - strong FE, and anomalous Q vs E behaviour (strong Q drop, cavity performance degraded during testing, potential RF cable damage also as a result).
SNS-CMH-CST-FPC-BRTL
SNS-CMH-CST-FPC-BRTR | See Traveler!
SNS-CMH-CST-FPC-BRTR | See Traveler!
SNS-CMH-CST-FPC-BRTR | See Traveler!
SNS-CMH-CST-FPC-BRTR | See Traveler!
SNS-CMH-CST-FPC-BRTR | See Traveler!
SNS-CMH-CST-FPC-BRTV
SNS-CMH-CST-FPC-BRTV
SNS-CMH-CST-FPC-BRTV
SNS-CMH-CST-FPC-BRTV
SNS-CMH-CST-FPC-BRTV
SNS-CMH-CST-FPC-DKNB
SNS-CMH-CST-FPC-DKNB
SNS-CMH-CST-FPC-DKNB
SNS-CMH-CST-FPC-DKNB
SNS-CMH-CST-FPC-DKNB
SNS-CMH-CST-FPC-INNX
SNS-CMH-CST-FPC-INNX
SNS-CMH-CST-FPC-INNX
SNS-CMH-CST-FPC-INNX | See Traveler!
SNS-CMH-CST-FPC-INNX | See Traveler!
SNS-CMH-CST-FPC-INNX | See Traveler!
SNS-CMH-CST-FPC-INNX | See Traveler!
SNS-CMH-CST-FPC-INNX
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC | .099" seal groove depth was apparrently a typo when entering taveler data. CMM output data reflected in tolerance, and the correct groove depth of .120" was re-entered into traveler Seq. # 54.
SNS-CMH-CST-FPC-OUTC | Only one Dimension out of tolerance as per traveler and that is the Perp. of large conflat flange (.012")
SNS-CMH-CST-FPC-OUTC | Katherine I change a typo on the trveler nominal of 4.908" from 4.920" that was entered to the correct measured value of 4.902, still .001" out of tolerance
SNS-CMH-CST-FPC-OUTC | Katherine I verified by two different CMM outputs on file for this part that the OAL is as entered to be 9.444".
SNS-CMH-CST-FPC-OUTC | 5/29/03 Typo found on CMM data input for CF flg. perp. an and re-entered correct dimension of .013" and not .133" as previuosly. SW
SNS-CMH-CST-FPC-OUTC | Katherine the correct pressure drop test had been performed previously but didn't get entered into traveler and has now been entered and passed test. SW
SNS-CMH-CST-FPC-OUTC | Initial leak test o.k. After baking, this part developed a leak at the vacuum gauge flange closest to the serial number stamping. Leaking around the center of the flange, opposite of the knife edge face (between plate and flange). S.C.
SNS-CMH-CST-FPC-OUTC | Copper plating has been scraped off of some areas around DESY seal end of outer conductor. Mircea has looked at and says needs to be replated. SC
SNS-CMH-CST-FPC-OUTC | 2.125" flange is not parallel to other flanges. Scott W. measured angle of 2.125" conflat - 3.33 degrees out of parallel with 6.75" flange. SC.
SNS-CMH-CST-FPC-OUTC | Copper plating does not completely cover area near DESY seal. Mircea says must be replated.
SNS-CMH-CST-FPC-OUTC | Scratches on DESY sealing surface - S. Castagnola
SNS-CMH-CST-FPC-OUTC | Katherine,I verified the 9.440" dimension and repeated the same data as the first time and the overall length is .026" too short from the nominal 9.466".
SNS-CMH-CST-FPC-OUTC | Noticed one 2.125" flange was not parallel to other flanges. 2.06 degree tilt.
SNS-CMH-CST-FPC-OUTC | Pressure drop information has been added to the traveler.
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC | 2.125" Flange not parallel to 6.75" flange. Copper plating not uniform on 6.75" end of component.
SNS-CMH-CST-FPC-OUTC | 6 3/4" conflat gasket does not fit into groove on conflat properly - too tight.
sns-cmh-cst-fpc-outc | Initial leak test o.k. After baking, this part developed a leak at the vacuum flange closest to the serial number stamping. Leaking around the center of the flange, opposite of the knife edge face (between plate and flange). S.C.
SNS-CMH-CST-FPC-OUTC | Protrusions of copper plating.
SNS-CMH-CST-FPC-OUTC | One 2.125 vacuum port not parallel with 6.75 conflat. Copper plating on 6.75 flange has numerous visible small copper balls (bubbles).
SNS-CMH-CST-FPC-OUTC | Copper has blisters and irregularities near the 6.75" flange end.
SNS-CMH-CST-FPC-OUTC | Vacuum gauge port at the 2 o¿clock position has severe damage to the knife edge surface. Unacceptable
SNS-CMH-CST-FPC-OUTC | Small dent at the 11 o¿clock position on the 6.75¿ conflat. Very small dents or dings at the 5 o¿clock position as well.
SNS-CMH-CST-FPC-OUTC | Welds are not smooth.
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC
SNS-CMH-CST-FPC-OUTC | Copper is flaking at the 4 o'clock position at the weld, on the conflat end.
SNS-CMH-CST-FPC-OUTC | Copper plating has irregularities and blisters.
SNS-CMH-CST-FPC-OUTC | Flange to flange length is too short. Copper plating is bad.
SNS-CMH-CST-FPC-OUTC | Copper flaking at the 6.75¿ end on a weld at the 3 o¿clock position.
SNS-CMH-CST-FPC-OUTC | Weld at the 6.75" end has a raised, pointed spot where the weld was finished. Mircea says unacceptable.
SNS-CMH-CST-FPC-OUTC | Copper plating has numerous craters and voids. Copper is not smooth.
SNS-CMH-CST-FPC-OUTC | There are two very small areas that appear to be flaking copper. Both are at the one o¿clock position on the 6.75¿ flange end, on the lower portion of the middle weld.
SNS-CMH-CST-FPC-OUTC | Small area of copper flaking at the 6.75¿ end, just below the middle weld at the 4 o¿clock position.
SNS-CMH-CST-FPC-OUTC | Three areas of copper flaking at the 6.75¿ end, near the lower portion of the middle weld at the 4, 7, and 8 o¿clock positions.
SNS-CMH-CST-FPC-OUTC | Small area of flaking copper at the 6 o¿clock position near the center weld.
SNS-CMH-CST-FPC-OUTC | Scratch on Desy sealing surface. Dent or ding on 6.75" knife edge.
SNS-CMH-CST-FPC-OUTC | Copper is flaking at the weld on the conflat end.
SNS-CMH-CST-FPC-OUTC | Conflat end: Protrusion at the 7 o¿clock position at the weld, copper has flaked off the tip of protrusion.
SNS-CMH-CST-FPC-OUTC | Strong traces of chemical stains in the taper area extending down in the tube. Welds not flush. Stains all over the internal surface of the tube. Stains could not be removed by cleaning in the chemistry room.
SNS-CMH-CST-FPC-OUTC | Stain on copper plating that cannot be removed by cleaning. Stain is located on the conflat end, on the weld, at the 9 o'clock position.
SNS-CMH-CST-FPC-OUTC | . On the conflat end at the 8 o\031clock position, copper is flaking at the weld in two or three very small spots.
SNS-CMH-CST-FPC-OUTX
SNS-CMH-CST-FPC-OUTX
SNS-CMH-CST-FPC-OUTX
SNS-CMH-CST-FPC-OUTX
SNS-CMH-CST-FPC-OUTX
SNS-CMH-CST-FPC-OUTX
SNS-CMH-CST-FPC-WGCV
SNS-CMH-CST-FPC-WGCV
SNS-CMH-CST-FPC-WGCV
SNS-CMH-CST-FPC-WGCV
SNS-CMH-CST-FPC-WGCV
SNS-CMH-CST-FPC-WGD | See Traveler!
SNS-CMH-CST-FPC-WGD | See Traveler!
SNS-CMH-CST-FPC-WGD | See Traveler!
SNS-CMH-CST-FPC-WGD | See Traveler!
SNS-CMH-CST-FPC-WGD
SNS-CMH-CST-FPC-WGD | See Traveler!
SNS-CMH-CST-FPC-WGD
SNS-CMH-CST-FPC-WGD
SNS-CMH-CST-FPC-WGD
SNS-CMH-CST-FPC-WGD
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND | Re-measured inner conductor w/different coordinate reference system.
SNS-CMH-CST-FPC-WIND | Re-measured inner conductor w/different coordinate reference system.
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND | Re-calculated inner cond. position
SNS-CMH-CST-FPC-WIND | Re-calculated inner cond. position
SNS-CMH-CST-FPC-WIND | Re-calculated inner cond. position
SNS-CMH-CST-FPC-WIND | Re-calculated inner cond. position
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-FPC-WIND | 6.75" conflat will not seal. This window has been leak tested three times with three different gaskets.
SNS-CMH-CST-FPC-WIND
SNS-CMH-CST-HELV-INSP
SNS-CMH-CST-HELV-INSP
SNS-CMH-CST-HELV-INSP
SNS-CMH-CST-HELV-INSP
SNS-CMH-CST-HELV-INSP
SNS-CMH-FPC-WIND | Re-measured inner conductor w/different coordinate reference system.
SNS-CMH-TEST
SNS-CMH-TEST | 1. H05-1 Qext Field Probe. Measured value is above spec. at 3.87e12.2. Cryomodule failed Integrated Insulating Vacuum Leak Test. Vacuum pressure increased from 2.3e-7 torr to 1.2e-6 torr in 7 days and increased to 2.1e-5 torr after 19 days. see below.
SNS-CMM-CRY-IMAG-INSP
SNS-CMM-CRY-IMAG-INSP
SNS-CMM-CRY-SFR-INSP | Surveyors completed inspection 10/31/2002. NCR was not generated.
SNS-CMM-CRY-SFR-INSP
SNS-CMM-CRY-SFR-INSP
SNS-CMM-CRY-SFR-INSP
SNS-CMM-CRY-SFR-INSP
SNS-CMM-CRY-SFR-INSP
SNS-CMM-CRY-SFR-INSP
SNS-CMM-CRY-SHP-PKG | FPC conditioning travelers not closed out (responsible engineer off site, at ORNL), so FPC conditioning travelers to be sent to ORNL under seperate cover, perhaps with next module shipment.
SNS-CMM-CRY-THRM-INSP
SNS-CMM-CRY-THRM-INSP
SNS-CMM-CRY-THRM-INSP
SNS-CMM-CRY-VAC-INSP | Refer to page 10 only in inspection traveler. The following data was entered incorrectly into the inspection traveler. Measured value 0.097 should be 1.09, and measured value 0.067 should be .89. The part, CRM9003000-0013 meets inspected tolorances and i
SNS-CMM-CRY-VAC-INSP | See Traveler!
SNS-CMM-CRY-VAC-INSP
SNS-CMM-CRY-VAC-INSP
SNS-CMM-CRY-VAC-INSP
SNS-CMM-CRY-VAC-INSP
SNS-CMM-CRY-VAC-INSP
SNS-CMM-CST-BVLV-INSP | Vacuum leak on 4.62 flange
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-BELL
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM | Please refer to traveler stated abovefor CMM data.
SNS-CMM-CST-CAV-CMM | See traveler.
SNS-CMM-CST-CAV-CMM | See Traveler
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM | See Traveler!
SNS-CMM-CST-CAV-CMM
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-HPTI
SNS-CMM-CST-CAV-INSP | See travler for flange defect write up.
SNS-CMM-CST-CAV-INSP | See travler for write up on flange defects.
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-INSP | The end cell of the cavity at the field probe end has a dent and several scratches located near the field probe. A picture of the defect is available from Tim Rothgeb x5348 or rothgeb@jlab.org
SNS-CMM-CST-CAV-INSP | See travler
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-INSP
SNS-CMM-CST-CAV-VTRF | Cavity fails VTA acceptance test. Does not meet Qo/E requirements.
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-EPRB
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-MODG
SNS-CMM-CST-FPC-VGIN | Serial number on sensor does not match serial number on magnet.
SNS-CMM-CST-FPC-VGIN | This gauge did not perform properly during pre-rf bake or during RF testing. Refer to Mircea Stirbet for particular performance problems. This gauge has been removed from service.
SNS-CMM-CST-FPC-VGIN | This gauge did not perform properly during pre-rf bake or during RF testing. Refer to Mircea Stirbet for particular performance problems. This gauge has been removed from service for further evaluation.
SNS-CMM-CST-FPC-VGIN | This gauge displayed "HI x 10-2" on controller during and after RF testing. There is a build up of blue-green crusty material on the sensor at the electrical pins.
SNS-CMM-CST-FPC-VGIN | The vacuum side of this gauge has scratches and gouges. Mark Wiseman said to clean them up when ready to use.
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND | See Traveler.
SNS-CMM-CST-FPC-WIND | See Traveler
SNS-CMM-CST-FPC-WIND | See Traveler!
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND | Part looks good overall and NCR is generated for primarily as a result of the angular location of the external 3/8" dia. tubes and the depth of the 1/4-28 tapped hole on the air side.
SNS-CMM-CST-FPC-WIND | Katherine,I verified the CMM output data and re-measured assembly. The true position for the inner extension repeated as being out from nominal by .041". *************************************Katherine,True position of the inner conductor was remeas
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND | see traveler
SNS-CMM-CST-FPC-WIND | see traveler
SNS-CMM-CST-FPC-WIND | see traveler
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND | Re-calculated inner and outer conductor positions.
SNS-CMM-CST-FPC-WIND | Re-calculated inner and outer conductor positions.
SNS-CMM-CST-FPC-WIND | Re-calculated innner and outer conductor position.
SNS-CMM-CST-FPC-WIND | Re-calculated innner and outer conductor position.
SNS-CMM-CST-FPC-WIND | Re-calculated innner and outer conductor position.
SNS-CMM-CST-FPC-WIND | Re-calculated inner and outer conductor position.
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-FPC-WIND | Re-calculated inner and outer conductor positions.
SNS-CMM-CST-FPC-WIND | Re-calculated inner and outer conductor positions.
SNS-CMM-CST-FPC-WIND | Re-calculated inner and outer conductor positions.
SNS-CMM-CST-FPC-WIND
SNS-CMM-CST-HELV-INSP
SNS-CMM-CST-HELV-INSP
SNS-CMM-CST-HELV-INSP
SNS-CMM-CST-HELV-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-DIAG-FTF-INSP
SNS-CMM-TEST | SNS Cryomodule M1 NCR Report1.\tInsulating vacuum- During the first cold test the insulating vacuum seemed to have a leak from the helium vessels. After a warm up no leak could be found using a pressure test and helium mass spectrometer. After the second
SNS-CMM-TEST | 1. Piezo tuner associated with Cavity 3 was found to be shorted to ground. It was not tested. 2. The following tests were not completed on cavity 3: One hour run, Qo vs Eacc, dynamic Lorentz force. 3. Bad CCG on cavity 2.
SNS-CMM-TEST | 1. Cavity 2 HOM port 2(FPC side) does not meet spec(>3E10).2. Cavity 3 HOM port 2(FPC side) does not meet spec(>3E10).3. Stepper motors for mech. tuners were replaced after testing wass completed.
SNS-CMM-TEST | 1. TD023B diode shorted. 2. Piezo Cavity 3 short to ground. 3. HOM2 port open connection internally. 4. Insulating vacuum leak. 5. Low Pwr measurement of QextFPC for Cav 2 above spec although high pwr meas good.
SNS-CMM-TEST | 1. Mech Tuner on Cav 3 malfunctioned due to broken piezo tuner casing. 2. Low pwr measurement of Qext FPC on all three cavities was above spec.3. Measurements on Cavity 3 were performed at 805.7 MHz due to tuner problem.
SNS-CMM-TEST
SNS-CMM-TEST | No RF testing performed on M07. First 1st Cooldown aborted due to failure of feedthru on the high pressure side of the heat exchanger. The second cooldown was aborted when the feedthru on the low pressure inlet side of the heat exchanger failed.
SNS-CMM-TEST | Testing at 2K of cryomodule not performed.
SNS-CMM-TEST | Testing at 2K of cryomodule not performed.
SNS-CMM-TEST
SNS-CMM-TEST | 1. M11-2 HOM2 probe damaged.2. M11-2 low Emax (8.6 MV/m). Unable to process due to HOM probe damage.3. M11-2 Qext fld probe above spec by factor of 3.4. Piezos wiring appears to be reversed. Tests not completed. 5.Diode TD321 does not read.
SNS-INSR
SNS-INSR | See Inspection Summary Report found under SNS Seq.#49 for data relative to Window Assembly "B".
SNS-INSR | See Inspection Summary Report ( Seq.# 50) for details.
SNS-INSR
SNS-INSR
SNS-INSR
SNS-INSR
SNS-NCR
SNS-NCR
SNS-NCR
SNS-NCR
-- | Cryomodule End cans No relief valves installed on Primary and Shield supply. The valves are on order. No J-T actuators are installed. J-T actuators are being reworked at this time. Tuner Stepper motors on all tuners were changed to rew
-- | Cryomodule M-10 not tested at JLab per agreement between JLab and SNS. Therefore traveler SNS-CMM-TEST not completed for this cryomodule.
-- | Testing at 2K of cryomodule not performed.

## NCR Counts
Row Labels | Count of TravelerId/Part Info
-- | 3
Coupler modified conflat gasket | 1
Coupler outer conductor | 2
Coupler outer conductors | 2
CRM9005020-1001 | 1
CRM9005020-1003 | 1
FPC 6.75 | 1
FPC Bellows Assy. | 10
FPC Doorknob Assy. | 4
H-3 | 2
HOM Probe Tip | 1
HVA warm bl valve | 1
MB cavity | 3
MB- Helium vessel | 1
Med. Beta Inner Magnetic Shield | 4
Med. Beta Magnetic Shield | 1
Med. Beta Outer Magnetic Shield | 6
Medium Beta cavity | 1
SNS Cavity (MB-04) | 1
SNS FPC Outer Conductor | 1
SNS FPC Window | 11
SNS High Beta Inner Magnetic Shield | 3
SNS High Beta Outer Magnetic Shield | 3
SNS MB Vacuum Vessel | 2
SNS MB-08 Cavity | 1
SNS Outer Conductor | 2
SNS RETURN END CAN | 1
SNS Supply end can | 1
SNS-CM-CRY-RENC-INSP | 28
SNS-CM-CRY-SENC-INSP | 29
SNS-CM-CST-FLNG-INSP | 2
SNS-CM-CST-FPC-DKNB | 58
SNS-CM-CST-FPC-INNX | 82
SNS-CM-CST-FPC-OUTC | 14
SNS-CM-CST-FPC-OUTX | 45
SNS-CM-CST-FPC-WGCV | 71
SNS-CM-CST-FPC-WGD | 86
SNS-CMH-CRY-IMAG-INSP | 7
SNS-CMH-CRY-OMAG-INSP | 8
SNS-CMH-CRY-SFR-INSP | 4
SNS-CMH-CRY-THRM-INSP | 2
SNS-CMH-CRY-VAC-INSP | 2
SNS-CMH-CST-CAV-CMM | 15
SNS-CMH-CST-CAV-INSP | 4
SNS-CMH-CST-CAV-VTRF | 1
SNS-CMH-CST-FPC-BRTL | 1
SNS-CMH-CST-FPC-BRTR | 5
SNS-CMH-CST-FPC-BRTV | 5
SNS-CMH-CST-FPC-DKNB | 5
SNS-CMH-CST-FPC-INNX | 8
SNS-CMH-CST-FPC-OUTC | 118
SNS-CMH-CST-FPC-OUTX | 6
SNS-CMH-CST-FPC-WGCV | 5
SNS-CMH-CST-FPC-WGD | 10
SNS-CMH-CST-FPC-WIND | 41
SNS-CMH-CST-HELV-INSP | 5
SNS-CMH-FPC-WIND | 1
SNS-CMH-TEST | 2
SNS-CMM-CRY-IMAG-INSP | 2
SNS-CMM-CRY-SFR-INSP | 7
SNS-CMM-CRY-SHP-PKG | 1
SNS-CMM-CRY-THRM-INSP | 3
SNS-CMM-CRY-VAC-INSP | 7
SNS-CMM-CST-BVLV-INSP | 1
SNS-CMM-CST-CAV-BELL | 40
SNS-CMM-CST-CAV-CMM | 20
SNS-CMM-CST-CAV-HPTI | 12
SNS-CMM-CST-CAV-INSP | 11
SNS-CMM-CST-CAV-VTRF | 1
SNS-CMM-CST-FPC-EPRB | 24
SNS-CMM-CST-FPC-MODG | 12
SNS-CMM-CST-FPC-VGIN | 5
SNS-CMM-CST-FPC-WIND | 40
SNS-CMM-CST-HELV-INSP | 4
SNS-CMM-DIAG-FTF-INSP | 11
SNS-CMM-TEST | 11
SNS-Cryomodule Saddle | 1
SNS-INSR | 7
SNS-MB cavity | 1
SNS-MB Prototype cavity | 3
SNS-NCR | 4
Vacuum Vessel Tophat Assy. | 1
Vacuum Vessel Tophat Assy. # 005 | 1
Vacuum Vessel Tophjat Assy. | 1
Grand Total | 972

## D3
TravelerId | Description
SNS-CPT-ASSY | HPR ran only 2 of the 3 passes on the first HPR run Second Hpr run repeated the problem We aborted the second assembly and will repeat the second HPR run with 3 passes as originally intended