## TIMELINE
Task Name | Start | UPDATED RECEIVING SCHEDULE?? 27-Aug-19 |  |  | ORIGINAL SCHEDULE
SNS PPU Overview from 10JUN2019 | Tue 7/23/19 | PART | RECEIVE | CM | ASSEMBLIES | START | FINISH
Procurement (RECV PARTS) | 2020-01-08 | Flange NW250 + feedthrough flange weld | 2020-01-08 | CM-00 | ALL CAVITIES QUALIFIED | 2020-08-01 | 2022-01-31
Cavity Qualification | 2020-03-17 | FLANGE NW250 + FEEDTHRU FLANGE WELD | 2020-01-08 | CM-01 | CM-01 Cavity String Assembly | 2021-02-11 | 2021-04-08
Cavity String Assembly | 2020-08-18 | SURGE TANK | 2020-01-08 | CM-01 | CM-01 COLD MASS ASSEMBLY | 2021-04-08 | 2021-06-11
Cold Mass Assembly | 2020-09-30 | WARM TO COOL ASSY (SUPPLY END) | 2020-01-08 | CM-02 | CM-02 Cavity String Assembly | 2021-05-06 | 2021-06-25
Space Frame Assembly | 2020-11-23 | TOPHATS | 2020-02-06 | CM-01 | CM-01 SPACEFRAME THERMAL SHIELD | 2021-06-11 | 2021-08-30
Final Assembly | 2021-02-18 | SHIPPING TESTS | 2020-02-14 | CM-02 | CM-02 COLD MASS ASSEMBLY | 2021-06-25 | 2021-08-30
Cold Shock Test | 2021-05-01 | FLANGE BLANK ASSY | 2020-02-21 | CM-03 | CM-03 Cavity String Assembly | 2021-07-12 | 2021-08-30
Shipping Preparation | 2021-06-01 | FPCs | 2020-02-21 | CM-01 | CM-01 Final Assembly | 2021-08-30 | 2021-11-02
Cryomodule Shipping | 2021-06-09 | HELV | 2020-03-03 | CM-02 | CM-02 SPACEFRAME THERMAL SHIELD | 2021-08-30 | 2021-11-09
|  | LARGE FPC/TOPHAT BELLOWS | 2020-03-05 | CM-03 | CM-03 COLD MASS ASSEMBLY | 2021-08-30 | 2021-10-26
|  | TUNER | 2020-03-11 | CM-04 | CM-04 Cavity String Assembly | 2021-09-07 | 2021-10-26
|  | CAVs | 2020-03-17 | CM-04 | CM-04 COLD MASS ASSEMBLY | 2021-10-26 | 2021-12-23
|  | WARM TO COOL BELLOWS | 2020-04-02 | CM-05 | CM-05 Cavity String Assembly | 2021-10-26 | 2021-12-09
Need confirmation on schedule of parts arriving and start of assemblies |  | WARM TO COOL SPOOL ASSY | 2020-04-02 | CM-01 | CM-01 COLD SHOCK TESTING | 2021-11-02 | 2021-11-23
|  | GATE VALVE MDC 303006-133 | 2020-04-30 | CM-02 | CM-02 Final Assembly | 2021-11-09 | 2022-01-24
|  | HELIUM OUTLET BELLOWS | 2020-04-30 | CM-03 | CM-03 SPACEFRAME THERMAL SHIELD | 2021-11-09 | 2022-01-24
|  | VAT RIGHT ANGLE VALBE (SUPPLY END) | 2020-04-30 | CM-06 | CM-06 Cavity String Assembly | 2021-12-09 | 2022-01-31
|  | GATE VALVE MDC 302004 | 2020-05-14 | CM-01 | CM-01 SHIPPING | 2021-12-23 | 2022-01-14
|  | SOFT SHUT VALVES | 2020-05-14 | CM-05 | CM-05 COLD MASS ASSEMBLY | 2021-12-23 | 2022-02-28
|  | SPACEFRAME | 2020-05-29 | CM-02 | CM-02 COLD SHOCK TESTING | 2022-01-24 | 2022-02-04
|  | BELLOWS | 2020-06-26 | CM-03 | CM-03 Final Assembly | 2022-01-24 | 2022-03-21
|  | INSTRUMENTATION | 2020-06-26 | CM-04 | CM-04 SPACEFRAME THERMAL SHIELD | 2022-01-24 | 2022-03-28
|  | MAG SHIELDING | 2020-06-26 | CM-07 | CM-07 Cavity String Assembly | 2022-01-31 | 2022-03-14
|  | SENC | 2020-07-27 | CM-06 | CM-06 COLD MASS ASSEMBLY | 2022-02-28 | 2022-04-25
|  | VV | 2020-08-10 | CM-02 | CM-02 SHIPPING | 2022-03-14 | 2022-03-28
|  | CST ASSY | 2020-08-18 | CM-03 | CM-03 COLD SHOCK TESTING | 2022-03-21 | 2022-04-11
|  | THERMAL SHIELD | 2020-09-14 | CM-04 | CM-04 Final Assembly | 2022-03-28 | 2022-05-23
|  | COLD MASS ASSY | 2020-09-30 | CM-05 | CM-05 SPACEFRAME THERMAL SHIELD | 2022-03-28 | 2022-05-31
|  | SPACEFRAME THERMAL SHIELD ASSY | 2020-11-23 | CM-07 | CM-07 COLD MASS ASSEMBLY | 2022-04-25 | 2022-06-21
|  | RENC | 2020-12-04 | CM-03 | CM-03 SHIPPING | 2022-05-09 | 2022-05-23
|  | CM FINAL ASSY | 2021-02-18 | CM-04 | CM-04 COLD SHOCK TESTING | 2022-05-23 | 2022-06-14
|  | SHIP CM01 | 2021-06-09 | CM-05 | CM-05 Final Assembly | 2022-05-31 | 2022-07-27
|  |  |  | CM-06 | CM-06 SPACEFRAME THERMAL SHIELD | 2022-05-31 | 2022-08-03
|  |  |  | CM-04 | CM-04 SHIPPING | 2022-07-13 | 2022-07-27
|  |  |  | CM-05 | CM-05 COLD SHOCK TESTING | 2022-07-27 | 2022-08-17
|  |  |  | CM-06 | CM-06 Final Assembly | 2022-08-03 | 2022-09-29
|  |  |  | CM-07 | CM-07 SPACEFRAME THERMAL SHIELD | 2022-08-03 | 2022-10-06
|  |  |  | CM-05 | CM-05 SHIPPING | 2022-09-15 | 2022-09-29
|  |  |  | CM-06 | CM-06 COLD SHOCK TESTING | 2022-09-29 | 2022-10-20
|  |  |  | CM-07 | CM-07 Final Assembly | 2022-10-06 | 2022-12-05
|  |  |  | CM-06 | CM-06 SHIPPING | 2022-11-17 | 2022-12-05
|  |  |  | CM-07 | CM-07 COLD SHOCK TESTING | 2022-12-05 | 2023-01-04
|  |  |  | CM-07 | CM-07 SHIPPING | 2023-02-02 | 2023-02-16

## PROCUREMENT
| Procurement Requirement | Subcontracting Officer | SOTR/ Engineer | Contract Award date (SOW and requirements defined, so Traveler can be started ) | Expected delivery date
1 | Helium Vessel | Tom Huratiak | Katherine Wilson | 2019-07-23 | 2020-06-02
2 | Tuner Motors (Stepper) | Ted Peshehonoff | Naeem Huque | 2019-09-03 | 2020-05-06
2a | Tuner Harmonic Drives | Ted Peshehonoff | Naeem Huque | 2019-09-03 | 2020-05-06
2b | Tuner Frames | Ted Peshehonoff | Naeem Huque | 2019-09-03 | 2020-06-15
3 | Thermal Shield | Tom Huratiak | M. Marchlik | 2019-09-03 | 2020-10-13
4 | MLI | Tom Huratiak | M. Marchlik | 2019-09-03 | 2020-10-13
5 | Spaceframe | DeAnn Maddox | M. Marchlik | 2019-09-03 | 2020-08-10
6 | Vacuum Vessel | Ted Peshehonoff | M. Marchlik | 2019-09-03 | 2021-01-11
7 | Supply End Can | Melissa Torres | G. Cheng | 2019-09-03 | 2020-12-03
8 | Return End Can | Melissa Torres | G. Cheng | 2019-02-27 | 2020-12-21
9 | Return End Can Heat Exchangers | Melissa Torres | G. Cheng | 2019-09-16 | 2020-04-30
10 | Instrumentation | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-05-01
10a | Instrumentation - Cernox Diodes | Melissa Torres | Peter Owen | 2019-09-03 | 2020-05-01
10b | Instrumentation - Heater | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-05-01
10c | Instrumentation - Liquid Level Probe | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-05-01
10d | Instrumentation - Field Probe Cable | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-05-01
10e | Instrumentation - Pressure Gages | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-05-01
10f | Instrumentation - Helium Feedthrough | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-05-01
10g | Instrumentation - Vacuum Feedthroughs | DeAnn Maddox | Peter Owen | 2019-09-03 | 2020-01-23
12 | Magnetic Shielding | DeAnn Maddox | G. Cheng | 2019-09-03 | 2020-06-30
13 | Cleanroom String Assembly (Beamline Bellows) | Ted Peshehonoff | Katherine Wilson | 2019-09-03 | 2020-04-17
13a | Cleanroom String Assembly (Gate Valves) | DeAnn Maddox | Katherine Wilson | 2019-09-03 | 2020-05-15
13b | Cleanroom String Assembly (Warm to Cold Spool Assemblies) | Ted Peshehonoff | Katherine Wilson | 2019-09-03 | 2020-04-17
13c | Cleanroom String Assembly (VAT Right Angle Valves) | DeAnn Maddox | Katherine Wilson | 2019-09-03 | 2020-05-15
13d | Cleanroom String Assembly (Titan Pump) | DeAnn Maddox | Katherine Wilson | 2019-09-03 | 2020-01-16
13e | Cleanroom String Assembly (Soft Shut Valve) | Tom Huratiak | Katherine Wilson | 2019-09-03 | 2020-06-15
14 | Cold Mass Assembly (Helium Outlet Bellows) | DeAnn Maddox | Katherine Wilson | 2019-09-03 | 2020-05-15
14a | Cold Mass Assembly (Large FPC/Tophat Bellows) | DeAnn Maddox | Matt Marchlik | 2019-09-03 | 2020-05-15
15 | Final Cryomodule Assembly (Gate Valve VAT) | Tom Huratiak | Katherine Wilson | 2019-09-03 | 2020-02-26
15a | Final Cryomodule Assembly (Flange Blank Assembly) | Tom Huratiak | Matt Marchlik | 2019-09-03 | 2020-01-23
15b | Final Cryomodule Assembly (Surge Tank) | DeAnn Maddox | Naeem Huque | 2019-09-03 | 2020-01-23
15c | Final Cryomodule Assembly (Flange NW 250 Feedthrough) | Tom Huratiak | Matt Marchlik | 2019-09-03 | 2020-01-23
15d | Final Cryomodule Assembly (Pressure Relief Plates and Rupture Disks) | Tom Huratiak | Matt Marchlik | 2020-09-03 | 2020-01-23
15e | Final Cryomodule Assembly (Tophats) | Tom Huratiak | Matt Marchlik | 2019-09-03 | 2020-02-20

## PARTS
order | Pansophy Acronym | Part | Drawing Number(s) | SOTR/ENGR | BACKUP ENGR | RECV (VEND DOCS/VISUAL) | INSP (VISUAL/CMM) | PROC (CHEM/BAKE) | ASSY | TEST (LEAK/VTA) | PART SERIALIZATION
47 | FPCWSN | AIR SIDE ASSEMBLY | 104210500-M8U-8200-A00X | WISEMAN |  |  | VISUAL
14 | CAVSN | CAVITY | 104211800-M8U-8200-A00X | KW(ORNL) |  |  | VISUAL / HOM DEPTH / CMM | BCP / USC / HEAT / HPR | ASSY? HELV? | TUNE / VTA
16 |  | CAVITY STRING ASSEMBLY "PARTS" | 104211500-M8U-8200-A00X | KWILSON
36 | VARIES | CERNOX DIODES | 104212000-M8U-8200-A00X | POWEN
18 | CSTSN | CLEAN ROOM ASSEMBLY |  | KWILSON |  |  |  | CLN
26 |  | CRYOMODULE ASSY FLANGE BLANK | 104210200-M8U-8200-A00X | MARCHLIK |  |  | VISUAL
27 |  | CRYOMODULE ASSY FLANGE NW 250 FEEDTHROUGH | 104210200-M8U-8200-A00X | MARCHLIK |  |  | VISUAL
25 | VARIES | CRYOMODULE ASSY GATE VALVE MDC |  | KWILSON
28 | PBDSN | CRYOMODULE ASSY RUPTURE DISKS | 104210200-M8U-8200-A00X | MARCHLIK
9 |  | CRYOMODULE ASSY SURGE TANK |  | HUQUE
29 | VARIES | CRYOMODULE ASSY TOPHATS | 104210200-M8U-8200-A00X | MARCHLIK
11 |  | CRYOMODULE STAND | 104210400-M8U-8200-A00X | MACHA
45 |  | CRYOMODULE TOP LEVEL ASSEMBLY | 104210200-M8U-8200-A00X | WISEMAN
46 |  | CRYOMODULE WARM TO COLD | 104210300-M8U-8200-A00X | WISEMAN |  | The bellows from the cold valve to the flat head and also the pump drop on the other side of the flat head
19 | AMGVSN | CST ASSY GATE VALVES |  | KWILSON
39 | VARIES | FIELD PROBE CABLE | 104212000-M8U-8200-A00X | POWEN
13 | FPCSN | FUNDAMENTAL POWER COUPLER | 104211600-M8U-8200-A00X | KW(ORNL) |  |  | VISUAL | BAKE | HPRF
37 | VARIES | HEATER | 104212000-M8U-8200-A00X | POWEN
41 | VARIES | HELIUM FEEDTHROUGHS | 104212000-M8U-8200-A00X | POWEN
23 |  | HELIUM OUTLET BELLOWS |  | KWILSON
17 | HELVSN | HELIUM VESSEL | 104211700-M8U-8200-A026 | KWILSON |  | 1. With delivery of parts, certified mill test reports for all material used, including weld filler, tracked to the parts by serial number 2. With delivery of parts, copy of the weld inspection 3. With delivery of parts, copies of the results of the cold shock, leak check, and radiographic examination All documents should be provided electronically | VISUAL |  | ASSY |  | The subcontractor shall mark each of the three subassemblies of 104211700-M8U-8200-A026 (i.e., -A020, -A023, and –A025) with serial numbers. Serial numbers shall be in the form: 104211700-A02x-R-SSS
5 | IMAGSN | INNER MAGNETIC SHIELD | 104211200-M8U-8200-A00X | CHENG |  |  | VISUAL
44 |  | INSTALLATION ASSEMBLY | 104210100-M8U-8200-A00X | WISEMAN
35 | VARIES | INSTRUMENTATION | 104212000-M8U-8200-A00X | POWEN |  |  |  | CALIBRATION?
42 |  | INSULATING VACUUM | 104212100-M8U-8200-A00X | SNS |  | New insulating vacuum system in the LINAC and is in SNS’s scope
24 |  | LARGE FPC / TOPHAT BELLOWS |  | KWILSON
38 | HLSSN | LIQUID LEVEL PROBE | 104212000-M8U-8200-A00X | POWEN
33 |  | MLI | 104211300-M8U-8200-A00X | MARCHLIK
4 | OMAGSN | OUTER MAGNETIC SHIELD | 104211000-M8U-8200-A00X | CHENG |  |  | VISUAL
40 | VARIES | PRESSURE GAGES | 104212000-M8U-8200-A00X | POWEN
43 |  | REFERENCE MODEL | 104212200-M8U-8200-A00X | SNS |  | Reference model is what was sent in the dropbox and any new drawing that was created for reference
1 |  | RENC HEAT EXCHANGERS | 104100000-M8U-8200-A059 | CHENG |  | Certified mill test reports (CMTR) of all raw materials used to fabricate deliverables shall be provided Copies of all inspection and test reports shall be provided |  |  |  |  | Heat exchangers shall be serialized and the serial numbers (SN) shall be used on all related vendor documents. This identification-marking scheme shall be submitted to JLAB prior to contract award for approval
3 | RECSN | RETURN END CAN | 104210700-M8U-8200-A00X | CHENG |  |  | VISUAL / MEASURE |  |  | LEAK
22 |  | SOFT SHUT VALVE |  | KWILSON
31 | SFRSN | SPACEFRAME | 104210900-M8U-8200-A001 | MARCHLIK |  | Certified mill test reports (CMTR) of all raw materials used to fabricate deliverables shall be provided Deliverable Documentation shall be in electronic format | VISUAL / DIMENSIONAL |  |  |  | Where possible, each component of the Space Frame Assembly shall be marked according to format: 10421XXXX-AYYY-R-SSS
2 | SECSN | SUPPLY END CAN | 104210600-M8U-8200-A00X | CHENG |  |  | VISUAL / MEASURE |  |  | LEAK
32 | THRMSN | THERMAL SHIELD / RENC THERMAL SHIELD / SENC THERMAL SHIELD | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 | MARCHLIK |  | VERIFY PACKING LIST / CMTR's | VISUAL / CMM |  |  |  | Where possible, each component of the Space Frame Assembly shall be marked according to format: 10421XXXX-AYYY-R-SSS
21 | VARIES | TITAN PUMP |  | KWILSON
12 |  | TOOLING | 104211900-M8U-8200-A00X | MACHA
6 | TUNWSN or TUNCSN | TUNER ASSY | 104211400-M8U-8200-A001 | HUQUE |  | Electronic copies of all Quality Assurance and Quality Control data sheets as specified herein (including but not limited to Certificates of Conformance, material certifications, and NCRs) shall be provided |  |  |  |  | Subcontractor shall inscribe the top assembly with the serial number (in the location specified on 104211400-M8U-8200-A001) in the form: 104211400-A001-R-SSS
10 | VARIES | TUNER FRAMES |  | HUQUE
7 | HMDRSN | TUNER HARMONIC DRIVES | 104211400-M8U-8200-A056 | HUQUE
8 | SMSN | TUNER MOTORS | CRM 900-7030-0047 RevA | HUQUE | [6 empty] | Subcontractor shall inscribe parts with identifiable and traceable markings. These are to be recorded by the manufacturer. Sufficient information shall be recorded in order to trace materials, processes and any possible lower-tier subcontractor work
34 | VARIES | VACUUM FEEDTHROUGHS | 104212000-M8U-8200-A00X | POWEN
30 | VVSN | VACUUM VESSEL | 104210800-M8U-8200-A001 | MARCHLIK |  | Certified mill test reports (CMTR) of all raw materials used to fabricate deliverables shall be provided | VISUAL
20 | AV15SN | VAT RIGHT ANGLE VALVES |  | KWILSON
15 | RTBPSN SUBPSN | WARM TO COLD SPOOL ASSY | 104210300-M8U-8200-A00X | KWILSON |  | The bellows from the cold valve to the flat head and also the pump drop on the other side of the flat head

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
ALUMINUM CLEANING PROCEDURE (for vendor) | 11141S0028 Rev B | B | ASHLEYA |  |  | 2019-08-08 |  | M:SNS_PPU/Procurement/Specs/11141S0028 Aluminum Cleaning and Handling Rev B.pdf
STAINLESS STEEL CLEANING PROCEDURE (for vendor) | 11141S0034 | - | ASHLEYA |  |  | 2019-07-26 |  | M:SNS_PPU/Procurement/Specs/11141S0034 Stainless Steel Cleaning REV.pdf
TITANIUM CLEANING PROCEDURE (for vendor) | 11520S0100 | - | ASHLEYA |  |  | 2019-08-07 |  | M:SNS_PPU/Procurement/Specs/11520S0100 Titaniumn Cleaning REV A.pdf
Acid Etching at the Chemical Fume Hood Procedure | CP-STP-CAV-CHEM-ACID
Degreasing Procedure | CP-STP-CAV-CHEM-DEGR
Standard Cavity Seal Surface Repair | CP-STP-CAV-CHEM-FLNG
EP Procedure? | CP-STP-CAV-CHEM-HEP
Standard Manual UltrasonicWall Thickness Measurement Procedure | CP-STP-CHEM-THKN
Standard Cavity Degreasing Procedure | CP-STP-CAV-CHEM-USC
Cavity Procedures
HIGH SENSITIVITY VACUUM LEAK | 11141S0029 Rev B | B | MACHA | WISEMAN | EDALY | 2019-06-30 |  | M:SNS_PPU/Procurement/Specs/11141S0029 2e-10 Leak Check Final.pdf
STANDARD VACUUM LEAK CHECK REQUIREMENTS | 11141S0033 Rev B | B | MACHA | WISEMAN |  | 2019-08-09 |  | M:SNS_PPU/Procurement/Specs/11141S0033 1e9 Leak Check Final.pdf
SNSPPU Coupler Installation onto the Cavity | CP-SNSPPU-CAV-INST-FPC |  | Macha
String Production Procedures
SNSPPU Cavity String Tooling Preparation | CP-SNSPPU-CST-INST-TOOL |  | Macha
Cryomodule Production Procedures
SNSPPU End Can Installation | CP-SNSPPU-CM-INST-TOOL-ENDC |  | Macha
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Cavity
Cavity
Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV
Cavity Incoming RF Inspection | SNSPPU-CAV-RFIN
Cavity Assembly to Test Stand | SNSPPU-CAV-ASSY-TSTD
Cavity Baking at 125℃ | SNSPPU-CAV-CHEM-BAKE
Cavity Vertical RF Testing | SNSPPU-CAV-VTRF
Cavity RF Tuning (if necessary) | SNSPPU-CAV-TUNE
Helium Vessel
Helium Vessel Shell Inspection | SNSPPU-CAV-INSP-HES
Helium Vessel Probe End Inspection | SNSPPU-CAV-INSP-HEHDP
Helium Vessel FPC End Inspection | SNSPPU-CAV-INSP-HEHDF
Helium Vessel Liquid Level Probe Visual Inspection | SNSPPU-CAV-INSP-HLS
Helium Vessel Assembly | SNSPPU-CAV-ASSY-HELV
Dressed Cavity
Dressed Cavity Leak Check | SNSPPU-CAV-LEAK
Dressed Cavity Cleaning | SNSPPU-CAV-CHEM-CLN
Dressed Cavity Slow Bleed Up | Procedure vs Traveler??
Dressed Cavity HPR | SNSPPU-CAV-CHEM-HPR
FPC
FPC Visual Inspection | SNSPPU-CAV-INSP-FPC
FPC Leak Test | SNSPPU-CAV-LEAK-FPC
FPC Cleaning | SNSPPU-CAV-CHEM-CLN-FPC
Cavity String
Beamline Bellows Visual Inspection | SNSPPU-CST-INSP-BLBP
Supply Warm to Cold Bellows Visual Inspection | SNSPPU-CST-INSP-
Return Warm to Cold Bellows Visual Inspection | SNSPPU-CST-INSP
Cold Vat Valves Visual Inspection | SNSPPU-CST-INSP
Right Angle Valves Visual Inspection | SNSPPU-CST-INSP
Cavity String Assembly | SNSPPU-CST-ASSY
Cryomodule
Cold Mass
Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG
Tuner Assembly Visual & CMM Inspection | SNSPPU-CM-INSP-
Tuner Harmonic Drives Batch Inspection | SNSPPU-CM-INSP
Tuner Motor Batch Inspection | SNSPPU-CM-INSP
Helium Outlet Bellows & Con Bellows Inspection | SNSPPU-CM-INSP
Equalizer Flex Hose Inspection | SNSPPU-CM-INSP
Cold Mass Misc. Components Inspection | SNSPPU-CM-INSP
Cold Mass Misc. Components Leak Test | SNSPPU-CM-LEAK
8 Pin Helium Feedthru Visual Inspection | SNSPPU-CM-INSP
8 Pin Helium Feedthru Leak Test | SNSPPU-CM-LEAK
8 Pin Helium Feedthru Cryo Cycle/Coldshock Test | SNSPPU-CM
RF Cable for FP Visual Inspection | SNSPPU-CM-INSP
RF Cable for FP Cryo Cycle/Coldshock Test | SNSPPU-CM
Cold Mass Assembly | SNSPPU-CM-ASSY-CMASS
Space Frame and Shielding
Space Frame Inspection | SNSPPU-CM-INSP-SFR
Thermal Shield Inspection (This has the thermal shield, RENC thermal shield, and senc thermal shield. Will these be received and inspected separately? Do they have different SNs) | SNSPPU-CM-INSP-THRM
Outer Magnetic Shield Visual Inspecton | SNSPPU-CM-INSP-OMAG
MLI Installation
Space Frame and Thermal Shield Assembly | SNSPPU-CM-ASSY
Vacuum Vessel
Vacuum Vessel Inspection | SNSPPU-CM-INSP-VV
Supply End Can Inspection | SNSPPU-CM-INSP-SENC
Supply End Can Leak Test | SNSPPU-CM-LEAK-SENC
Return End Can Inspection | SNSPPU-CM-INSP-RENC
Return End Can Leak Test | SNSPPU-CM-LEAK-RENC
Tophat Inspection | SNSPPU-CM-INSP-TPHT
Tophat Leak Test | SNSPPU-CM-LEAK-TPHT
Parallel Plate Relief Valves Inspection | SNSPPU-CM-INSP
JT Valve Inspection | SNSPPU-CM-INSP-JTV
JT Valve Actuator Inspection | SNSPPU-CM-INSP-JTVA
Return End Can Heat Exchangers Inpsection | SNSPPU-CM-INSP
Return End Can Parallel Plate Relief Valves Inpsection | SNSPPU-CM-INsP
Vacuum Vessel End Plates Inspection | SNSPPU-CM-INSP
Vacuum Vessel Assembly | SNSPPU-CM-ASSY-VV
Cryomodule
Phase 1 Cryomodule Assembly | SNSPPU-CM-ASSY-FRST
Phase 2 Cryomodule Assembly | SNSPPU-CM-ASSY-SCND
Final Cryomodule Assembly | SNSPPU-CM-ASSY-FNAL
Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3
Inspection Summary Report | SNSPPU-INSR
Inspection Nonconformance Report | SNSPPU-NCR

## INVENTORY TRAVELERS
| Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes
_ | Cavity Inventory | SNSPPU-INV-CAV |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-01-30 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
_ | Helium Vessel Shell Inventory | SNSPPU-INV-HES |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-02-12 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
_ | Helium Vessel Probe End Inventory | SNSPPU-INV-HEHDP |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-02-12 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
_ | Helium Vessel FPC End Inventory | SNSPPU-INV-HEHDF |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-02-12 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
_ | Helium Vessel Liquid Level Probe Inventory | SNSPPU-INV-HLS |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-02-12 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
_ | FPC Inventory | SNSPPU-INV-FPC |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-02-04 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
_ | Beamline Bellows Inventory | SNSPPU-INV-BLBP |  |  | M. Dickey | C. Barnes | E. Daly | K. Wilson | 2020-02-05 | edaly,kwilson,areilly | kwilson | edaly,areilly,mdickey
| Supply Warm to Cold Bellows Inventory | SNSPPU-INV | Beam tube? |  | M. Dickey | C. Barnes | E. Daly | K. Wilson
| Return Warm to Cold Bellows Inventory | SNSPPU-INV | Beam tube? |  | M. Dickey | C. Barnes | E. Daly | K. Wilson
| Cold Vat Valves Inventory | SNSPPU-INV | All Metal Gate Valve? |  | M. Dickey | C. Barnes | E. Daly
| Right Angle Valves Inventory | SNSPPU-INV | 1.5" RAV? |  | M. Dickey | C. Barnes | E. Daly
| Ion Pump Inventory | SNSPPU-INV | Depends on pump type |  | M. Dickey | C. Barnes | E. Daly
| Ion Pump Tee Inventory | SNSPPU-INV | Is this just a tee? |  | M. Dickey | C. Barnes | E. Daly
| Cavity String Hardware Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
_ | Inner Magnetic Shield Inventory | SNSPPU-INV-IMAG |  |  | M. Dickey | C. Barnes | E. Daly | G. Cheng | 2020-02-05 | edaly,cheng,areilly | cheng | edaly,areilly,mdickey
| Tuner Assembly Inventory | SNSPPU-INV-TUN? | Warm or Cold? |  | M. Dickey | C. Barnes | E. Daly | N. Huque |  | edaly,huque,areilly | huque | edaly,areilly,mdickey
_ | Tuner Harmonic Drives Inventory | SNSPPU-INV-HMDR |  |  | M. Dickey | C. Barnes | E. Daly | N. Huque | 2020-02-17 | edaly,huque,areilly | huque | edaly,areilly,mdickey
| Tuner Motors Inventory | SNSPPU-INV-SM |  |  | M. Dickey | C. Barnes | E. Daly | N. Huque |  | edaly,huque,areilly | huque | edaly,areilly,mdickey
| MLI Inventory | SNSPPU-INV-MLI |  |  | M. Dickey | C. Barnes | E. Daly | M. Marchlik |  | edaly,marchlik,areilly | marchlik | edaly,areilly,mdickey
| Helium Outlet Bellows & Con Bellows Inventory | SNSPPU-INV | What is this? |  | M. Dickey | C. Barnes | E. Daly
| Equalizer Flex Hose Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
| Cold Mass Misc. Components Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
| Cold Mass Hardware Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
_ | Cernox Diode Inventory | SNSPPU-INV-DCXCU |  |  | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 | edaly,kwilson,areilly | powen,king | edaly,areilly,mdickey
_ | 8 Pin Helium Feedthru Inventory | SNSPPU-INV-FT08 |  |  | M. Dickey | C. Barnes | E. Daly
| RF Cable for Field Probe Inventory | SNSPPU-INV | Depends on cable type |  | M. Dickey | C. Barnes | E. Daly
| 8 Pin Heater Wire Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
_ | Space Frame Inventory | SNSPPU-INV-SFR |  |  | M. Dickey | C. Barnes | E. Daly | M. Marchlik | 2020-02-04 | edaly,marchlik,areilly | marchlik | edaly,areilly,mdickey
_ | Thermal Shield Inventory (3 pieces?) | SNSPPU-INV-THRM |  |  | M. Dickey | C. Barnes | E. Daly | M. Marchlik | 2020-02-12 | edaly,marchlik,areilly | marchlik | edaly,areilly,mdickey
_ | Outer Magnetic Shield Inventory | SNSPPU-INV-OMAG |  |  | M. Dickey | C. Barnes | E. Daly | G. Cheng | 2020-02-05 | edaly,cheng,areilly | cheng | edaly,areilly,mdickey
_ | Vacuum Vessel Inventory | SNSPPU-INV-VV |  |  | M. Dickey | C. Barnes | E. Daly | M. Marchlik | 2020-02-05 | edaly,marchlik,areilly | marchlik | edaly,areilly,mdickey
_ | Supply End Can Inventory | SNSPPU-INV-SENC |  |  | M. Dickey | C. Barnes | E. Daly | G. Cheng | 2020-02-05 | edaly,cheng,areilly | cheng | edaly,areilly,mdickey
_ | Return End Can Inventory | SNSPPU-INV-RENC |  |  | M. Dickey | C. Barnes | E. Daly | G. Cheng | 2020-02-05 | edaly,cheng,areilly | cheng | edaly,areilly,mdickey
| Assembly Flange Blank Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
| Assembly Flange NW 250 Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
_ | Assembly Rupture Disks Inventory | SNSPPU-INV-PBD |  |  | M. Dickey | C. Barnes | E. Daly | M. Marchlik | 2020-02-17 | edaly,marchlik,areilly | marchlik | edaly,areilly,mdickey
_ | Assembly Tophats Inventory | SNSPPU-INV-TPHT |  |  | M. Dickey | C. Barnes | E. Daly | M. Marchlik | 2020-02-17 | edaly,marchlik,areilly | marchlik | edaly,areilly,mdickey
_ | JT Valve Inventory (CRYO build) | SNSPPU-INV-JTV |  |  | M. Dickey | C. Barnes | E. Daly | G. Cheng | 2020-02-17 | edaly,cheng,areilly | cheng | edaly,areilly,mdickey
_ | JT Valve Actuator Inventory (CRYO build) | SNSPPU-INV-JTVA |  |  | M. Dickey | C. Barnes | E. Daly | G. Cheng | 2020-02-17 | edaly,cheng,areilly | cheng | edaly,areilly,mdickey
| RENC Heat Exchangers Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
| RENC Parallel Plate Relief Valves Inventory | SNSPPU-INV | Is this serialized? |  | M. Dickey | C. Barnes | E. Daly
| Vacuum Vessel End Plates Inventory (Supply & Return) | SNSPPU-INV | What is this? |  | M. Dickey | C. Barnes | E. Daly
21
42

## TRAVELERSold
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A