## TIMELINE
Task Name | Start
P100-01 Overview |  | PART | RECEIVE | CM | ASSEMBLIES | START | FINISH
Procurement (RECV PARTS) |  | Flange NW250 + feedthrough flange weld |  | P100-01 | Cavity String Assembly
Cavity Qualification |  | FLANGE NW250 + FEEDTHRU FLANGE WELD |  | P100-01 | COLD MASS ASSEMBLY
Cavity String Assembly |  | SURGE TANK |  | P100-01 | SPACEFRAME THERMAL SHIELD
Cold Mass Assembly |  | WARM TO COOL ASSY (SUPPLY END) |  | P100-01 | Final Assembly
Space Frame Assembly |  | TOPHATS |  | P100-01 | CMTF Testing
Final Assembly |  | SHIPPING TESTS |  | P100-01 | Tunnel Installation
Cold Shock Test |  | FLANGE BLANK ASSY |  | P100-01 | Commissioning
Shipping Preparation |  | FPCs
Cryomodule Shipping |  | HELV
LARGE FPC/TOPHAT BELLOWS
TUNER
CAVs
WARM TO COOL BELLOWS
Need confirmation on schedule of parts arriving and start of assemblies |  | WARM TO COOL SPOOL ASSY
GATE VALVE MDC 303006-133
HELIUM OUTLET BELLOWS
VAT RIGHT ANGLE VALBE (SUPPLY END)
GATE VALVE MDC 302004
SOFT SHUT VALVES
SPACEFRAME
BELLOWS
INSTRUMENTATION
MAG SHIELDING
SENC
VV
CST ASSY
THERMAL SHIELD
COLD MASS ASSY
SPACEFRAME THERMAL SHIELD ASSY
RENC
CM FINAL ASSY
SHIP CM01

## PROCUREMENT
| Procurement Requirement | Subcontracting Officer | SOTR/ Engineer | Contract Award date (SOW and requirements defined, so Traveler can be started ) | Expected delivery date
1 | Helium Vessel
2 | Tuner Motors (Stepper)
2a | Tuner Harmonic Drives
2b | Tuner Frames
3 | Thermal Shield
4 | MLI
5 | Spaceframe
6 | Vacuum Vessel
7 | Supply End Can
8 | Return End Can
9 | Return End Can Heat Exchangers
10 | Instrumentation
10a | Instrumentation - Cernox Diodes
10b | Instrumentation - Heater
10c | Instrumentation - Liquid Level Probe
10d | Instrumentation - Field Probe Cable
10e | Instrumentation - Pressure Gages
10f | Instrumentation - Helium Feedthrough
10g | Instrumentation - Vacuum Feedthroughs
12 | Magnetic Shielding
13 | Cleanroom String Assembly (Beamline Bellows)
13a | Cleanroom String Assembly (Gate Valves)
13b | Cleanroom String Assembly (Warm to Cold Spool Assemblies)
13c | Cleanroom String Assembly (VAT Right Angle Valves)
13d | Cleanroom String Assembly (Titan Pump)
13e | Cleanroom String Assembly (Soft Shut Valve)
14 | Cold Mass Assembly (Helium Outlet Bellows)
14a | Cold Mass Assembly (Large FPC/Tophat Bellows)
15 | Final Cryomodule Assembly (Gate Valve VAT)
15a | Final Cryomodule Assembly (Flange Blank Assembly)
15b | Final Cryomodule Assembly (Surge Tank)
15c | Final Cryomodule Assembly (Flange NW 250 Feedthrough)
15d | Final Cryomodule Assembly (Pressure Relief Plates and Rupture Disks)
15e | Final Cryomodule Assembly (Tophats)

## PARTS
order | Pansophy Acronym | Part | Drawing Number(s) | SOTR/ENGR | BACKUP ENGR | RECV (VEND DOCS/VISUAL) | INSP (VISUAL/CMM) | PROC (CHEM/BAKE) | ASSY | TEST (LEAK/VTA) | PART SERIALIZATION
47 | FPCWSN | AIR SIDE ASSEMBLY |  |  |  |  | VISUAL
14 | CAVSN | CAVITY |  |  |  |  | VISUAL / HOM DEPTH / CMM | BCP / USC / HEAT / HPR | ASSY? HELV? | TUNE / VTA
16 |  | CAVITY STRING ASSEMBLY "PARTS"
36 | VARIES | CERNOX DIODES
18 | CSTSN | CLEAN ROOM ASSEMBLY | [5 empty] | CLN
26 |  | CRYOMODULE ASSY FLANGE BLANK |  |  |  |  | VISUAL
27 |  | CRYOMODULE ASSY FLANGE NW 250 FEEDTHROUGH |  |  |  |  | VISUAL
25 | VARIES | CRYOMODULE ASSY GATE VALVE MDC
28 | PBDSN | CRYOMODULE ASSY RUPTURE DISKS
9 |  | CRYOMODULE ASSY SURGE TANK
29 | VARIES | CRYOMODULE ASSY TOPHATS
11 |  | CRYOMODULE STAND
45 |  | CRYOMODULE TOP LEVEL ASSEMBLY
46 |  | CRYOMODULE WARM TO COLD
19 | AMGVSN | CST ASSY GATE VALVES
39 | VARIES | FIELD PROBE CABLE
13 | FPCSN | FUNDAMENTAL POWER COUPLER |  |  |  |  | VISUAL | BAKE | HPRF
37 | VARIES | HEATER
41 | VARIES | HELIUM FEEDTHROUGHS
23 |  | HELIUM OUTLET BELLOWS
17 | HELVSN | HELIUM VESSEL |  |  |  |  | VISUAL |  | ASSY
5 | IMAGSN | INNER MAGNETIC SHIELD |  |  |  |  | VISUAL
44 |  | INSTALLATION ASSEMBLY
35 | VARIES | INSTRUMENTATION | [5 empty] | CALIBRATION?
42 |  | INSULATING VACUUM
24 |  | LARGE FPC / TOPHAT BELLOWS
38 | HLSSN | LIQUID LEVEL PROBE
33 |  | MLI
4 | OMAGSN | OUTER MAGNETIC SHIELD |  |  |  |  | VISUAL
40 | VARIES | PRESSURE GAGES
43 |  | REFERENCE MODEL
1 |  | RENC HEAT EXCHANGERS
3 | RECSN | RETURN END CAN |  |  |  |  | VISUAL / MEASURE |  |  | LEAK
22 |  | SOFT SHUT VALVE
31 | SFRSN | SPACEFRAME |  |  |  |  | VISUAL / DIMENSIONAL
2 | SECSN | SUPPLY END CAN |  |  |  |  | VISUAL / MEASURE |  |  | LEAK
32 | THRMSN | THERMAL SHIELD / RENC THERMAL SHIELD / SENC THERMAL SHIELD |  |  |  |  | VISUAL / CMM
21 | VARIES | TITAN PUMP
12 |  | TOOLING
6 | TUNWSN or TUNCSN | TUNER ASSY
10 | VARIES | TUNER FRAMES
7 | HMDRSN | TUNER HARMONIC DRIVES
8 | SMSN | TUNER MOTORS
34 | VARIES | VACUUM FEEDTHROUGHS
30 | VVSN | VACUUM VESSEL |  |  |  |  | VISUAL
20 | AV15SN | VAT RIGHT ANGLE VALVES
15 | RTBPSN SUBPSN | WARM TO COLD SPOOL ASSY

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
ALUMINUM CLEANING PROCEDURE (for vendor) | 11141S0028 Rev B | B | ASHLEYA |  |  | 2019-08-08 |  | M:SNS_PPU/Procurement/Specs/11141S0028 Aluminum Cleaning and Handling Rev B.pdf
STAINLESS STEEL CLEANING PROCEDURE (for vendor) | 11141S0034 | - | ASHLEYA |  |  | 2019-07-26 |  | M:SNS_PPU/Procurement/Specs/11141S0034 Stainless Steel Cleaning REV.pdf
TITANIUM CLEANING PROCEDURE (for vendor) | 11520S0100 | - | ASHLEYA |  |  | 2019-08-07 |  | M:SNS_PPU/Procurement/Specs/11520S0100 Titaniumn Cleaning REV A.pdf
Acid Etching at the Chemical Fume Hood Procedure | CP-STP-CAV-CHEM-ACID
Degreasing Procedure | CP-STP-CAV-CHEM-DEGR
Standard Cavity Seal Surface Repair | CP-STP-CAV-CHEM-FLNG
EP Procedure? | CP-STP-CAV-CHEM-HEP
Standard Manual UltrasonicWall Thickness Measurement Procedure | CP-STP-CHEM-THKN
Standard Cavity Degreasing Procedure | CP-STP-CAV-CHEM-USC
Cavity Procedures
C100 Cavity Tophat Flange Repair | CP-C100-CAV-LAP-THAT |  | Daniels | Castagnola
C100 Cavity Flange Protection | CP-C100-CAV-PROT-FLNG |  | Macha | Castagnola
C100 Top Hat Seal Surface Repair | CP-C100-TH-REPR-FLNG |  | Daniels | Castagnola
C100 probe calibration procedure | CP-C100-CAL-PRB |  | Forehand | Marhauser
C100 Cavity Cage Bracket Alingment Procedure | CP-C100-CAV-ALGN-CAGE |  | Carpenter | Castagnola
C100 1st assembly procedure for VTA qualification | CP-C100-CAV-ASSY |  | Castagnola | Macha
C100 Final assembly procedure for VTA qualification | CP-C100-CAV-ASSY2 |  | Castagnola | Macha
C100 Cavity bake procedure | CP-C100-CAV-BAKE |  | Macha | Davis
C100 BCP procedure | CP-C100-CAV-CHEM |  | Harris | Reilly
C100 waveguide cleaning procedure | CP-C100-CAV-CLN-WGD |  | Davenport | Reilly
C100 cavity degreasing procedure | CP-C100-CAV-DEGR |  | Williams | Reilly
C100 EP procedure | CP-C100-CAV-EPOL |  | Burrill | Reilly
C100 cavity evacuation | CP-C100-CAV-EVAC |  | Castagnola | Macha
C100 cavity heat Treatment | CP-C100-CAV-HEAT |  | Forehand | Reilly
C100 HPR procedure | CP-C100-CAV-HPR |  | Tipton | Reilly
C100 cavity HOM tuning procedure | CP-C100-CAV-HTUNE |  | Forehand | Marhauser
RGA Leak Test Procedure | CP-C100-CAV-LKTS |  | Castagnola | Macha
C100 lollipop assembly and cavity alignment procedure | CP-C100-CAV-LOLI |  | Macha | Castagnola
C100 Cavity Seal surface repair | CP-C100-CAV-REPR-FLNG |  | Daniels | Castagnola
C100 Cavity Straightness Inspection Procedure | CP-C100-CAV-STRAT |  | Carpenter | Reilly
C100 cavity tuning procedure | CP-C100-CAV-TUNE |  | Forehand | Marhauser
1497 MHZ Vertizal Testing Procedure | CP-C100-CAV-VTRF |  | Grenoble | Davis
Low Power RF HOM Measurement Procedure for C100 Cavity in the VTA | CP-C100-CAV-VTRF-HOM |  | Marhauser | Wang
Low Power RF Hom Measurement Procedure for Low Loss Cavities in the VTA using Polfit Mathematica package | CP-C100-CAV-VTRF-HOM-Polfit |  | Stirbet | Wang
C100 waveguide sub-assembly | CP-C100-CAV-WAVG |  | Macha | Castagnola
Ionized Nitrogen Cleaning w/particle counter | CP-C100-CLN-IONN |  | Macha | Castagnola
C100 cover the cavity in the class 10 clean room | CP-C100-CAV-COVR |  | Macha | Castagnola
C100 cavity installation into the lift cart and rail install | CP-C100-CST-CAV-LFTC |  | Macha | Castagnola
C100 VAT valve assembly onto cavity | CP-C100-CST-CAV-VALV |  | Macha | Castagnola
C100 Waveguide assembly onto cavity | CP-C100-CST-CAV-WAVG |  | Macha | Castagnola
Cavity installation into test stand procedure | CP-CAV-INST-TSTD |  | Castagnola | Macha
Test stand Cable connection procedure | CP-CAVPR-CAV-CHK-TSTD |  | Overton | Davis
C100 Radial Wedge Clamp Installation Procedure | CP-C100-RWFC-INST |  | Smith | Castagnola
C100 Waveguide Flange surface repair | CP-C100-WG-REPR-FLNG |  | Daniels | Macha
CMM Program Writing Procedure | CP-SRF-FAC-CMM |  | Carpenter | Williams
C100 Replacing Wireless Thermocouple Data Logging Hardware | CP-C100-EP-HDWR |  | Davenport | Grenoble
Ultrasonic Cavity Wall Thickness Measurement Procedure | CP-C100-CAV-THKM |  | Stirbet | Reilly
String Production Procedures
C100 Beamline Assembly Procedure | CP-C100-CST-CAV-BLN |  | Macha | Castagnola
C100 Cavity String Component | CP-C100-CST-CLN-COMP |  | Davenport | Reilly
C100 Cavity String Tooling Cleaning | CP-C100-CST-CLN-STTL |  | Davenport | Reilly
C100 Cavity String Evacuation and Leak Test Procedure | CP-C100-CST-EVAC |  | Macha | Castagnola
C100 Ion Pump Installation and Starting Procedure | CP-C100-CST-ION |  | Macha | Castagnola
C100 Cavity String Kit List | CP-C100-CST-KIT |  | Macha | Castagnola
Cryomodule Production Procedures
C100 RF Window Welding Procedure | CP-C100-CST-WELD-WWIN |  | Worland | Bennington
C100 Helium Vessel Installation | CP-C100-CAV-INST-HELV |  | Fischer | Hogan
C100 Helium Vessel Welding | CP-C100-CST-WELD-HELV |  | Fischer | Hogan
C100 Cryomodule Alignment | CP-C100-CM-ALGN |  | Fischer | Humphry
C100 Cryomodule Beampipe Assembly/Installation | CP-C100-CM-ASSY-BPIP |  | Bigalow | Page
C100 Cold Tuner Installation Procedure | CP-C100-CM-ASSY-CTNR |  | McCrea | Fischer
C100 Cryomodule Spaceframe Assembly | CP-C100-CM-ASSY-SFR |  | Page | Fischer
C100 Cryomodule Tuner Assembly-Warm | CP-C100-CM-ASSY-TUNW (was CP-C100-CM-ASSY-WTNR) |  | Fischer | McCrea
C100 Cryomodule JT Actuator calibration | CP-C100-CM-CAL-JTAT |  | Campbell | Humphry
C100 Helium Vessel Installation Procedure | CP-C100-CM-INST-HELV |  | Fischer | McCrea
C100 Cryomodule MLI installation | CP-C100-CM-INST-MLI |  | McCrea | Campbell
C100 Cryomodule Secondary Waveguide/Sweep Installation/Removal | CP-C100-CM-INST-WGSP |  | Carpenter | Fischer
C100 Cryomodule Leak check | CP-C100-CM-LKTS |  | Bigalow | Campbell
C100 Cryomodule Endcan Prep | CP-C100-CM-PREP-ENC |  | Fischer
C100 Cryomodule Pressure Test | CP-C100-CM-PRET |  | Bigalow | Fischer
Cryomodule Endcan Alignment | CP-CM-ALGN-ENC |  | Page | Humphry
Cryomodule Warmup in CMTF | CP-CM-CMTF-WARM |  | Worland | Bigalow
Cryomodule U-tube Installation | CP-CM-INST |  | Worland | Bigalow
CM Lifting/Moving to Tunnel | CP-C100-CM-MOVE-CM (was CP-CM-MOVE-CM) |  | Humphry | Worland
CM Lifting/Moving To CMTF | CP-C100-CM-CMTF (was CP-CM-MOVE-CMTF) |  | Humphry | Worland
Preperation for Cryomodule Cooldown in CMTF | CP-CM-PREP-CM |  | Bigalow | Worland
Cryomodule circuit cleanup | CP-CM-PREP-HEHD |  | Worland | Bigalow
Cryomodule Related Operations in the CMTF | CP-CM-OPER-CMTF |  | Fischer | Humphry
Cryomodule Testing Procedures
C100 Maximum Gradient and Operating Gradient Determinations (Tunnel) | CP-C100-COM-CM-CAV-EMAX (was CP-C100-ACC-CM-CAV-EMAX) |  | Drury | Reece/Stirbet
C100 Qo vs. Eacc (Tunnel) | CP-C100-COM-CM-CAV-Qo (was C100-ACC-CM-CAV-QO) |  | Drury | Reece/Stirbet
C100 Cool Down Procedure (Tunnel) | CP-C100-ACC-CM-COOL |  | Hogan | Preble
C100 Swept AM / Dynamic Lorentz | CP-C100-CMTF-CM-CAV-DLRTZ |  | Davis | Drury / (Kirk pick)
C100 Maximum Gradient and Operating Gradient Determinations (CMTF) | C100-CMTF-CM-CAV-EMAX |  | Drury | Reece/Stirbet
C100 Field Emission vs. Eacc (CMTF) | C100-CMTF-CM-CAV-FE |  | Drury | Reece/Stirbet
C100 Qext Measurements (CMTF) | C100-CMTF-CM-CAV-HPRF-QEXT |  | Drury | Reece/Stirbet
HOM survey | CP-C100-CAV-CMTF-HOM |  | Marhauser / Wang
C100 Microphonics | CP-C100-CMTF-CM-CAV-LPRF-MICR (was C100-CMTF-CM-CAV-LPRF-MICR) |  | Davis | Drury / (Kirk pick)
C100 Mechanical Modes | CP-C100-CMTF-CM-CAV-LPRF-MODE |  | Davis | Drury / (Kirk pick)
C100 Passbands Measurements | CP-C100-CMTF-CM-CAV-LPRF-PASS (was C100-CMTF-CM-CAV-LPRF-PASS) |  | Drury | Reece/Stirbet
C100 Pressure Sensitivity | C100-CMTF-CM-CAV-PSNS |  | Drury | Reece/Stirbet
C100 Qo vs. Eacc (CMTF) | C100-CMTF-CM-CAV-QO |  | Drury | Reece/Stirbet
C100 Static Lorentz | CP-C100-CMTF-CM-CAV-SLRTZ (was C100-CMTF-CM-CAV-SLRTZ) |  | Davis | Drury / (Kirk pick)
C100 Mechanical Tuner Resolution | CP-C100-CMTF-CM-CAV-TUNE-MRES |  | Davis | Drury / (Kirk pick)
C100 Mechanical Tuner Range and Hysteresis | CP-C100-CMTF-CM-CAV-TUNE-MRNG (was C100-CMTF-CM-CAV-TUNE-MRNG) |  | Grenoble | Drury / Davis
C100 Piezo Tuner Resolution | CP-C100-CMTF-CM-CAV-TUNE-PRES |  | Davis | Drury / (Kirk pick)
C100 Piezo Tuner Range and Hysteresis | CP-C100-CMTF-CM-CAV-TUNE-PRNG (was C100-CMTF-CM-CAV-TUNE-PRNG) |  | Grenoble | Drury / Davis
C100 Cool Down Procedure (CMTF) | CP-C100-CMTF-CM-COOL |  | Hogan | Preble
C100 CMTF Thermal Shield Static Heat Load Measurement | CP-C100-CM-SHHL |  | Hogan | Preble
C100 Silicon Diode Cryogenic Testing Procedure | CP-C100-CM-INSP-DIO |  | Stirbet | Drury/Davis/Hogan
Cryomodule Shipping Procedures
C100 Commissioning Procedure for 8CAV | CP-C100-CM-COM-8CAV |  | Drury | Hogan

## TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Disassembly
Cavity Disassembly | P100-CAV-DISA
Cavity String Disassembly | P100-CST-DISA
Cryomodule Disassembly | P100-CM-DISA
Cavity
Cavity CMM Receiving Inspectopn | P100-INSP-CAV
Cavity HOM Feedthru Receiving Inspection | P100-INSP-HMFT
Secondary Waveguide Inspection (knife edge and sealing surface) | P100-INSP-GVWG
Primary waveguide Inspection | P100-INSP-WGD
Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | P100-INSP-WGD-RCYC
Cavity RF Inspection Receiving Inspection | P100-CAV-RFIN
Cavity Tuning | P100-CAV-TUNE
Cavity Bake-Out | P100-CAV-BAKE
Window Leak Check | P100-CAV-LEAK-WIN
Cavity BCP | P100-CHEM-BCP
Cavity Degreasing | P100-CHEM-USC
Cavity EP | P100-CHEM-EP
Cavity HPR | P100-CHEM-HPR
Cavity String Component Cleaning | P100-CHEM-CLN-COMP
Cavity String Tooling Cleaning | P100-CHEM-CLN-STTL
Secondary waveguide cleaning | P100-CHEM-CLN-GVWG
Cavity Flange Lapping | P100-CHEM-LAP
Cavity Assembly & Leak Test | P100-CAV-ASSY
Helium Vessel Installation | P100-CAV-ASSY-HELV
VTA Cooldown of P100 7-Cell cavities | P100-CAV-VTA-COOL
VTA HOM | P100-CAV-VTA-HOM
Cavity VTA Test | P100-CAV-VTRF | VTA RF Testing Procedure, Excel Spreafsheet for VTRF Measurements
Cavity String
Valve INSP | P100-INSP-VALV | [8 empty] | K. Wilson
Cavity String Component Cleaning | P100-CHEM-CLN-COMP
Cavity String Tooling Cleaning | P100-CHEM-CLN-STTL
Cavity String Assembly & Leak Test | P100-CST-ASSY-AS01
Waveguide Sub-Assembly & Leak Test | P100-CST-ASSY-WGD
Cryomodule
Cold Electrical Feedthru Receiving Inspection | P100-INSP-ELFT
Cryomodule Assembly
Phase 1 Cryomodule Assembly | P100-CM-ASSY-FRST | [8 empty] | I think these are
Phase 2 Cryomodule Assembly | P100-CM-ASSY-SCND | [8 empty] | redundant
Cold Mass Assembly | P100-CM-ASSY-COLD
Cryomodule Beampipe Assembly | P100-CM-ASSY-BPIP
Thermal Shield and Space Frame Assembly | P100-CM-ASSY-SFR
Vacuum Vessel and End Can Assembly | P100-CM-ASSY-VV
Final Cryomodule Assembly | P100-CM-ASSY
Cryomodule Testing
Cryomodule Acceptance Test | P100-CM-ACTS-CRYO
Cryomodule Acceptance Test | P100-CM-ACTS-LPRF
Cryomodule Acceptance Test | P100-CM-ACTS-HPRF
Cryomodule Installation & Commissioning
Cryomodule Tunnel Installation | P100-CM-INST
Cryomodule Commissioning | P100-CM-COMM
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | P100-D3
Inspection Summary Report | P100-INSR
Inspection Nonconformance Report | P100-NCR

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## TRAVELERSold
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A