## P1 Inv
P1 Waveguide Conversion to F100 Style
Parts Inventory, Location, and Inspection notes
Part |  | SN's |  |  | Location |  | Inspection Status/Notes | Primes Disposition | NCR Link
CRM1007070-0000 Cold Waveguide (2) |  |  |  | NONE FOUND
I chose an arbitrary batch, more in the | WGD | F034887/14 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
Inventory area. See attached Primes |  | F034887/11 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
sheet |  | F034887/18 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
|  | F034887/06 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
|  | F034887/02 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
|  | F034887/19 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
|  | F034887/08 | CRM1007070-0000 | R100 | INV Area |  | No data in Pansophy | Hold-Inspection Pending
Total 7
CRM1207070-0000 Cold Waveguide (6)
11 Others in Inventory area-Rejected tag | WGD | F063952/02 | NOT IN PRIMES |  | CG Rad Cabinet -TLA | RAM Tag-6171 | Cavity end flange machined, small step left | No Info- NCR 18/325 D3-18 | C100-CAV-NCR #18 #325;
for various reasons |  | F067764/05 | NOT IN PRIMES |  | CG Rad Cabinet -TLA | RAM Tag-6169 | Cavity end flange machined, small step left | No Info- NCR 323 D3-7/9 | C100-CAV-NCR #323
|  | F061584/04 | NOT IN PRIMES |  | CG Rad Cabinet -TLA | RAM Tag-6170 | Cavity end flange machined, small step left | No Info- NCR-137 D3-6/11 | C100R-D3 #6 #11
|  | F067764/15 | NOT IN PRIMES |  | CG Rad Cabinet -TLA | RAM Tag-6234 | Cavity end flange machined, small step left | No Info- NCR 322 D3-3/8 | C100-CAV-NCR #322
|  | F061359/10 | NOT IN PRIMES |  | CG Rad Cabinet -TLA | RAM Tag-6235 | Cavity end flange machined, small step left | No Info- NCR 218 D3- 5/10/19 | C100-CAV-NCR #218; C100R-D3 #5, 10, 19
|  | F356223/05 | CRM1207070-0000 | C100 | INV Area |  |  | Hold-Inspection Pending- NCR 340/1014 | C100-CAV-NCR #598 / C100-CAV-INSP-WGD #108 | F100-CAV-NCR
|  | G103046/04 | CRM1207070-0000 | F100 | INV Area |  |  | Use As Is | 40/68; F100-CAV-NCR #40 #68 | black spots in wg after blister test/ modify; scratches in seal area, dark spots/modify/USE AS IS
|  | F890195/03 | CRM1207070-0000 | C100 | INV Area |  |  | Use As Is- NCR 1002 D3-13/15/20/21 | C100-CAV-NCR #1002 / C100-CAV-INSP-WGD #150
|  | G103046/07 | CRM1207070-0000 | F100 | INV Area |  | Yellow Tag- Scratches small flange | Hold- NCR 46/67 | 46/67 F100-CAV-NCR #46 #67 | scratches small flange/ USE AS IS
|  | G103046/01 | NOT IN PRIMES | F100 | INV Area |  | Yellow Tag- Scratches small flange | Hold- NCR 41/71 | 41/71; F100-CAV-NCR #41 #71
|  | G096314/01 | CRM1207070-0000 | F100 | INV Area |  | Yellow Tag- Need RF Testing/Cu plating | Modify- NCR 62 | F100-CAV-NCR #62
|  | G096314/12 | CRM1207070-0000 | F100 | INV Area |  | Yellow Tag- Need RF Testing/Cu plating | Hold- NCR 45/65 | F100-CAV-NCR #45 #65
Total 12
CRM1207075-0035 C100 RF Windows (14)
6 Empty window flanges in Inventory area | WIN | Assem 0035-202 |  |  | INV Area |  | F100 traveler -passed RF tests and "OK to use" | Use As Is | F100-CAV-NCR #55
|  | Assem 0035-181 | CRM1207075-0035 | C100 | INV Area |  | Flunked RF test for high max temp (200+ C) and large gradient across ceramic (10 - 15C)
|  | Assem 0035-191 | CRM1207075-0035 | C100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-224 | CRM1207075-0035 | C100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-192 | CRM1207075-0035 | C100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-223 | CRM1207075-0035 | C100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-095 |  |  | INV Area |  | Traveler states "undetermined failure at 400C- multiple cracks "
|  | Assem 0035-020 | CRM1207075-0035 | C100 | INV Area |  | R100 traveler states "frame failed DIM INSP". No RF test
|  | Assem 0035-222 | CRM1207075-0035 | F100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-221 | CRM1207075-0035 | F100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-022 | CRM1207075-0035 | C100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-220 | CRM1207075-0035 | F100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
|  | Assem 0035-219 | CRM1207075-0035 | F100 | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
Total 13
115800-1033 RF Windows (2)
|  | Rev- 1003 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev- 1009 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev- 1005 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev- 1002 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev- 1007 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev A 1013 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev A 1011 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
|  | Rev A 1016 |  |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
Total 8
CRM1207075-0040 C100 WG Spool Left (3)
| GVWG | L44 | CRM1207075-0040 | C100 | Blue Crab |  | No info on part | Hold- NCR 328/339
| GVWG | L51 | CRM1207075-0040 | F100 | Blue Crab |  | NCR 18 -DNU | Hold- NCR 18
| GVWG | L53 | CRM1207075-0040 | F100 | Blue Crab |  | NCR 20- DNU | Hold- NCR 16/20/21/22/23
| GVWG | L54 | CRM1207075-0040 | F100 | Blue Crab |  | Yellow tag- DNU Rework ? | Hold- NCR 14/30
| GVWG | L50 | CRM1207075-0040 | F100 | INV Area |  | Rejected | Rejected- NCR 10
Total 5
CRM1207075-0041 C100 WG Spool Right (3)
| GVWG | R24 | CRM1207075-0041 | C100 | Blue Crab |  | No info on part | Hold-Inspection Pending/83
| GVWG | R25 | CRM1207075-0041 | C100 | Blue Crab |  | No info on part | Hold-Inspection Pending/66
| GVWG | R35 | CRM1207075-0041 | C100 | Blue Crab |  | Did not locate | Use As Is
| GVWG | R50 | CRM1207075-0041 | F100 | Blue Crab |  | Yellow tag- DNU Rework ? | Hold- NCR 12/29
| GVWG | R53 | CRM1207075-0041 | F100 | Blue Crab |  | NCR 28- DNU | Hold- NCR 15/28
Total 5
115800-1011 WG Spool Left (1)
|  | L01 | GVWG | F100 | Blue Crab |  | Yellow Tag- Repairable or Rework | Modify, NCR 4/27
Total 1
115800-1010 WG Spool Right (1)
|  | R02 | GVWG | F100 | Blue Crab |  | Accepted RFU | Use As Is NCR 7
Total 1

## PRIMES
PARTNUMBER | PARTNAME | PARTREV | SERIALNUMBER | CPNAME | BUILDINGNAME | LOCATIONNAME | STATUSNAME | INVENTORYQTY | VARTYPE
11140-0044 | WAVEGUIDE ASSEMBLY |  | 7 | C50R | TEST LAB | 4I2 | HOLD - NCR | 1
11140-0044 | WAVEGUIDE ASSEMBLY |  |  | SRFOPS | TEST LAB | 3L | NO INSPECTION REQUIRED | 1
115120-1005 | WAVEGUIDE ASSY |  | F018219/15 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A-13 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A-15 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A-5 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A-6 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A-8 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A16 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115120-1005 | WAVEGUIDE ASSY |  | F018219/A7 | F100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
115800-1010 | DBL WINDOW WAVEGUIDE SPOOL-RIGHT |  | R02 | F100 | TEST LAB | 3J | USE AS IS | 1 | GVWGSN
115800-1011 | DBL WINDOW WAVEGUIDE SPOOL-LEFT |  | L01 | F100 | TEST LAB | 3I | MODIFY | 1 | GVWGSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/01 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/02 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/03 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/04 | R100 | TEST LAB | RM 1012 - CMM / RF TUNING | USE AS IS | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/05 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/06 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/07 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/09 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/10 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/13 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/15 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/17 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/19 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F028589/20 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/02 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/06 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/07 | C100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/08 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/10 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/11 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/12 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/14 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/16 | R100 | TEST LAB | 4I2 | PASSED INSPECTION | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/18 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/19 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/21 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/22 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/23 | R100 | TEST LAB | RM 1012 - CMM / RF TUNING | USE AS IS | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/24 | R100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1007070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F034887/25 | C100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1207001-1101 | WAVEGUIDE SUPPORT TUBE |  |  | C100 | TEST LAB | 1B | NO INSPECTION REQUIRED | 12
CRM1207001-1200 HDWR PKG | SINGLE WAVEGUIDE SUPPORT HARDWARE PKG |  |  | C100 | TEST LAB | 9K | NO INSPECTION REQUIRED | 5
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F058824/01 | C100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F061359/13 | C100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F061584/03 | C100 | TEST LAB | RM 1025 - FURNACE | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F063951/03 | C100 | TEST LAB | RM 2224 - MACHA | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F063951/07 | C100 | TEST LAB | RM 1022 - CNC MILLING | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F064155/02 | C100 | TEST LAB | AT LARGE | RETURN TO VENDOR | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F067763/20 | C100 | TEST LAB | AT LARGE | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F356223/05 | C100 | TEST LAB | 4I2 | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F356224/06 | C100 | TEST LAB | 2G | HOLD - INSPECTION PENDING | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F356225/01 | C100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F890195/03 | C100 | TEST LAB | 4I2 | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F892522/04 | C100 | TEST LAB | LEAK TEST | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F892522/05 | C100 | TEST LAB | RM 1025 - FURNACE | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F892522/08 | C100 | TEST LAB | 6G | RETURN TO VENDOR | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F897109/01 | C100 | TEST LAB | RM 1025 - FURNACE | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F898271/01 | C100 | TEST LAB | RM 1025 - FURNACE | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F898271/04 | C100 | TEST LAB | 6G | MODIFY | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | F898271/05 | C100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G010213-01 | F100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G010213-02 | F100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G096314-01 | F100 | TEST LAB | 4I2 | MODIFY | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G096314-03 | F100 | TEST LAB | RM 1025 - FURNACE | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G096314-12 | F100 | TEST LAB | 4I2 | HOLD - NCR | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G103046-01 | F100 | TEST LAB | 4I2 | HOLD - NCR | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G103046-02 | F100 | TEST LAB | RM 1012 - CMM / RF TUNING | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G103046-03 | F100 | TEST LAB | 6G | REJECTED | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G103046-04 | F100 | TEST LAB | 4I2 | USE AS IS | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G103046-06 | F100 | TEST LAB | 4I2 | HOLD - NCR | 1 | WGDSN
CRM1207070-0000 | 12GEV WAVEGUIDE ASSEMBLY |  | G103046-07 | F100 | TEST LAB | 4I2 | HOLD - NCR | 1 | WGDSN
CRM1207075-0003 HDWR PKG | RIGHT SIDE WAVEGUIDE SPOOL ASSY |  |  | C100 | TEST LAB | 9I | NO INSPECTION REQUIRED | 3
CRM1207075-0040 | WAVEGUIDE SPOOL - LEFT |  | L44 | C100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - NCR | 1 | GVWGSN
CRM1207075-0040 | WAVEGUIDE SPOOL - LEFT |  | L50 | F100 | TEST LAB | 6D | REJECTED | 1 | GVWGSN
CRM1207075-0040 | WAVEGUIDE SPOOL - LEFT |  | L51 | F100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - NCR | 1 | GVWGSN
CRM1207075-0040 | WAVEGUIDE SPOOL - LEFT |  | L53 | F100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - NCR | 1 | GVWGSN
CRM1207075-0040 | WAVEGUIDE SPOOL - LEFT |  | L54 | F100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - NCR | 1 | GVWGSN
CRM1207075-0041 | WAVEGUIDE SPOOL - RIGHT |  | R24 | C100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - INSPECTION PENDING | 1 | GVWGSN
CRM1207075-0041 | WAVEGUIDE SPOOL - RIGHT |  | R25 | C100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - INSPECTION PENDING | 1 | GVWGSN
CRM1207075-0041 | WAVEGUIDE SPOOL - RIGHT |  | R35 | C100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | USE AS IS | 1 | GVWGSN
CRM1207075-0041 | WAVEGUIDE SPOOL - RIGHT |  | R50 | F100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - NCR | 1 | GVWGSN
CRM1207075-0041 | WAVEGUIDE SPOOL - RIGHT |  | R53 | F100 | BLUE CRAB - LCLS-II | BLUECRAB FLOOR | HOLD - NCR | 1 | GVWGSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-020 | C100 | TEST LAB | RM 1012 - CMM / RF TUNING | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-022 | C100 | TEST LAB | 4J | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-089 | C100 | TEDF | LOBBY | REJECTED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-095 | C100 | TEST LAB | 4J | HOLD - INSPECTION PENDING | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-122 | C100 | TEST LAB | 6D | REJECTED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-140 | C100 | TEST LAB | RM 2224 - MACHA | REJECTED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-161 | C100 | TEST LAB | RM 1012 - CMM / RF TUNING | USE AS IS | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-181 | C100 | TEST LAB | 4J | HOLD - NCR | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-188 | C100 | TEST LAB | 4J | HOLD - INSPECTION PENDING | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-190 | C100 | TEST LAB | RM 1012 - CMM / RF TUNING | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-191 | C100 | TEST LAB | 4J | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-192 | C100 | TEST LAB | 4J | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-219 | F100 | TEST LAB | 3J2 | PASSED INSPECTION | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-220 | F100 | TEST LAB | 3J2 | PASSED INSPECTION | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-221 | F100 | TEST LAB | 3J2 | PASSED INSPECTION | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-222 | F100 | TEST LAB | 3J2 | PASSED INSPECTION | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-223 | F100 | TEST LAB | 3J2 | PASSED INSPECTION | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | ASSEM0035-224 | F100 | TEST LAB | 3J2 | PASSED INSPECTION | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | OML-B-0001 | BNL | TEST LAB | 4I2 | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | OML-B-0003 | BNL | TEST LAB | 4I2 | NO INSPECTION REQUIRED | 1 | WINSN
CRM1207075-0035 | ADAPTER WINDOW ASSEMBLY |  | OML-B-0004 | BNL | TEST LAB | 4I2 | NO INSPECTION REQUIRED | 1 | WINSN