## TIMELINE
Task Name | Start
P100-01 Overview |  | PART | RECEIVE | CM | ASSEMBLIES | START | FINISH
Procurement (RECV PARTS) |  | Flange NW250 + feedthrough flange weld |  | P100-01 | Cavity String Assembly
Cavity Qualification |  | FLANGE NW250 + FEEDTHRU FLANGE WELD |  | P100-01 | COLD MASS ASSEMBLY
Cavity String Assembly |  | SURGE TANK |  | P100-01 | SPACEFRAME THERMAL SHIELD
Cold Mass Assembly |  | WARM TO COOL ASSY (SUPPLY END) |  | P100-01 | Final Assembly
Space Frame Assembly |  | TOPHATS |  | P100-01 | CMTF Testing
Final Assembly |  | SHIPPING TESTS |  | P100-01 | Tunnel Installation
Cold Shock Test |  | FLANGE BLANK ASSY |  | P100-01 | Commissioning
Shipping Preparation |  | FPCs
Cryomodule Shipping |  | HELV
LARGE FPC/TOPHAT BELLOWS
TUNER
CAVs
WARM TO COOL BELLOWS
Need confirmation on schedule of parts arriving and start of assemblies |  | WARM TO COOL SPOOL ASSY
GATE VALVE MDC 303006-133
HELIUM OUTLET BELLOWS
VAT RIGHT ANGLE VALBE (SUPPLY END)
GATE VALVE MDC 302004
SOFT SHUT VALVES
SPACEFRAME
BELLOWS
INSTRUMENTATION
MAG SHIELDING
SENC
VV
CST ASSY
THERMAL SHIELD
COLD MASS ASSY
SPACEFRAME THERMAL SHIELD ASSY
RENC
CM FINAL ASSY
SHIP CM01

## PROCUREMENT
| Procurement Requirement | Subcontracting Officer | SOTR/ Engineer | Contract Award date (SOW and requirements defined, so Traveler can be started ) | Expected delivery date
1 | Helium Vessel
2 | Tuner Motors (Stepper)
2a | Tuner Harmonic Drives
2b | Tuner Frames
3 | Thermal Shield
4 | MLI
5 | Spaceframe
6 | Vacuum Vessel
7 | Supply End Can
8 | Return End Can
9 | Return End Can Heat Exchangers
10 | Instrumentation
10a | Instrumentation - Cernox Diodes
10b | Instrumentation - Heater
10c | Instrumentation - Liquid Level Probe
10d | Instrumentation - Field Probe Cable
10e | Instrumentation - Pressure Gages
10f | Instrumentation - Helium Feedthrough
10g | Instrumentation - Vacuum Feedthroughs
12 | Magnetic Shielding
13 | Cleanroom String Assembly (Beamline Bellows)
13a | Cleanroom String Assembly (Gate Valves)
13b | Cleanroom String Assembly (Warm to Cold Spool Assemblies)
13c | Cleanroom String Assembly (VAT Right Angle Valves)
13d | Cleanroom String Assembly (Titan Pump)
13e | Cleanroom String Assembly (Soft Shut Valve)
14 | Cold Mass Assembly (Helium Outlet Bellows)
14a | Cold Mass Assembly (Large FPC/Tophat Bellows)
15 | Final Cryomodule Assembly (Gate Valve VAT)
15a | Final Cryomodule Assembly (Flange Blank Assembly)
15b | Final Cryomodule Assembly (Surge Tank)
15c | Final Cryomodule Assembly (Flange NW 250 Feedthrough)
15d | Final Cryomodule Assembly (Pressure Relief Plates and Rupture Disks)
15e | Final Cryomodule Assembly (Tophats)

## PARTS
order | Pansophy Acronym | Part | Drawing Number(s) | SOTR/ENGR | BACKUP ENGR | RECV (VEND DOCS/VISUAL) | INSP (VISUAL/CMM) | PROC (CHEM/BAKE) | ASSY | TEST (LEAK/VTA) | PART SERIALIZATION
47 | FPCWSN | AIR SIDE ASSEMBLY |  |  |  |  | VISUAL
14 | CAVSN | CAVITY |  |  |  |  | VISUAL / HOM DEPTH / CMM | BCP / USC / HEAT / HPR | ASSY? HELV? | TUNE / VTA
16 |  | CAVITY STRING ASSEMBLY "PARTS"
36 | VARIES | CERNOX DIODES
18 | CSTSN | CLEAN ROOM ASSEMBLY | [5 empty] | CLN
26 |  | CRYOMODULE ASSY FLANGE BLANK |  |  |  |  | VISUAL
27 |  | CRYOMODULE ASSY FLANGE NW 250 FEEDTHROUGH |  |  |  |  | VISUAL
25 | VARIES | CRYOMODULE ASSY GATE VALVE MDC
28 | PBDSN | CRYOMODULE ASSY RUPTURE DISKS
9 |  | CRYOMODULE ASSY SURGE TANK
29 | VARIES | CRYOMODULE ASSY TOPHATS
11 |  | CRYOMODULE STAND
45 |  | CRYOMODULE TOP LEVEL ASSEMBLY
46 |  | CRYOMODULE WARM TO COLD
19 | AMGVSN | CST ASSY GATE VALVES
39 | VARIES | FIELD PROBE CABLE
13 | FPCSN | FUNDAMENTAL POWER COUPLER |  |  |  |  | VISUAL | BAKE | HPRF
37 | VARIES | HEATER
41 | VARIES | HELIUM FEEDTHROUGHS
23 |  | HELIUM OUTLET BELLOWS
17 | HELVSN | HELIUM VESSEL |  |  |  |  | VISUAL |  | ASSY
5 | IMAGSN | INNER MAGNETIC SHIELD |  |  |  |  | VISUAL
44 |  | INSTALLATION ASSEMBLY
35 | VARIES | INSTRUMENTATION | [5 empty] | CALIBRATION?
42 |  | INSULATING VACUUM
24 |  | LARGE FPC / TOPHAT BELLOWS
38 | HLSSN | LIQUID LEVEL PROBE
33 |  | MLI
4 | OMAGSN | OUTER MAGNETIC SHIELD |  |  |  |  | VISUAL
40 | VARIES | PRESSURE GAGES
43 |  | REFERENCE MODEL
1 |  | RENC HEAT EXCHANGERS
3 | RECSN | RETURN END CAN |  |  |  |  | VISUAL / MEASURE |  |  | LEAK
22 |  | SOFT SHUT VALVE
31 | SFRSN | SPACEFRAME |  |  |  |  | VISUAL / DIMENSIONAL
2 | SECSN | SUPPLY END CAN |  |  |  |  | VISUAL / MEASURE |  |  | LEAK
32 | THRMSN | THERMAL SHIELD / RENC THERMAL SHIELD / SENC THERMAL SHIELD |  |  |  |  | VISUAL / CMM
21 | VARIES | TITAN PUMP
12 |  | TOOLING
6 | TUNWSN or TUNCSN | TUNER ASSY
10 | VARIES | TUNER FRAMES
7 | HMDRSN | TUNER HARMONIC DRIVES
8 | SMSN | TUNER MOTORS
34 | VARIES | VACUUM FEEDTHROUGHS
30 | VVSN | VACUUM VESSEL |  |  |  |  | VISUAL
20 | AV15SN | VAT RIGHT ANGLE VALVES
15 | RTBPSN SUBPSN | WARM TO COLD SPOOL ASSY

## Cavity
Document Type | Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Pull traveler from Project? | Revision | Author | Reviewer | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Inventory
Cavity Component Preparation
Inspection
Traveler | Cavity HOM Feedthru Receiving Inspection | P70-INSP-HMFT
Traveler | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | P70-INSP-WGD-RCYC
Chemistry
Procedure | Acid Etching at the Chemical Fume Hood Procedure | CP-STP-CAV-CHEM-ACID
Procedure | Degreasing Procedure | CP-STP-CAV-CHEM-DEGR
Procedure | Standard Cavity Seal Surface Repair | CP-STP-CAV-CHEM-FLNG
Procedure | EP Procedure? | CP-STP-CAV-CHEM-HEP
Procedure | Standard Manual UltrasonicWall Thickness Measurement Procedure | CP-STP-CHEM-THKN
Procedure | Standard Cavity Degreasing Procedure | CP-STP-CAV-CHEM-USC
Traveler | Secondary waveguide cleaning | P70-CHEM-CLN-GVWG
Traveler | Cavity Flange Lapping | P70-CHEM-LAP
Procedure | C100 Cavity Tophat Flange Repair | CP-C100-CAV-LAP-THAT
Procedure | C100 Cavity Flange Protection | CP-C100-CAV-PROT-FLNG
Procedure | C100 Top Hat Seal Surface Repair | CP-C100-TH-REPR-FLNG
Procedure | C100 probe calibration procedure | CP-C100-CAL-PRB
Procedure | C100 Cavity Cage Bracket Alingment Procedure | CP-C100-CAV-ALGN-CAGE
Procedure | C100 waveguide cleaning procedure | CP-C100-CAV-CLN-WGD
Assembly
Traveler | Waveguide and window weldment modification | P70-COMP-WGWIN-WELD |  |  |  | New | R1 | K Macha | S Williams |  |  |  | 2020-08-01 |  |  |  |  | Draft in Docushare
Cavity Preparation
Inspection
Traveler | Cavity CMM Receiving Inspection | P70-INSP-CAV
Traveler | Cavity RF Inspection Receiving Inspection | P70-CAV-RFIN
Traveler | Cavity Tuning | P70-CAV-TUNE
Traveler | Cavity Bake-Out | P70-CAV-BAKE
Procedure | Ultrasonic Cavity Wall Thickness Measurement Procedure | CP-C100-CAV-THKM
Chemistry
Traveler | Cavity BCP | P70-CHEM-BCP
Traveler | Cavity Degreasing | P70-CHEM-USC
Traveler | Cavity EP | P70-CHEM-EP
Traveler | Cavity HPR | P70-CHEM-HPR
Procedure | C100 Cavity bake procedure | CP-C100-CAV-BAKE
Procedure | C100 BCP procedure | CP-C100-CAV-CHEM
Procedure | C100 cavity degreasing procedure | CP-C100-CAV-DEGR
Procedure | C100 EP procedure | CP-C100-CAV-EPOL
Procedure | C100 cavity evacuation | CP-C100-CAV-EVAC
Procedure | C100 cavity heat Treatment | CP-C100-CAV-HEAT
Procedure | C100 HPR procedure | CP-C100-CAV-HPR
Procedure | C100 cavity HOM tuning procedure | CP-C100-CAV-HTUNE
Procedure | RGA Leak Test Procedure | CP-C100-CAV-LKTS
Procedure | C100 lollipop assembly and cavity alignment procedure | CP-C100-CAV-LOLI
Procedure | C100 Cavity Seal surface repair | CP-C100-CAV-REPR-FLNG
Procedure | C100 Cavity Straightness Inspection Procedure | CP-C100-CAV-STRAT
Procedure | C100 cavity tuning procedure | CP-C100-CAV-TUNE
Assembly
Traveler | Cavity Assembly & Leak Test | P70-CAV-ASSY
Traveler | Helium Vessel Installation | P70-CAV-ASSY-HELV
Procedure | C100 1st assembly procedure for VTA qualification | CP-C100-CAV-ASSY
Procedure | C100 Final assembly procedure for VTA qualification | CP-C100-CAV-ASSY2
Procedure | C100 cover the cavity in the class 10 clean room | CP-C100-CAV-COVR
Procedure | C100 cavity installation into the lift cart and rail install | CP-C100-CST-CAV-LFTC
Procedure | C100 VAT valve assembly onto cavity | CP-C100-CST-CAV-VALV
Procedure | C100 Waveguide assembly onto cavity | CP-C100-CST-CAV-WAVG
Procedure | Cavity installation into test stand procedure | CP-CAV-INST-TSTD
Procedure | Test stand Cable connection procedure | CP-CAVPR-CAV-CHK-TSTD
Procedure | C100 Radial Wedge Clamp Installation Procedure | CP-C100-RWFC-INST
Testing
Traveler | VTA Cooldown of P70 7-Cell cavities | P70-CAV-VTA-COOL
Traveler | VTA HOM | P70-CAV-VTA-HOM
Traveler | Cavity VTA Test | P70-CAV-VTRF

## Cavity String
Document Type | Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Pull traveler from Project? | Revision | Author | Reviewer | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Inventory
Cavity String Component Preparation
Inspection
Chemistry
Traveler | Cavity String Component Cleaning | P70-CHEM-CLN-COMP
Traveler | Cavity String Tooling Cleaning | P70-CHEM-CLN-STTL
Assembly
Cavity String Assembly
Inspection
Traveler | Valve INSP | P70-INSP-VALV
Chemistry
Traveler | Cavity String Component Cleaning | P70-CHEM-CLN-COMP
Traveler | Cavity String Tooling Cleaning | P70-CHEM-CLN-STTL
Assembly
Traveler | Cavity String Assembly & Leak Test | P70-CST-ASSY-AS01
Traveler | Waveguide Sub-Assembly & Leak Test | P70-CST-ASSY-WGD
Procedure | C100 Beamline Assembly Procedure | CP-C100-CST-CAV-BLN
Procedure | C100 Cavity String Component | CP-C100-CST-CLN-COMP
Procedure | C100 Cavity String Tooling Cleaning | CP-C100-CST-CLN-STTL
Procedure | C100 Cavity String Evacuation and Leak Test Procedure | CP-C100-CST-EVAC
Procedure | C100 Ion Pump Installation and Starting Procedure | CP-C100-CST-ION
Procedure | C100 Cavity String Kit List | CP-C100-CST-KIT

## Cryomodule
Document Type | Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Inventory
Disassembly
Cryomodule Component Preparation
Inspection
Traveler | Primary waveguide Leak Check [RF Wave Guides?] | P70-RFIN-WGD |  |  |  |  | fischer |  |  |  |  | ASAP
Traveler | Primary waveguide Inspection [RF Wave Guides?] | P70-INSP-WGD |  |  |  |  | fischer |  |  |  |  | SOON |  |  |  |  | C100R-CAV-INSP-WGD
Traveler | Waveguide Spools Leak Check | P70-LEAK-GVWG |  |  |  |  | fischer |  |  |  |  | ASAP
Traveler | Secondary Waveguide Inspection [RF Wave Guide Spools?] | P70-INSP-GVWG |  |  |  |  | fischer |  |  |  |  | SOON |  |  |  |  | C100R-CM-INSP-GVWG
Traveler | Window Leak Check | P70-LEAK-WIN |  |  |  |  | fischer |  |  |  |  | SOON
Traveler | RF Ceramic Windows RF Testing | P70-RFIN-WIN |  |  |  |  | fischer |  |  |  |  | ASAP
Traveler | RF Ceramic Windows Inspection | P70-INSP-WIN |  |  |  |  | fischer |  |  |  |  | SOON |  |  |  |  | C100-CAV-INSP-ASSY-WIN
Chemistry
Assembly
Traveler | Welding Waveguide to Window | [5 empty] | macha
VTA RF Testing Procedure, Excel Spreafsheet for VTRF Measurements
Cryomodule Assembly
Inspection
Traveler | Cold Electrical Feedthru Receiving Inspection | P70-INSP-ELFT
Cryomodule Assembly
Traveler | Phase 1 Cryomodule Assembly | P70-CM-ASSY-FRST | [8 empty] | I think these are
Traveler | Phase 2 Cryomodule Assembly | P70-CM-ASSY-SCND | [8 empty] | redundant
Traveler | Cold Mass Assembly | P70-CM-ASSY-COLD
Traveler | Cryomodule Beampipe Assembly | P70-CM-ASSY-BPIP
Traveler | Thermal Shield and Space Frame Assembly | P70-CM-ASSY-SFR
Traveler | Vacuum Vessel and End Can Assembly | P70-CM-ASSY-VV
Traveler | Final Cryomodule Assembly | P70-CM-ASSY
Traveler | Alignment?
Traveler | Leak Test?
Traveler | Demag?
Procedure | C100 RF Window Welding Procedure | CP-C100-CST-WELD-WWIN
Procedure | C100 Helium Vessel Installation | CP-C100-CAV-INST-HELV
Procedure | C100 Helium Vessel Welding | CP-C100-CST-WELD-HELV
Procedure | C100 Cryomodule Alignment | CP-C100-CM-ALGN
Procedure | C100 Cryomodule Beampipe Assembly/Installation | CP-C100-CM-ASSY-BPIP
Procedure | C100 Cold Tuner Installation Procedure | CP-C100-CM-ASSY-CTNR
Procedure | C100 Cryomodule Spaceframe Assembly | CP-C100-CM-ASSY-SFR
Procedure | C100 Cryomodule Tuner Assembly-Warm | CP-C100-CM-ASSY-TUNW (was CP-C100-CM-ASSY-WTNR)
Procedure | C100 Cryomodule JT Actuator calibration | CP-C100-CM-CAL-JTAT
Procedure | C100 Helium Vessel Installation Procedure | CP-C100-CM-INST-HELV
Procedure | C100 Cryomodule MLI installation | CP-C100-CM-INST-MLI
Procedure | C100 Cryomodule Secondary Waveguide/Sweep Installation/Removal | CP-C100-CM-INST-WGSP
Procedure | C100 Cryomodule Leak check | CP-C100-CM-LKTS
Procedure | C100 Cryomodule Endcan Prep | CP-C100-CM-PREP-ENC
Procedure | C100 Cryomodule Pressure Test | CP-C100-CM-PRET
Procedure | Cryomodule Endcan Alignment | CP-CM-ALGN-ENC
Procedure | Cryomodule Warmup in CMTF | CP-CM-CMTF-WARM
Procedure | Cryomodule U-tube Installation | CP-CM-INST
Procedure | CM Lifting/Moving to Tunnel | CP-C100-CM-MOVE-CM (was CP-CM-MOVE-CM)
Procedure | CM Lifting/Moving To CMTF | CP-C100-CM-CMTF (was CP-CM-MOVE-CMTF)
Procedure | Preperation for Cryomodule Cooldown in CMTF | CP-CM-PREP-CM
Procedure | Cryomodule circuit cleanup | CP-CM-PREP-HEHD
Procedure | Cryomodule Related Operations in the CMTF | CP-CM-OPER-CMTF
Cryomodule Testing
Cryomodule Testing
Traveler | Cryomodule Acceptance Test | P70-CM-ACTS-CRYO
Traveler | Cryomodule Acceptance Test | P70-CM-ACTS-LPRF
Traveler | Cryomodule Acceptance Test | P70-CM-ACTS-HPRF
Procedure | C100 Maximum Gradient and Operating Gradient Determinations (Tunnel) | CP-C100-COM-CM-CAV-EMAX (was CP-C100-ACC-CM-CAV-EMAX)
Procedure | C100 Qo vs. Eacc (Tunnel) | CP-C100-COM-CM-CAV-Qo (was C100-ACC-CM-CAV-QO)
Procedure | C100 Cool Down Procedure (Tunnel) | CP-C100-ACC-CM-COOL
Procedure | C100 Swept AM / Dynamic Lorentz | CP-C100-CMTF-CM-CAV-DLRTZ
Procedure | C100 Maximum Gradient and Operating Gradient Determinations (CMTF) | C100-CMTF-CM-CAV-EMAX
Procedure | C100 Field Emission vs. Eacc (CMTF) | C100-CMTF-CM-CAV-FE
Procedure | C100 Qext Measurements (CMTF) | C100-CMTF-CM-CAV-HPRF-QEXT
Procedure | HOM survey | CP-C100-CAV-CMTF-HOM
Procedure | C100 Microphonics | CP-C100-CMTF-CM-CAV-LPRF-MICR (was C100-CMTF-CM-CAV-LPRF-MICR)
Procedure | C100 Mechanical Modes | CP-C100-CMTF-CM-CAV-LPRF-MODE
Procedure | C100 Passbands Measurements | CP-C100-CMTF-CM-CAV-LPRF-PASS (was C100-CMTF-CM-CAV-LPRF-PASS)
Procedure | C100 Pressure Sensitivity | C100-CMTF-CM-CAV-PSNS
Procedure | C100 Qo vs. Eacc (CMTF) | C100-CMTF-CM-CAV-QO
Procedure | C100 Static Lorentz | CP-C100-CMTF-CM-CAV-SLRTZ (was C100-CMTF-CM-CAV-SLRTZ)
Procedure | C100 Mechanical Tuner Resolution | CP-C100-CMTF-CM-CAV-TUNE-MRES
Procedure | C100 Mechanical Tuner Range and Hysteresis | CP-C100-CMTF-CM-CAV-TUNE-MRNG (was C100-CMTF-CM-CAV-TUNE-MRNG)
Procedure | C100 Piezo Tuner Resolution | CP-C100-CMTF-CM-CAV-TUNE-PRES
Procedure | C100 Piezo Tuner Range and Hysteresis | CP-C100-CMTF-CM-CAV-TUNE-PRNG (was C100-CMTF-CM-CAV-TUNE-PRNG)
Procedure | C100 Cool Down Procedure (CMTF) | CP-C100-CMTF-CM-COOL
Procedure | C100 CMTF Thermal Shield Static Heat Load Measurement | CP-C100-CM-SHHL
Procedure | C100 Silicon Diode Cryogenic Testing Procedure | CP-C100-CM-INSP-DIO
Cryomodule Installation & Commissioning
Traveler | Cryomodule Tunnel Installation | P70-CM-INST
Traveler | Cryomodule Commissioning | P70-CM-COMM
Procedure | C100 Commissioning Procedure for 8CAV | CP-C100-CM-COM-8CAV