## FY20
PANSOPHY ROADMAP |  |  | START MONTH |  | 2020-01-01
FY20 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
MILESTONES
Quality
Core Development
Traveler System
Project Tools
Production Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q2 Review
Q3 Review
Q4 Review
Q1 Review
Projects Overview
Converter Upgrades
Sec 4
Sec 7
Sec 9
CF2018
Key Security
Login Security
Template Upgrades
Automate Conversion
Traveler Completion
Traveler Writing
Procedure Writing
Inventory
Status Boards
Project Travelers
Help System
Training Slides
SRF Webpage
WHO?
WHO?
VB
VB
VB
MM
MM
MD
MD
Students
D.C.
MM
Records Process Management
TPQM
WHO?
WHO?
EDX
Student
COVID 19 / MEDCON 5
C75
P1

## FY21
PANSOPHY ROADMAP |  |  | START MONTH |  | 2021-01-01
FY21 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
MILESTONES
Quality
Core Development
Traveler System
Project Tools
Production Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q2 Review
Q3 Review
Q4 Review
Q1 Review
QMS
VTA Use
FE Onset
Calibration
Training
Beyond the Firewall
CF2020
Data Security
Converter Upgrades
Template Upgrades
Workcenter Timelines
ASSY Part Verification
Global Project
Global Quality
Status Board Generator
CM Drilldowns
KPIs/ACLs
Process Flow
Menu System / Editor
Pansophy Facelift
Programmer Guides
User Guides
SRF Webpage
Communication system
Training Classes
Project Travelers (Student?)
WHO?
Student / D.C.
WHO?
Student
SAMTRAXS (Summer Student?)
VB
VB
VB
VB
MD
MM
MM
D.C.
MM
QB Metrics
Production Overview
SQL Security
Automate User Verification
Drawing Cfg
Part Status/Trace
Data Completion
Closure Completion
SAMTRAXS (Student?)
C75
C100R
P1
PPU

## FY22
PANSOPHY ROADMAP |  |  | START MONTH |  | 2022-01-01
FY22 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
MILESTONES
Quality
Core Development
Traveler System
Project Tools
Production Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q2 Review
Q3 Review
Q4 Review
Q1 Review
QMS
Beyond the Firewall
CF2020 Patches
Converter Upgrades
Template Upgrades
CMTF
VTA
VTA Cooldowns
VTA Schedule
UDQ
CM Drilldowns
Programmer Guides
User Guides
SRF Webpage
Communication system
Training Classes
Project Travelers (Student?)
WHO?
Student / D.C.
WHO?
Student
SAMTRAXS (Summer Student?)
VB
VB
VB
MM
MM
MD
MM
D.C.
MM
VB
C75
C100R
PPU

## FY23
PANSOPHY ROADMAP |  |  | START MONTH |  | 2023-01-01
FY23 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
MILESTONES
Quality
Core Development
Traveler System
Project Tools
Production Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q2 Review
Q3 Review
Q4 Review
Q1 Review
QMS
Beyond the Firewall
CF2020 Patches
Converter Upgrades
Template Upgrades
CMTF
VTA
VTA Cooldowns
VTA Schedule
UDQ
CM Drilldowns
Programmer Guides
User Guides
SRF Webpage
Communication system
Training Classes
Project Travelers (Student?)
WHO?
Student / D.C.
WHO?
Student
SAMTRAXS (Summer Student?)
VB
VB
VB
MM
MM
MD
MM
MM
VB
C75
C100R

## FY
PANSOPHY ROADMAP |  |  | START MONTH |  | 2020-01-01
FY20 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
MILESTONES
Quality
Core Development
Traveler System
Production Tools
Project Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q1 Review
Q2 Review
Q3 Review
Q4 Review
Converter Upgrades
ISO 9001
CF server
Data Completion
Status Boards
Project Travelers (Student?)
SRF Webpage

## CM BUILDS
|  |  | P1 | C75-01 | C75-02 | C75-03 | C75-04 | C75-05 | C100R-10 | C100R-11 | C100R-12 | PPU01 | PPU02 | PPU03 | PPU04 | PPU05 | CAVITIES | CST | UCM | SFTS | FINAL
FY20 | 2020-01-05 | 1
| 2020-01-12 | 2
| 2020-01-19 | 3
| 2020-01-26 | 4
| 2020-02-02 | 5
| 2020-02-09 | 6
| 2020-02-16 | 7
| 2020-02-23 | 8
| 2020-03-01 | 9
| 2020-03-08 | 10
| 2020-03-15 | 11
| 2020-03-22 | 12
| 2020-03-29 | 13
| 2020-04-05 | 14
| 2020-04-12 | 15
| 2010-04-29 | 16
| 2020-04-26 | 17
| 2020-05-03 | 18
| 2020-05-10 | 19
| 2020-05-17 | 20
| 2020-05-24 | 21
| 2020-05-31 | 22
| 2020-06-07 | 23
| 2020-06-14 | 24
| 2020-06-21 | 25
| 2020-06-28 | 26
FY20 | 2020-07-05 | 27 |  | BUILD | [12 empty] | NOW |  | FY20Q3
Q4 | 2020-07-12 | 28
| 2020-07-19 | 29
| 2020-07-26 | 30
| 2020-08-02 | 31
| 2020-08-09 | 32
| 2020-08-16 | 33
| 2020-08-23 | 34
| 2020-08-30 | 35
| 2020-09-06 | 36
| 2020-09-13 | 37
| 2020-09-20 | 38
| 2020-09-27 | 39
FY21 | 2020-10-04 | 40 | [15 empty] | FY21Q1
Q1 | 2020-10-11 | 41
| 2020-10-18 | 42
| 2020-10-25 | 43
| 2020-11-01 | 44
| 2020-11-08 | 45
| 2020-11-15 | 46
| 2020-11-22 | 47
| 2020-11-29 | 48
| 2020-12-06 | 49 | BUILD
| 2020-12-13 | 50
| 2020-12-20 | 51
| 2020-12-27 | 52
2021 | 2021-01-03 | 1
Q2 | 2021-01-10 | 2
| 2021-01-17 | 3
| 2021-01-24 | 4
| 2021-01-31 | 5
| 2021-02-07 | 6
| 2021-02-14 | 7
| 2021-02-28 | 8
| 2021-03-07 | 9 | [17 empty] | FY21Q2
| 2021-03-14 | 10
| 2021-03-21 | 11
| 2021-03-28 | 12
Q3 | 2021-04-04 | 13
| 2021-04-11 | 14
| 2021-04-18 | 15
| 2021-04-25 | 16
| 2021-04-25 | 17
| 2021-05-02 | 18 | [9 empty] | BUILD | [8 empty] | FY21Q3
| 2021-05-09 | 19
| 2021-05-16 | 20
| 2021-05-23 | 21
| 2021-05-30 | 22
| 2021-06-06 | 23 |  | TEST
| 2021-06-13 | 24
| 2020-06-20 | 25
| 2021-06-27 | 26
Q4 | 2021-07-04 | 27 |  | INSTALL
| 2021-07-11 | 28 | PLASMA
| 2021-07-18 | 29 |  |  | BUILD
| 2021-07-25 | 30
| 2021-08-01 | 31 | [10 empty] | BUILD
| 2021-08-08 | 32 | INSTALL
| 2021-08-15 | 33
| 2021-08-22 | 34
| 2021-08-29 | 35 | [6 empty] | BUILD |  |  |  |  | BUILD
| 2021-09-05 | 36
| 2021-09-12 | 37
| 2021-09-19 | 38
| 2021-09-26 | 39 |  |  |  | BUILD | [10 empty] | FY21Q4
FY22 | 2021-10-03 | 40
Q1 | 2021-10-10 | 41
| 2021-10-17 | 42
| 2021-10-24 | 43 | [9 empty] | TEST |  |  | BUILD
| 2021-10-31 | 44
| 2021-11-07 | 45 | [9 empty] | SHIP
| 2021-11-14 | 46
| 2021-11-21 | 47
| 2021-11-28 | 48
| 2021-12-05 | 49
| 2021-12-12 | 50
| 2021-12-19 | 51
| 2021-12-26 | 52 | [13 empty] | BUILD |  | FY22Q1
2022 | 2022-01-02 | 1
Q2 | 2022-01-09 | 2 |  |  | TEST
| 2022-01-16 | 3
| 2022-01-23 | 4 | [10 empty] | TEST
| 2022-01-30 | 5
| 2022-02-06 | 6 |  |  | INSTALL | [7 empty] | SHIP
| 2022-02-13 | 7
| 2022-02-20 | 8 | [11 empty] | TEST
| 2022-02-27 | 9
| 2022-03-06 | 10 | [11 empty] | SHIP
| 2022-03-13 | 11
| 2022-03-20 | 12 |  |  |  | TEST
| 2022-03-27 | 13 | [16 empty] | FY22Q2
Q3 | 2022-04-03 | 14 | [6 empty] | TEST
| 2022-04-10 | 15
| 2022-04-17 | 16 |  |  |  | INSTALL | [8 empty] | TEST
| 2022-04-24 | 17
| 2022-05-01 | 18 |  |  |  |  | BUILD |  | INSTALL | [5 empty] | SHIP |  |  |  |  | FY22Q3
| 2022-05-08 | 19
| 2022-05-15 | 20 | [7 empty] | BUILD | BUILD
| 2022-05-22 | 21
| 2022-05-29 | 22
| 2022-06-05 | 23
| 2022-06-12 | 24
| 2022-06-19 | 25 | [13 empty] | TEST
| 2022-06-26 | 26
Q4 | 2022-07-03 | 27 | [13 empty] | SHIP
| 2022-07-10 | 28
| 2022-07-17 | 29
| 2022-07-24 | 30
| 2022-07-31 | 31
| 2022-08-07 | 32
| 2022-08-14 | 33
| 2022-08-21 | 34 | [5 empty] | BUILD
| 2022-08-28 | 35
| 2022-09-04 | 36
| 2022-09-11 | 37
| 2022-09-18 | 38
| 2022-09-25 | 39 | [18 empty] | FY22Q4
FY23 | 2022-10-02 | 40
Q1 | 2022-10-09 | 41
| 2022-10-16 | 42
| 2022-10-23 | 43
| 2022-10-30 | 44
| 2022-11-06 | 45
| 2022-11-13 | 46
| 2022-11-20 | 47
| 2022-11-27 | 48
| 2022-12-04 | 49
| 2022-12-11 | 50
| 2022-12-18 | 51
| 2022-12-25 | 52
2023 | 2023-01-01 | 1
Q3 | 2023-01-08 | 2
| 2023-01-15 | 3 | [7 empty] | TEST
| 2023-01-22 | 4
| 2023-01-29 | 5
| 2023-02-05 | 6 | [8 empty] | TEST
| 2023-02-12 | 7 | [7 empty] | INSTALL
| 2023-02-19 | 8
| 2023-02-26 | 9
| 2023-03-05 | 10 | [8 empty] | INSTALL
| 2023-03-12 | 11
| 2023-03-19 | 12
| 2023-03-26 | 13
Q3 | 2023-04-02 | 14
| 2023-04-09 | 15
| 2023-04-16 | 16
| 2023-04-23 | 17
| 2023-04-30 | 18
| 2023-05-07 | 19
| 2023-05-14 | 20
| 2023-05-21 | 21
| 2023-05-28 | 22
| 2023-06-04 | 23
| 2023-06-11 | 24
| 2023-06-18 | 25
| 2023-06-25 | 26
Q4 | 2023-07-02 | 27
| 2023-07-09 | 28
| 2023-07-16 | 29
| 2023-07-23 | 30
| 2023-07-30 | 31
| 2023-08-06 | 32
| 2023-08-13 | 33
| 2023-08-20 | 34
| 2023-08-27 | 35
| 2023-09-03 | 36
| 2023-09-10 | 37
| 2023-09-17 | 38
| 2023-09-24 | 39
| 2023-10-01 | 40
| 2023-10-08 | 41
| 2023-10-15 | 42
| 2023-10-22 | 43
| 2023-10-29 | 44
| 2023-11-05 | 45
| 2023-11-12 | 46
| 2023-11-19 | 47
| 2023-11-26 | 48
| 2023-12-03 | 49
| 2023-12-10 | 50
| 2023-12-17 | 51
| 2023-12-24 | 52
| 2023-12-31 | 1