## TIMELINE
Task Name | Start
P100-01 Overview |  | PART | RECEIVE | CM | ASSEMBLIES | START | FINISH
Procurement (RECV PARTS) |  | Flange NW250 + feedthrough flange weld |  | P100-01 | Cavity String Assembly
Cavity Qualification |  | FLANGE NW250 + FEEDTHRU FLANGE WELD |  | P100-01 | COLD MASS ASSEMBLY
Cavity String Assembly |  | SURGE TANK |  | P100-01 | SPACEFRAME THERMAL SHIELD
Cold Mass Assembly |  | WARM TO COOL ASSY (SUPPLY END) |  | P100-01 | Final Assembly
Space Frame Assembly |  | TOPHATS |  | P100-01 | CMTF Testing
Final Assembly |  | SHIPPING TESTS |  | P100-01 | Tunnel Installation
Cold Shock Test |  | FLANGE BLANK ASSY |  | P100-01 | Commissioning
Shipping Preparation |  | FPCs
Cryomodule Shipping |  | HELV
LARGE FPC/TOPHAT BELLOWS
TUNER
CAVs
WARM TO COOL BELLOWS
Need confirmation on schedule of parts arriving and start of assemblies |  | WARM TO COOL SPOOL ASSY
GATE VALVE MDC 303006-133
HELIUM OUTLET BELLOWS
VAT RIGHT ANGLE VALBE (SUPPLY END)
GATE VALVE MDC 302004
SOFT SHUT VALVES
SPACEFRAME
BELLOWS
INSTRUMENTATION
MAG SHIELDING
SENC
VV
CST ASSY
THERMAL SHIELD
COLD MASS ASSY
SPACEFRAME THERMAL SHIELD ASSY
RENC
CM FINAL ASSY
SHIP CM01

## PROCUREMENT
| Procurement Requirement | Subcontracting Officer | SOTR/ Engineer | Contract Award date (SOW and requirements defined, so Traveler can be started ) | Expected delivery date
1 | Helium Vessel
2 | Tuner Motors (Stepper)
2a | Tuner Harmonic Drives
2b | Tuner Frames
3 | Thermal Shield
4 | MLI
5 | Spaceframe
6 | Vacuum Vessel
7 | Supply End Can
8 | Return End Can
9 | Return End Can Heat Exchangers
10 | Instrumentation
10a | Instrumentation - Cernox Diodes
10b | Instrumentation - Heater
10c | Instrumentation - Liquid Level Probe
10d | Instrumentation - Field Probe Cable
10e | Instrumentation - Pressure Gages
10f | Instrumentation - Helium Feedthrough
10g | Instrumentation - Vacuum Feedthroughs
12 | Magnetic Shielding
13 | Cleanroom String Assembly (Beamline Bellows)
13a | Cleanroom String Assembly (Gate Valves)
13b | Cleanroom String Assembly (Warm to Cold Spool Assemblies)
13c | Cleanroom String Assembly (VAT Right Angle Valves)
13d | Cleanroom String Assembly (Titan Pump)
13e | Cleanroom String Assembly (Soft Shut Valve)
14 | Cold Mass Assembly (Helium Outlet Bellows)
14a | Cold Mass Assembly (Large FPC/Tophat Bellows)
15 | Final Cryomodule Assembly (Gate Valve VAT)
15a | Final Cryomodule Assembly (Flange Blank Assembly)
15b | Final Cryomodule Assembly (Surge Tank)
15c | Final Cryomodule Assembly (Flange NW 250 Feedthrough)
15d | Final Cryomodule Assembly (Pressure Relief Plates and Rupture Disks)
15e | Final Cryomodule Assembly (Tophats)

## PARTS
order | Pansophy Acronym | Part | Drawing Number(s) | SOTR/ENGR | BACKUP ENGR | RECV (VEND DOCS/VISUAL) | INSP (VISUAL/CMM) | PROC (CHEM/BAKE) | ASSY | TEST (LEAK/VTA) | PART SERIALIZATION
47 | FPCWSN | AIR SIDE ASSEMBLY |  |  |  |  | VISUAL
14 | CAVSN | CAVITY |  |  |  |  | VISUAL / HOM DEPTH / CMM | BCP / USC / HEAT / HPR | ASSY? HELV? | TUNE / VTA
16 |  | CAVITY STRING ASSEMBLY "PARTS"
36 | VARIES | CERNOX DIODES
18 | CSTSN | CLEAN ROOM ASSEMBLY | [5 empty] | CLN
26 |  | CRYOMODULE ASSY FLANGE BLANK |  |  |  |  | VISUAL
27 |  | CRYOMODULE ASSY FLANGE NW 250 FEEDTHROUGH |  |  |  |  | VISUAL
25 | VARIES | CRYOMODULE ASSY GATE VALVE MDC
28 | PBDSN | CRYOMODULE ASSY RUPTURE DISKS
9 |  | CRYOMODULE ASSY SURGE TANK
29 | VARIES | CRYOMODULE ASSY TOPHATS
11 |  | CRYOMODULE STAND
45 |  | CRYOMODULE TOP LEVEL ASSEMBLY
46 |  | CRYOMODULE WARM TO COLD
19 | AMGVSN | CST ASSY GATE VALVES
39 | VARIES | FIELD PROBE CABLE
13 | FPCSN | FUNDAMENTAL POWER COUPLER |  |  |  |  | VISUAL | BAKE | HPRF
37 | VARIES | HEATER
41 | VARIES | HELIUM FEEDTHROUGHS
23 |  | HELIUM OUTLET BELLOWS
17 | HELVSN | HELIUM VESSEL |  |  |  |  | VISUAL |  | ASSY
5 | IMAGSN | INNER MAGNETIC SHIELD |  |  |  |  | VISUAL
44 |  | INSTALLATION ASSEMBLY
35 | VARIES | INSTRUMENTATION | [5 empty] | CALIBRATION?
42 |  | INSULATING VACUUM
24 |  | LARGE FPC / TOPHAT BELLOWS
38 | HLSSN | LIQUID LEVEL PROBE
33 |  | MLI
4 | OMAGSN | OUTER MAGNETIC SHIELD |  |  |  |  | VISUAL
40 | VARIES | PRESSURE GAGES
43 |  | REFERENCE MODEL
1 |  | RENC HEAT EXCHANGERS
3 | RECSN | RETURN END CAN |  |  |  |  | VISUAL / MEASURE |  |  | LEAK
22 |  | SOFT SHUT VALVE
31 | SFRSN | SPACEFRAME |  |  |  |  | VISUAL / DIMENSIONAL
2 | SECSN | SUPPLY END CAN |  |  |  |  | VISUAL / MEASURE |  |  | LEAK
32 | THRMSN | THERMAL SHIELD / RENC THERMAL SHIELD / SENC THERMAL SHIELD |  |  |  |  | VISUAL / CMM
21 | VARIES | TITAN PUMP
12 |  | TOOLING
6 | TUNWSN or TUNCSN | TUNER ASSY
10 | VARIES | TUNER FRAMES
7 | HMDRSN | TUNER HARMONIC DRIVES
8 | SMSN | TUNER MOTORS
34 | VARIES | VACUUM FEEDTHROUGHS
30 | VVSN | VACUUM VESSEL |  |  |  |  | VISUAL
20 | AV15SN | VAT RIGHT ANGLE VALVES
15 | RTBPSN SUBPSN | WARM TO COLD SPOOL ASSY

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
ALUMINUM CLEANING PROCEDURE (for vendor) | 11141S0028 Rev B | B | ASHLEYA |  |  | 2019-08-08 |  | M:SNS_PPU/Procurement/Specs/11141S0028 Aluminum Cleaning and Handling Rev B.pdf
STAINLESS STEEL CLEANING PROCEDURE (for vendor) | 11141S0034 | - | ASHLEYA |  |  | 2019-07-26 |  | M:SNS_PPU/Procurement/Specs/11141S0034 Stainless Steel Cleaning REV.pdf
TITANIUM CLEANING PROCEDURE (for vendor) | 11520S0100 | - | ASHLEYA |  |  | 2019-08-07 |  | M:SNS_PPU/Procurement/Specs/11520S0100 Titaniumn Cleaning REV A.pdf
Acid Etching at the Chemical Fume Hood Procedure | CP-STP-CAV-CHEM-ACID
Degreasing Procedure | CP-STP-CAV-CHEM-DEGR
Standard Cavity Seal Surface Repair | CP-STP-CAV-CHEM-FLNG
EP Procedure? | CP-STP-CAV-CHEM-HEP
Standard Manual UltrasonicWall Thickness Measurement Procedure | CP-STP-CHEM-THKN
Standard Cavity Degreasing Procedure | CP-STP-CAV-CHEM-USC
Cavity Procedures
C100 Cavity Tophat Flange Repair | CP-C100-CAV-LAP-THAT |  | Daniels | Castagnola
C100 Cavity Flange Protection | CP-C100-CAV-PROT-FLNG |  | Macha | Castagnola
C100 Top Hat Seal Surface Repair | CP-C100-TH-REPR-FLNG |  | Daniels | Castagnola
C100 probe calibration procedure | CP-C100-CAL-PRB |  | Forehand | Marhauser
C100 Cavity Cage Bracket Alingment Procedure | CP-C100-CAV-ALGN-CAGE |  | Carpenter | Castagnola
C100 1st assembly procedure for VTA qualification | CP-C100-CAV-ASSY |  | Castagnola | Macha
C100 Final assembly procedure for VTA qualification | CP-C100-CAV-ASSY2 |  | Castagnola | Macha
C100 Cavity bake procedure | CP-C100-CAV-BAKE |  | Macha | Davis
C100 BCP procedure | CP-C100-CAV-CHEM |  | Harris | Reilly
C100 waveguide cleaning procedure | CP-C100-CAV-CLN-WGD |  | Davenport | Reilly
C100 cavity degreasing procedure | CP-C100-CAV-DEGR |  | Williams | Reilly
C100 EP procedure | CP-C100-CAV-EPOL |  | Burrill | Reilly
C100 cavity evacuation | CP-C100-CAV-EVAC |  | Castagnola | Macha
C100 cavity heat Treatment | CP-C100-CAV-HEAT |  | Forehand | Reilly
C100 HPR procedure | CP-C100-CAV-HPR |  | Tipton | Reilly
C100 cavity HOM tuning procedure | CP-C100-CAV-HTUNE |  | Forehand | Marhauser
RGA Leak Test Procedure | CP-C100-CAV-LKTS |  | Castagnola | Macha
C100 lollipop assembly and cavity alignment procedure | CP-C100-CAV-LOLI |  | Macha | Castagnola
C100 Cavity Seal surface repair | CP-C100-CAV-REPR-FLNG |  | Daniels | Castagnola
C100 Cavity Straightness Inspection Procedure | CP-C100-CAV-STRAT |  | Carpenter | Reilly
C100 cavity tuning procedure | CP-C100-CAV-TUNE |  | Forehand | Marhauser
1497 MHZ Vertizal Testing Procedure | CP-C100-CAV-VTRF |  | Grenoble | Davis
Low Power RF HOM Measurement Procedure for C100 Cavity in the VTA | CP-C100-CAV-VTRF-HOM |  | Marhauser | Wang
Low Power RF Hom Measurement Procedure for Low Loss Cavities in the VTA using Polfit Mathematica package | CP-C100-CAV-VTRF-HOM-Polfit |  | Stirbet | Wang
C100 waveguide sub-assembly | CP-C100-CAV-WAVG |  | Macha | Castagnola
Ionized Nitrogen Cleaning w/particle counter | CP-C100-CLN-IONN |  | Macha | Castagnola
C100 cover the cavity in the class 10 clean room | CP-C100-CAV-COVR |  | Macha | Castagnola
C100 cavity installation into the lift cart and rail install | CP-C100-CST-CAV-LFTC |  | Macha | Castagnola
C100 VAT valve assembly onto cavity | CP-C100-CST-CAV-VALV |  | Macha | Castagnola
C100 Waveguide assembly onto cavity | CP-C100-CST-CAV-WAVG |  | Macha | Castagnola
Cavity installation into test stand procedure | CP-CAV-INST-TSTD |  | Castagnola | Macha
Test stand Cable connection procedure | CP-CAVPR-CAV-CHK-TSTD |  | Overton | Davis
C100 Radial Wedge Clamp Installation Procedure | CP-C100-RWFC-INST |  | Smith | Castagnola
C100 Waveguide Flange surface repair | CP-C100-WG-REPR-FLNG |  | Daniels | Macha
CMM Program Writing Procedure | CP-SRF-FAC-CMM |  | Carpenter | Williams
C100 Replacing Wireless Thermocouple Data Logging Hardware | CP-C100-EP-HDWR |  | Davenport | Grenoble
Ultrasonic Cavity Wall Thickness Measurement Procedure | CP-C100-CAV-THKM |  | Stirbet | Reilly
String Production Procedures
C100 Beamline Assembly Procedure | CP-C100-CST-CAV-BLN |  | Macha | Castagnola
C100 Cavity String Component | CP-C100-CST-CLN-COMP |  | Davenport | Reilly
C100 Cavity String Tooling Cleaning | CP-C100-CST-CLN-STTL |  | Davenport | Reilly
C100 Cavity String Evacuation and Leak Test Procedure | CP-C100-CST-EVAC |  | Macha | Castagnola
C100 Ion Pump Installation and Starting Procedure | CP-C100-CST-ION |  | Macha | Castagnola
C100 Cavity String Kit List | CP-C100-CST-KIT |  | Macha | Castagnola
Cryomodule Production Procedures
C100 RF Window Welding Procedure | CP-C100-CST-WELD-WWIN |  | Worland | Bennington
C100 Helium Vessel Installation | CP-C100-CAV-INST-HELV |  | Fischer | Hogan
C100 Helium Vessel Welding | CP-C100-CST-WELD-HELV |  | Fischer | Hogan
C100 Cryomodule Alignment | CP-C100-CM-ALGN |  | Fischer | Humphry
C100 Cryomodule Beampipe Assembly/Installation | CP-C100-CM-ASSY-BPIP |  | Bigalow | Page
C100 Cold Tuner Installation Procedure | CP-C100-CM-ASSY-CTNR |  | McCrea | Fischer
C100 Cryomodule Spaceframe Assembly | CP-C100-CM-ASSY-SFR |  | Page | Fischer
C100 Cryomodule Tuner Assembly-Warm | CP-C100-CM-ASSY-TUNW (was CP-C100-CM-ASSY-WTNR) |  | Fischer | McCrea
C100 Cryomodule JT Actuator calibration | CP-C100-CM-CAL-JTAT |  | Campbell | Humphry
C100 Helium Vessel Installation Procedure | CP-C100-CM-INST-HELV |  | Fischer | McCrea
C100 Cryomodule MLI installation | CP-C100-CM-INST-MLI |  | McCrea | Campbell
C100 Cryomodule Secondary Waveguide/Sweep Installation/Removal | CP-C100-CM-INST-WGSP |  | Carpenter | Fischer
C100 Cryomodule Leak check | CP-C100-CM-LKTS |  | Bigalow | Campbell
C100 Cryomodule Endcan Prep | CP-C100-CM-PREP-ENC |  | Fischer
C100 Cryomodule Pressure Test | CP-C100-CM-PRET |  | Bigalow | Fischer
Cryomodule Endcan Alignment | CP-CM-ALGN-ENC |  | Page | Humphry
Cryomodule Warmup in CMTF | CP-CM-CMTF-WARM |  | Worland | Bigalow
Cryomodule U-tube Installation | CP-CM-INST |  | Worland | Bigalow
CM Lifting/Moving to Tunnel | CP-C100-CM-MOVE-CM (was CP-CM-MOVE-CM) |  | Humphry | Worland
CM Lifting/Moving To CMTF | CP-C100-CM-CMTF (was CP-CM-MOVE-CMTF) |  | Humphry | Worland
Preperation for Cryomodule Cooldown in CMTF | CP-CM-PREP-CM |  | Bigalow | Worland
Cryomodule circuit cleanup | CP-CM-PREP-HEHD |  | Worland | Bigalow
Cryomodule Related Operations in the CMTF | CP-CM-OPER-CMTF |  | Fischer | Humphry
Cryomodule Testing Procedures
C100 Maximum Gradient and Operating Gradient Determinations (Tunnel) | CP-C100-COM-CM-CAV-EMAX (was CP-C100-ACC-CM-CAV-EMAX) |  | Drury | Reece/Stirbet
C100 Qo vs. Eacc (Tunnel) | CP-C100-COM-CM-CAV-Qo (was C100-ACC-CM-CAV-QO) |  | Drury | Reece/Stirbet
C100 Cool Down Procedure (Tunnel) | CP-C100-ACC-CM-COOL |  | Hogan | Preble
C100 Swept AM / Dynamic Lorentz | CP-C100-CMTF-CM-CAV-DLRTZ |  | Davis | Drury / (Kirk pick)
C100 Maximum Gradient and Operating Gradient Determinations (CMTF) | C100-CMTF-CM-CAV-EMAX |  | Drury | Reece/Stirbet
C100 Field Emission vs. Eacc (CMTF) | C100-CMTF-CM-CAV-FE |  | Drury | Reece/Stirbet
C100 Qext Measurements (CMTF) | C100-CMTF-CM-CAV-HPRF-QEXT |  | Drury | Reece/Stirbet
HOM survey | CP-C100-CAV-CMTF-HOM |  | Marhauser / Wang
C100 Microphonics | CP-C100-CMTF-CM-CAV-LPRF-MICR (was C100-CMTF-CM-CAV-LPRF-MICR) |  | Davis | Drury / (Kirk pick)
C100 Mechanical Modes | CP-C100-CMTF-CM-CAV-LPRF-MODE |  | Davis | Drury / (Kirk pick)
C100 Passbands Measurements | CP-C100-CMTF-CM-CAV-LPRF-PASS (was C100-CMTF-CM-CAV-LPRF-PASS) |  | Drury | Reece/Stirbet
C100 Pressure Sensitivity | C100-CMTF-CM-CAV-PSNS |  | Drury | Reece/Stirbet
C100 Qo vs. Eacc (CMTF) | C100-CMTF-CM-CAV-QO |  | Drury | Reece/Stirbet
C100 Static Lorentz | CP-C100-CMTF-CM-CAV-SLRTZ (was C100-CMTF-CM-CAV-SLRTZ) |  | Davis | Drury / (Kirk pick)
C100 Mechanical Tuner Resolution | CP-C100-CMTF-CM-CAV-TUNE-MRES |  | Davis | Drury / (Kirk pick)
C100 Mechanical Tuner Range and Hysteresis | CP-C100-CMTF-CM-CAV-TUNE-MRNG (was C100-CMTF-CM-CAV-TUNE-MRNG) |  | Grenoble | Drury / Davis
C100 Piezo Tuner Resolution | CP-C100-CMTF-CM-CAV-TUNE-PRES |  | Davis | Drury / (Kirk pick)
C100 Piezo Tuner Range and Hysteresis | CP-C100-CMTF-CM-CAV-TUNE-PRNG (was C100-CMTF-CM-CAV-TUNE-PRNG) |  | Grenoble | Drury / Davis
C100 Cool Down Procedure (CMTF) | CP-C100-CMTF-CM-COOL |  | Hogan | Preble
C100 CMTF Thermal Shield Static Heat Load Measurement | CP-C100-CM-SHHL |  | Hogan | Preble
C100 Silicon Diode Cryogenic Testing Procedure | CP-C100-CM-INSP-DIO |  | Stirbet | Drury/Davis/Hogan
Cryomodule Shipping Procedures
C100 Commissioning Procedure for 8CAV | CP-C100-CM-COM-8CAV |  | Drury | Hogan

## TRAVELERS
Document Type | Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | From Project? | Revision | Author | Reviewer | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Inventory
Disassembly
| CM Disassembly |  |  |  |  | C100-DISA |  | J.FISCHER
Cavity Preparation
Inspection
Traveler | Cavity CMM Receiving Inspection | P1-INSP-HELV |  |  |  | F100-CAV-INSP-HELV-ASSY | R1 | A. DeKerlegand | T.GANEY | K.DAVIS | A.REILLY | T.GANEY | 2020-07-31 | GANEY,KDAVIS,AREILLY | GANEY,KDAVIS | AREILLY,GEORGED,LZHAO
Traveler | Cavity RF Inspection Receiving Inspection (BEFORE/AFTER) (HEATER CK) | P1-TUNE-CAV-RFIN |  |  |  | F100-CAV-RFIN | R1 | D.FOREHAND | C.DREYFUSS | K.DAVIS | A.REILLY
Chemistry
Traveler | Cavity Degreasing | P1-CHEM-CAV-DEGR |  |  |  | F100-CAV-DEGR | R1 | A.WILDESON | A.ANDERSON | K.DAVIS | A.REILLY |  |  | ashleya,kdavis,ganey,forehand | ashleya,kdavis,ganey | forehand,areilly
Traveler | Cavity Electropolish | P1-CHEM-CAV-EP |  |  |  | F100-CAV-EPOL | R1 |  | A.ANDERSON | K.DAVIS | A.REILLY |  |  | ashleya,kdavis,ganey,forehand | ashleya,kdavis,ganey | forehand,areilly
Traveler | Cavity High Pressure Rinse | P1-CHEM-CAV-HPR |  |  |  | F100-CAV-HPR | R1 | A.WILDESON | A.ANDERSON | K.DAVIS | A.REILLY |  |  | ashleya,kdavis,ganey,forehand | ashleya,kdavis,ganey | forehand,areilly
Traveler | Cavity Flange Lapping | P1-CHEM-CAV-LAP |  |  |  | F100-CAV-LAP | R1 |  | A.ANDERSON | K.DAVIS | A.REILLY |  |  | ashleya,kdavis,ganey,forehand | ashleya,kdavis,ganey | forehand,areilly
Traveler | Cavity Horizontal Electropolish | P1-CHEM-CAV-HEP
Assembly
Traveler | Cavity Assembly | P1-CLNRM-CAV-ASSY |  |  |  | F100-CAV-ASSY | R1 | D.FOREHAND | C.DREYFUSS | K.DAVIS | A.REILLY
Traveler | Helium Vessel Modification | P1-CMA-HELV-REWRK |  |  |  |  | R1 | J.FISCHER | [9 empty] | HV's are already on, consider a modification traveler
Traveler | Transfer to Test Stand & Leak Check | P1-CLNRM-CAV-TSTD |  |  |  | C75-CAV-TSTD | R1 | C.DREYFUSS | D.FOREHAND | K.DAVIS | A.REILLY
Testing
Traveler | VTA HOM | P1-VTA-HOM |  |  |  | F100-CAV-VTA-HOM | R1 | P.OWEN | C.REECE |  | A.REILLY
Traveler | CAVITY VTA TEST | P1-VTA-CAV-HPRF | VTA RF Testing Procedure, Excel Spreafsheet for VTRF Measurements |  |  | F100-CAV-VTA-HPRF | R1 | K.DAVIS | C.REECE |  | A.REILLY
Component Preparation
Inspection
Traveler | Inspection Primary waveguide (COLD) | P1-INSP-WGD |  |  |  | F100-CAV-INSP-WGD | R1 | [10 empty] | C100R-CAV-INSP-WGD
Traveler | Inspection Secondary Waveguide (WARM) & Leak Check | P1-INSP-GVWG |  |  |  | F100-CM-INSP-GVWG | R1 | A. DeKerlegand | [9 empty] | C100R-CM-INSP-GVWG
Traveler | Inspection Recycled Waveguide | P1-INSP-WGD-RCYC |  |  |  | C100R-CAV-INSP-WGD-RCYC | R1 | S.WILLIAMS | L.ZHAO
Traveler | Leak Check Window | P1-CMA-WIN-LEAK |  |  |  |  | R1 | J.FISCHER | S.WILLIAMS
Traveler | RF Testing Ceramic Windows | P1-TUNE-WINCR-RFIN |  |  |  |  | R1 | M.DRURY | [9 empty] | C100-CAV-INSP-ASSY-WIN
Traveler | Inspection Brazement Adapter Assembly | P1-INSP-ADPT |  |  |  | F100-CAV-INSP-ADPT | R1 | S. Williams | K. Macha |  | A. Reilly |  |  | scott,georged,macha | scott,macha,edaly | georged,forehand
Traveler | Inspection RF Window Welded Assembly | P1-INSP-WIN |  |  |  | F100-CAV-INSP-ASSY-WIN | R1 | S. Williams | K. Macha |  | A. Reilly |  |  | scott,georged,macha | scott,macha,edaly | georged,forehand
Traveler | Inspection Double Sided Rectangular Flange | P1-INSP-DSRF |  |  |  | F100-CAV-INSP-FLNG | R1 | S. Williams | K. Macha |  | A. Reilly |  |  | georged,lzhao,scott,macha,areilly | scott,macha,edaly | georged,lzhao
Traveler | Inspection Modified Window | P1-INSP-WINM |  |  |  | F100-CAV-INSP-MWND | R1 | S. Williams | K. Macha |  | A. Reilly |  |  | macha,kdavis,georged,lzhao,areilly | macha,kdavis | georged,lzhao
Traveler | Waveguide and window weldment modification | P1-WELD-WIN-ASSY |  |  |  |  | R1 | K.MACHA | S.WILLIAMS |  | A.REILLY
Chemistry
Traveler | Cavity String Component Cleaning | P1-CHEM-COMP-CLN |  |  |  | F100-CST-CLN-COMP | R1 | A.ANDERSON | K.DAVIS |  | A.REILLY |  |  | ashleya,kdavis,ganey,forehand | ashleya,kdavis,ganey | forehand,areilly
Traveler | Cavity String Tooling Cleaning | P1-CHEM-STTL-CLN |  |  |  |  | R1 | A.ANDERSON
Traveler | Secondary waveguide cleaning | P1-CHEM-GVWG-CLN |  |  |  |  | R1 | A.ANDERSON
| Valve Cleaning | P1-CHEM-VALV-CLN |  |  |  |  | R1
| Component High Pressure Rinse | P1-CHEM-COMP-HPR |  |  |  |  | R1
Assembly
Cavity String
Inspection
Traveler | Inspection Valve ??? | P1-CST-VALV-INSP |  |  |  |  | R1 | D. Forehand
Assembly
Traveler | Cavity String Assembly | P1-CST-ASSY |  |  |  | F100-CST-ASSY-ASO1 | R1 | D.FOREHAND | C.DREYFUSS | K.DAVIS | A.REILLY
| Cavity String Leak Test | P1-CST-LEAK |  |  |  |  | R1
Cryomodule
Inspection
Traveler | Inspection Waveguide Sweeps | P1-CMA-SWEEP-INSP |  |  |  | F100-CM-INSP-SWEEP | R1 | Fischer | K. Macha |  | A. Reilly |  |  | edaly,macha,areilly,fischer | fischer | edaly,macha,areilly
Traveler | Inspection Tophats (Double) | P1-CMA-THTD-INSP |  |  |  | F100-CM-INSP-THTD | R1 | Fischer | K. Macha |  | A. Reilly |  |  | edaly,macha,areilly,fischer | fischer | edaly,macha,areilly
Traveler | Inspection Tophats (Single) | P1-CMA-THTS-INSP |  |  |  | F100-CM-INSP-THTS | R1 | Fischer | K. Macha |  | A. Reilly |  |  | edaly,macha,areilly,fischer | fischer | edaly,macha,areilly
Traveler | Inspection Waveguide Supports | P1-CMA-WSPT-INSP |  |  |  | C100-CM-INSP-WSPT | R1 | Fischer | K. Macha |  | A. Reilly |  |  | edaly,macha,areilly,fischer | fischer | edaly,macha,areilly
Traveler | Inspection Coaxial Cables | P1-TSTMS-COAX-INSP |  |  |  | F100-CM-ASSY-COAX | R1 | L.KING | K. Davis |  | A. Reilly |  |  | king,kdavis,forehand | king,kdavis | forehand
Cryomodule Assembly
Traveler | Cold Mass Assembly | P1-CMAWS2-CMAS-ASSY |  |  |  | F100-CM-ASSY-COLD | R1 | J.FISCHER | K.WORLAND |  | A.REILLY
Traveler | Thermal Shield and Space Frame Assembly | P1-CMAWS3-SFR-ASSY |  |  |  | F100-CM-ASSY-SFR | R1 | J.FISCHER | K.WORLAND |  | A.REILLY
Traveler | Vacuum Vessel and End Can Assembly | P1-CMAWS3-VV-ASSY |  |  |  | F100-CM-ASSY-VV | R1 | J.FISCHER | K.WORLAND |  | A.REILLY
Traveler | Final Cryomodule Assembly | P1-CMAWS4-CM-ASSY |  |  |  | F100-CM-ASSY | R1 | J.FISCHER | K.WORLAND |  | A.REILLY
Traveler | Supply and return beam pipe assemblies | P1-CMAWS4-BPIP-ASSY |  |  |  | C100-CST-ASSY-BPIP | R1 | J.FISCHER | K.WORLAND |  | A.REILLY
Cryomodule Testing
Traveler | Cryomodule Acceptance Test | P1-ACTS-CM |  |  |  | L2PRD-CM-ACTS | R1 | M.DRURY | L.KING | A.SHABALIN | A.REILLY
Cryomodule Installation & Commissioning
Traveler | Cryomodule Tunnel Installation | P1-ACC-CM-INST |  |  |  |  | R1 | M.DRURY
Traveler | Cryomodule Commissioning | P1-ACC-CM-COMM |  |  |  | C100R-CM-COMM | R1 | M.DRURY
Standard Project Travelers
Traveler | Detours, Deviations and Discrepancies (D3) | P1-D3 | [5 empty] | V.BOOKWALTER
Traveler | Inspection Summary Report | P1-INSR | [5 empty] | V.BOOKWALTER
Traveler | Inspection Nonconformance Report | P1-NCR | [5 empty] | V.BOOKWALTER
sent to author for editing
Waiting Approval
Late
in production

## Notes
No BCP
CAVFLG rewrite; has double indium seal
new EP machine so traveler / procedure updates needed
CAV-ASSY
CAV-LEAK separate
CAM-MODIFY J.Fischer to write; in CMA
primary waveguide is the cold or CST waveguide
secondary waveguide is the warm or CM GVWG both are J.Fischer's
2 versions of GVWG - how to create in travelers
RF INSP Ceramic window
cold gate valves INSP under CST like F100 versions (reuse?)
Tiffany Ganey is the CAV Process Engr for this project
CST-ASSY
CST-LEAK
GVWG-ASSY
GVWG-LEAK
65 -> CM
Chg CONNECTOR to FEEDTHRU for L.King
CMTF-PREP has setup and cooldown
CMTF-ACTS testing traveler
need ACC travelers
GVWG-INSP
GVWG-CHEM
GVWG-HEAT

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## TRAVELERSold
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A

## F100
Traveler Id | Rev No | Traveler Name | Author | Date
F100-CAV-ASSY | R1 | F100 Cavity Assembly | Kurt Macha | 13-Apr-2012
F100-CAV-ASSY2 | R1 | F100 Cavity Assembly, Evacuation, and Leak Test | Kurt Macha | 13-Apr-2012
F100-CAV-BAKE | R1 | F100 Cavity Bake-out | Kurt Macha | 13-Apr-2012
F100-CAV-DEGR | R1 | F100 Cavity Degrease | Jim Follkie | 12-Jun-2012
F100-CAV-EPOL | R1 | 7 Cell Cavity Electropolish with Cavity Cooling System | Jim Follkie | 09-Jul-2012
F100-CAV-HPR | R1 | HPR F100 Cavities | James Davenport | 06-Jul-2012
F100-CAV-INSP-ADPT | R1 | F100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 30-May-2012
F100-CAV-INSP-ASSY-WIN | R1 | F100 RF Window Welded Assembly Inspection Traveler | HyeKyoung Park | 30-May-2012
F100-CAV-INSP-FLNG | R1 | F100 Double Sided Rectangular Flange Receiving Inspection Traveler | HyeKyoung Park | 30-May-2012
F100-CAV-INSP-FPFT | R1 | F100 Field Probe Feedthru Receiving Inspection | Brian Carpenter | 13-Jul-2012
F100-CAV-INSP-HELV-ASSY | R1 | F100 Helium Vessel Weldment Assembly Inspection | Brian Carpenter | 24-May-2012
F100-CAV-INSP-HMFT | R2 | F100 HOM Probe Feedthru Receiving Inspection | Brian Carpenter | 06-Dec-2012
F100-CAV-INSP-MWND | R1 | F100 Modified Window Inspection | Katherine Wilson | 24-Sep-2012
F100-CAV-INSP-WGD | R1 | Receiving Inspection - F100 Upgrade Waveguides | Katherine Wilson | 17-Jul-2012
F100-CAV-LAP | R2 | F100 Cavity Flange Lapping | Isiah Daniels | 15-Jan-2013
F100-CAV-NCR | R7 | Non-Conformance Report | M. Jones | 20-Aug-2012
F100-CAV-RFIN | R1 | F100 Cavity RF Incoming Inspection Traveler | R.Overton | 04-May-2012
F100-CAV-RWRK-WGD | R1 | Rework - F100 Upgrade Waveguides | Katherine Wilson | 17-Jul-2012
F100-CAV-VTA-COOL | R1 | F100 Cavity VTA Cooldown | T. Bass | 17-May-2012
F100-CAV-VTA-HOM | R1 | F100 Cavity VTA HOM Survey | T. Bass | 17-May-2012
F100-CAV-VTA-HPRF | R1 | F100 Cavity VTA High Power RF Test | T. Bass | 17-May-2012
F100-CM-ASSY | R1 | F100 Cryomodule Final Assembly Traveler | John Fischer | 15-Aug-2012
F100-CM-ASSY-COAX | R1 | F100 Coaxial Cables Receiving Inspection | L. King | 03-Sep-2013
F100-CM-ASSY-COLD | R1 | F100 Cold Mass Assembly | John Fischer | 03-May-2012
F100-CM-ASSY-SFR | R1 | F100 Thermal Shield and Spaceframe Assembly | John Fischer | 12-May-2012
F100-CM-ASSY-VV | R1 | F100 Vacuum Vessel and End Can Assembly | John Fischer | 12-May-2012
F100-CM-CRYO-ACTS | R1 | F100 Cryomodule Acceptance Test - Cryocycle | M. Drury | 13-May-2014
F100-CM-DISA | R1 | Admiral-F100-Disassembly Traveler | John Fischer | 24-Feb-2012
F100-CM-HPRF-ACTS | R1 | F100 Cryomodule Acceptance Test ¿ High Power Testing | M. Drury | 13-May-2014
F100-CM-INSP-GVWG | R1 | F100 Guard Vacuum Waveguide | Katherine Wilson | 17-Jul-2012
F100-CM-INSP-IMAG | R1 | Receiving Inspection of F100 Cryomodule Inner Magnetic Shield | Gary Cheng | 18-Jul-2012
F100-CM-INSP-OMAG | R1 | Receiving Inspection of F100 Cryomodule Supply/Return End Can and Center Magnetic Shield | Gary Cheng | 20-Jul-2012
F100-CM-INSP-RENC | R1 | Receiving Inspection for F100 Return End Can | Brian Carpenter | 15-Aug-2012
F100-CM-INSP-SENC | R1 | Receiving Inspection for F100 Supply End Cans | Brian Carpenter | 24-Jul-2012
F100-CM-INSP-SWEEP | R1 | F100 Waveguide Sweeps | Katherine Wilson | 17-Jul-2012
F100-CM-INSP-THTD | R1 | F100 Tophats (Double) | Katherine Wilson | 27-Oct-2013
F100-CM-INSP-THTS | R1 | F100 Tophats (Single) | Katherine Wilson | 27-Oct-2013
F100-CM-LPRF-ACTS | R1 | F100 Cryomodule Acceptance Test ¿ Low Power RF Measurements | M. Drury | 13-May-2014
F100-CST-ASSY-ASO1 | R1 | F100 cavity string assembly traveler | Kurt Macha | 13-Apr-2012
F100-CST-ASSY-BPIP | R1 | F100 Supply and return beam pipe assemblies | Kurt Macha | 18-Jul-2012
F100-CST-ASSY-WGD | R1 | F100 Waveguide sub-assembly and leak test traveler | Kurt Macha | 01-May-2012
F100-CST-CLN-COMP | R1 | F100 cavity string component cleaning | Teena Harris | 06-Jul-2012
F100-D3 | R1 | Detours, Deviations and Discrepancies (D3) | V. Bookwalter | 15-Jan-2010
F100-INSR | R1 | Inspection Summary Report | M. Jones | 27-Apr-2012
F100-NCR | R7 | Non-Conformance Report | V. Bookwalter | 07-Sep-2011

## C100
Traveler Id | Rev No | Traveler Name | Author | Date
C100-CAV-ASSY | R3 | C100 Cavity Assembly | Steve Castagnola | 31-May-2011
C100-CAV-ASSY2 | R3 | C100 Cavity Assembly, Evacuation, and Leak Test | Steve Castagnola | 13-May-2011
C100-CAV-BAKE | R2 | C100 Cavity Bake-out | Kurt Macha | 16-May-2011
C100-CAV-CHEM | R1 | C100 BCP | Teena Harris | 19-Apr-2010
C100-CAV-D3 | R1 | D3s for CAVITY processing | V. Bookwalter | 15-Jan-2010
C100-CAV-DEGR | R3 | C100 Cavity Degrease | James Davenport | 15-Apr-2011
C100-CAV-EPOL | R2 | 7 Cell Cavity Electropolish with Cavity Cooling System | James Davenport | 15-Apr-2011
C100-CAV-HEAT | R1 | C100 Cavity Heat Treatment | D. Forehand | 24-May-2010
C100-CAV-HPR | R2 | HPR C100 Cavities | James Davenport | 15-Apr-2011
C100-CAV-INSP | R3 | Receiving inspection for C100 Cavities | Brian Carpenter | 20-Apr-2010
C100-CAV-INSP-ADPT | R4 | C100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 25-Aug-2011
C100-CAV-INSP-ASSY-WIN | R3 | C100-CAV-INSP-ASSY-WIN | HyeKyoung Park | 25-Aug-2011
C100-CAV-INSP-CTUN | R1 | C100 Cold Tuner Receiving Inspection | J. Matalevich | 15-Feb-2010
C100-CAV-INSP-CTUN2 | R1 | C100 Cold Tuner Expanded Inspection | J. Matalevich | 25-Feb-2010
C100-CAV-INSP-FLNG | R2 | C100 Double Sided Rectangular Flange Receiving Inspection Traveler | HyeKyoung Park | 03-Feb-2011
C100-CAV-INSP-FPF | R1 | C100 Field Probe Feedthrough Inspection Traveler | Kurt Macha | 06-Jul-2010
C100-CAV-INSP-GVWF | R2 | C100 Guard Vacuum Waveguide Flange Receiving Inspection Traveler | Katherine Wilson | 01-Sep-2010
C100-CAV-INSP-HEHD | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Cryogenic Circuit Components | Gary Cheng | 01-Jun-2010
C100-CAV-INSP-HELV | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel | Gary Cheng | 20-Apr-2010
C100-CAV-INSP-HMFT | R6 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 25-Aug-2011
C100-CAV-INSP-IMAG | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Inner Magnetic Shield | Gary Cheng | 19-Jul-2010
C100-CAV-INSP-THRM | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule 50K Thermal Shield Components | Karl Smith | 24-Feb-2010
C100-CAV-INSP-VV | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 24-Jun-2010
C100-CAV-INSP-WGD | R6 | Receiving Inspection - 12 GeV Upgrade Waveguides | Katherine Wilson | 15-Mar-2011
C100-CAV-INSP2 | R3 | C100 Cavity CMM Post-tuning Inspection | Brian Carpenter | 29-Sep-2010
C100-CAV-INST-HELV | R2 | C100 Helium Vessel Installation Traveler | John Fischer | 24-Aug-2010
C100-CAV-LAP | R2 | C100 Cavity Flange Lapping | Isiah Daniels | 19-Nov-2010
C100-CAV-LAP-THAT | R1 | C100 Top Hat Flange Lapping | Isiah Daniels | 14-Mar-2011
C100-CAV-NCR | R7 | Non-Conformance Report | V. Bookwalter | 07-Sep-2011
C100-CAV-RFIN | R2 | C100 Cavity RF Incoming Inspection Traveler | D. Forehand | 22-Nov-2010
C100-CAV-RWRK-WGD | R4 | Rework - 12 GeV Upgrade Waveguides | Katherine Wilson | 14-Feb-2011
C100-CAV-THKN | R1 | C100 (CEBAF 12 GeV cryomodule upgrade) Cavity wall US thickness measurements | M. Stirbet | 26-Apr-2010
C100-CAV-TUNE | R4 | C100 Cavity Tuning Traveler | D. Forehand | 28-Mar-2011
C100-CAV-VTA-COOL | R1 | C100 (CEBAF 12 GeV cryomodule upgrade) Cavity VTA Cooldown | T. Bass | 02-May-2011
C100-CAV-VTRF | R4 | C100 (CEBAF 12 GeV Cryomodule Upgrade) Vertical cavity Testing | M. Stirbet | 15-Nov-2011
C100-CM-ASSY | R1 | C100 Cryomodule Final Assembly Traveler | John Fischer | 10-May-2011
C100-CM-ASSY-COAX | R1 | C100 Coaxial Cables Assembly and Qualification | L. King | 05-Sep-2013
C100-CM-ASSY-COLD | R4 | C100 COLD MASS ASSEMBLY | John Fischer | 03-Oct-2011
C100-CM-ASSY-SFR | R1 | C100 Thermal Shield and Spaceframe Assembly | John Fischer | 23-Feb-2011
C100-CM-ASSY-VV | R1 | C100 Vacuum Vessel and End Can Assembly | John Fischer | 10-May-2011
C100-CM-COMM | R1 | C100 Cryomodule Commissioning | Michael Drury | 29-Dec-2012
C100-CM-CRYO-ACTS | R1 | C100 Cryomodule Acceptance Test - Cryocycle | M. Drury | 21-Jun-2011
C100-CM-DIS-HELV | R1 | C100 Helium Vessel Removal Traveler | John Fischer | 10-Dec-2009
C100-CM-HPRF-ACTS | R1 | C100 Cryomodule Acceptance Test - High Power Testing | M. Drury | 22-Jun-2011
C100-CM-INSP-10FT | R1 | Receiving Inspection for 10 PIN DOUBLE ENDED CONNECTOR, used as vacuum vessel electrical feedthrough for C100 cryomodule. | John Fischer | 10-Dec-2010
C100-CM-INSP-19FT | R1 | Receiving Inspection for 19 PIN CONNECTOR, used as vacuum vessel electrical feedthrough for C100 cryomodule. | John Fischer | 10-Dec-2010
C100-CM-INSP-32FT | R1 | Receiving Inspection for 32 PIN CONNECTOR, used as vacuum vessel electrical feedthrough for C100 cryomodule. | John Fischer | 10-Dec-2010
C100-CM-INSP-CTUN | R1 | C100 Cold Tuner Receiving Inspection | J. Matalevich | 15-Feb-2010
C100-CM-INSP-CTUN2 | R1 | C100 Cold Tuner Expanded Inspection | J. Matalevich
C100-CM-INSP-DIO | R1 | C100 Si Diodes Receiving Inspection | M. Stirbet | 23-Feb-2011
C100-CM-INSP-ELFT | R2 | Receiving Inspection for 12GeV 8 pin Cryogenic Feedthrus | John Fischer | 03-May-2018
C100-CM-INSP-GVWG | R1 | 12 GeV Guard Vacuum Waveguide | Katherine Wilson | 15-Feb-2011
C100-CM-INSP-HEHD | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Cryogenic Circuit Components | Gary Cheng | 01-Jun-2010
C100-CM-INSP-HELV | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel | Gary Cheng | 20-Apr-2010
C100-CM-INSP-HVHD | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel Head Assemblies | Gary Cheng | 19-Oct-2010
C100-CM-INSP-IMAG | R3 | Receiving Inspection of 12GeV Upgrade Cryomodule Inner Magnetic Shield | Gary Cheng | 13-Jan-2011
C100-CM-INSP-INFF | R1 | Receiving Inspection - Instrumentation Feedthrough Flange | Joshua Feingold | 01-Nov-2010
C100-CM-INSP-NTFT | R1 | Receiving Inspection for 12GeV- ¿N-TYPE VacuumVessel Feedthrus | John Fischer | 14-Dec-2010
C100-CM-INSP-OMAG | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Outer Magnetic Shield | Gary Cheng | 10-May-2011
C100-CM-INSP-OMAGS | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Secondary Outer Magnetic Shield | Gary Cheng | 27-Apr-2011
C100-CM-INSP-RENC | R1 | Receiving Inspection for C100 End Cans | Brian Carpenter | 09-Sep-2010
C100-CM-INSP-RTBP | R1 | C100 Return Beam Pipe Receiving Inspection | J. Matalevich | 15-Dec-2010
C100-CM-INSP-SENC | R1 | Receiving Inspection for C100 Supply End Cans | Brian Carpenter | 27-Sep-2010
C100-CM-INSP-SFR | R1 | C100 Space Frame Receiving Inspection | J. Matalevich | 15-May-2010
C100-CM-INSP-SUBP | R1 | C100 Supply Beam Pipe Receiving Inspection | J. Matalevich | 15-Dec-2010
C100-CM-INSP-SWEEP | R1 | 12 GeV Waveguide Sweeps | Katherine Wilson | 22-Feb-2011
C100-CM-INSP-THRM | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule 50K Thermal Shield Components | Karl Smith | 26-Aug-2010
C100-CM-INSP-TPHTD | R1 | 12 GeV Tophats (Double) | Katherine Wilson | 14-Feb-2011
C100-CM-INSP-TPHTS | R1 | 12 GeV Tophats (Single) | Katherine Wilson | 31-Jan-2011
C100-CM-INSP-VPFT | R1 | Receiving Inspection for 12GeV Sapphire Viewport | John Fischer | 06-Dec-2010
C100-CM-INSP-VV | R3 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 26-Mar-2010
C100-CM-INSP-WSPT | R1 | 12 GeV Waveguide Supports | Katherine Wilson | 31-Jan-2011
C100-CM-INSP-WTUN | R1 | C100 Warm Tuner Receiving Inspection | J. Matalevich | 15-Aug-2010
C100-CM-INST | R1 | C100 CRYOMODULE TUNNEL INSTALLATION | Frank Humphry | 21-Jul-2010
C100-CM-LPRF-ACTS | R1 | C100 Cryomodule Acceptance Test ¿ Low Power RF Measurements | M. Drury | 22-Jun-2011
C100-CST-ASSY-ASO1 | R2 | C100 cavity string assembly traveler | Kurt Macha | 11-Feb-2011
C100-CST-ASSY-BPIP | R1 | C100 Supply and return beam pipe assemblies | Kurt Macha | 25-Apr-2011
C100-CST-ASSY-WGD | R1 | C100 Waveguide sub-assembly and leak test traveler | Kurt Macha | 06-Jun-2010
C100-CST-CLN-COMP | R1 | C100 cavity string component cleaning | James Davenport | 25-Aug-2010
C100-CST-CLN-STTL | R1 | C100 cavity string tooling cleaning | James Davenport | 25-Aug-2010
C100-D3 | R1 | D3s for Cryomodule Processing (NOT cavity) | V. Bookwalter | 15-Jan-2010
C100-INSR | R1 | Inspection Summary Report | Brian Carpenter | 04-Mar-2005
C100-NCR | R10 | Non-Conformance Report for Multiple Reworks | BOOKWALT | 26-Feb-2018

## C100R
Traveler Id | Rev No | Traveler Name | Author | Date
C100R-CAV-ASSY | R2 | C100R Cavity Assembly | Alex Wildeson | 06-Nov-2018
C100R-CAV-ASSY-HELV | R1 | C100R Helium Vessel Installation Traveler | J. Fischer | 09-Jan-2019
C100R-CAV-CHEM-COMP | R1 | C100 components cleaning | A. Anderson Mitchell | 05-Feb-2019
C100R-CAV-CHEM-HPR | R1 | Standard Traveler for Cavity High Pressure Rinse Processing | Ashley Mitchell | 04-Dec-2018
C100R-CAV-CHEM-USC | R1 | C100R Cavity Degrease | Ashley Mitchell | 04-Dec-2018
C100R-CAV-DISA | R3 | C-100R Cavity Disassembly | A. Wildeson | 28-Nov-2018
C100R-CAV-INSP | R1 | Receiving inspection for C100R Cavities | A. DeKerlegand | 30-Nov-2018
C100R-CAV-INSP-HMFT | R2 | C100R Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 23-Jan-2019
C100R-CAV-INSP-WGD | R1 | Receiving Inspection - 12 GeV Upgrade Waveguides | S. Williams | 16-Jan-2019
C100R-CAV-INSP-WGD-RCYC | R1 | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | S. Williams | 25-Jan-2019
C100R-CAV-INSP-WIN-RCYC | R1 | C100RWindow Recycled Visual Inspection | S. Williams | 16-Jan-2019
C100R-CAV-INST-HELV | R1 | C100R Helium Vessel Installation Traveler | J. Fischer | 29-Nov-2018
C100R-CAV-LAP | R2 | C100R Cavity Flange Lapping | C. Johnson | 29-Nov-2018
C100R-CAV-RFIN | R1 | C100R Cavity RF Incoming Inspection Traveler | A. Wildeson | 05-Dec-2018
C100R-CAV-RWRK-WGD | R1 | Rework - 12 GeV Upgrade Waveguides | G. DeKerlegand | 21-Feb-2019
C100R-CAV-TUNE | R1 | C100R Cavity Tuning Traveler | D. Forehand | 06-Nov-2018
C100R-CAV-VTRF | R1 | C100R (CEBAF 12 GeV Cryomodule Upgrade) Vertical cavity Testing | M. Stirbet | 06-Nov-2018
C100R-CM-ACTS | R1 | C100R Cryomodule Acceptance Test ¿ Cryocycle | M. Drury | 28-Oct-2019
C100R-CM-ASSY | R1 | C100R Cryomodule Final Assembly Traveler | J. Fischer | 22-Jan-2020
C100R-CM-ASSY-COLD | R1 | C100R COLD MASS ASSEMBLY | John Fischer | 25-Feb-2019
C100R-CM-ASSY-SFR | R1 | C100R Thermal Shield and Spaceframe Assembly | John Fischer | 04-Mar-2019
C100R-CM-ASSY-VV | R1 | C100R Vacuum Vessel and End Can Assembly | John Fischer | 05-Mar-2019
C100R-CM-COMM | R1 | C100R Cryomodule Commissioning | M. Drury | 25-Oct-2019
C100R-CM-DISA | R1 | C100R Disassembly Traveler | John Fischer | 24-Sep-2018
C100R-CM-INSP-GVWG | R2 | 12 GeV Guard Vacuum Waveguide | A. DeKerlegand | 15-Jan-2019
C100R-CST-ASSY | R1 | C100R Cavity String Assdembly Traveler | D. Forehand | 01-Feb-2019
C100R-CST-ASSY-LEAK | R1 | C100R Cavity string leak test | Danny Forehand | 27-Feb-2019
C100R-CST-ASSY-WGD | R1 | C100R Waveguide sub-assembly and leak test traveler | D. Forehand | 07-Feb-2019
C100R-D3 | R1 | Detours, Deviations and Discrepancies (D3) | V. Bookwalter | 08-Jul-2013
C100R-INSR | R1 | Inspection Summary Report | G. DeKerlegand | 21-Mar-2016
C100R-NCR | R10 | Non-Conformance Report for Multiple Reworks | BOOKWALT | 26-Feb-2018

## R100
Traveler Id | Rev No | Traveler Name | Author | Date
R100-CAV-ASSY | R1 | R100 Cavity Assembly | Steve Castagnola | 07-Jun-2010
R100-CAV-ASSY2 | R1 | R100 Cavity Assembly, Evacuation, and Leak Test | Steve Castagnola | 08-Jun-2010
R100-CAV-BAKE | R1 | R100 Cavity Bake-out | Kurt Macha | 12-May-2010
R100-CAV-CHEM | R1 | R100 BCP | Teena Harris | 21-Jun-2010
R100-CAV-D3 | R1 | Detours, Deviations and Discrepancies (D3) | M. Jones | 29-Jun-2010
R100-CAV-DBFL | R2 | R100 Cavity Cell Grinding and Finishing | S. Manning | 21-Sep-2010
R100-CAV-DEGR | R2 | R100 Cavity Degrease | James Davenport | 06-Dec-2010
R100-CAV-EBWA | R2 | Cavity Completion | S. Manning | 11-Oct-2010
R100-CAV-EPOL | R1 | 7 Cell Cavity Electropolish with Cavity Cooling System | James H. Davenport II | 21-Jun-2010
R100-CAV-FORM | R2 | Cavity Deep Draw Forming Procedures | S. Manning | 10-Sep-2010
R100-CAV-FPBA | R1 | Field Probe End Group HOM Beampipe EB Welding and Machining | S. Williams | 24-Mar-2010
R100-CAV-FPC | R1 | FPC End Group EB Welding and Machining | S. Williams | 24-Mar-2010
R100-CAV-FPCC | R1 | Cavity FPC End Group Completion | S. Williams | 24-Mar-2010
R100-CAV-FPCH | R1 | FPC End Group HOM beampipe EB Welding and Machining | S. Williams | 24-Mar-2010
R100-CAV-FPEG | R1 | Cavity Field Probe End Group Completion | S. Williams | 24-Mar-2010
R100-CAV-HCEL | R1 | Cavity Half-cell Inspection and Initial Chemistry Cleaning Prior to EBW | S. Williams | 25-Mar-2010
R100-CAV-HCEL | R2 | Cavity Half-cell Inspection and Initial Chemistry Cleaning Prior to EBW | S. Manning | 09-Sep-2010
R100-CAV-HEAT | R1 | R100 Cavity Heat Treatment | D. Forehand | 17-Jun-2010
R100-CAV-HOM | R1 | HOM Coupler EB Welding and Assembly | S. Williams | 25-Mar-2010
R100-CAV-HPR | R1 | HPR R100 Cavities | Sarah Tipton | 21-Jun-2010
R100-CAV-INSP | R1 | Receiving inspection for R100 Cavities | Brian Carpenter | 17-Jun-2010
R100-CAV-INSP-ADPT | R1 | R100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 27-Jul-2010
R100-CAV-INSP-ASSY-WIN | R3 | R100-CAV-INSP-ASSY-WIN | HyeKyoung Park | 16-Nov-2010
R100-CAV-INSP-FLNG | R1 | C100 Double Sided Rectangular Flange Receiving Inspection Traveler | HyeKyoung Park | 29-Jul-2010
R100-CAV-INSP-HMFT | R3 | R100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 09-Sep-2010
R100-CAV-INSP2 | R1 | R100 Cavity CMM Post-tuning Inspection | Brian Carpenter | 17-Jun-2010
R100-CAV-INST-HELV | R1 | R100 HELIUM VESSEL INSTALLATION TRAVELER | John Fischer | 24-Aug-2010
R100-CAV-LAP | R2 | R100 Cavity Flange Lapping | Isiah Daniels | 02-Dec-2010
R100-CAV-LLDB | R2 | Cavity Dumbbell Fabrication and Tuning | S. Manning | 21-Sep-2010
R100-CAV-NCR | R6 | Non-Conformance Report | V. Bookwalt | 29-Jun-2010
R100-CAV-THKN | R1 | R100 Cavity Wall US Thickness Measurements | M. Stirbet | 23-Jun-2010
R100-CAV-TUNE | R2 | R100 Cavity Tuning Traveler | D. Forehand | 17-Nov-2010
R100-CAV-VTRF | R1 | R100 (CEBAF 12 GeV cryomodule upgrade) Vertical cavity Testing | M. Stirbet | 21-Jul-2010
R100-CM-ASSY | R1 | R100 Cryomodule Final Assembly Traveler | John Fischer | 18-Apr-2011
R100-CM-ASSY-COLD | R1 | R100 Cold Mass Assembly | John Fischer | 24-Apr-2010
R100-CM-ASSY-SFR | R1 | R100 Thermal Shield and Spaceframe Assembly | John Fischer | 16-Jun-2010
R100-CM-ASSY-VV | R1 | R100 Vacuum Vessel and End Can Assembly | John Fischer | 18-Jun-2010
R100-CM-COMM | R1 | R100 Cryomodule Commissioning | Michael Drury | 13-Mar-2013
R100-CM-CRYO-ACTS | R1 | R100 Cryomodule Acceptance Test | M. Drury | 19-Jan-2011
R100-CM-HPRF-ACTS | R1 | R100 Cryomodule Acceptance Test | M. Drury | 19-Jan-2011
R100-CM-LPRF-ACTS | R1 | R100 Cryomodule Acceptance Test | M. Drury | 19-Jan-2011
R100-CST-ASSY-ASO1 | R1 | C100 cavity string assembly traveler | Kurt Macha | 30-Nov-2010
R100-CST-ASSY-WGD | R1 | R100 Waveguide sub-assembly and leak test traveler | Kurt Macha | 10-Jun-2010
R100-CST-CLN-COMP | R1 | R100 cavity string component cleaning | James Davenport | 25-Aug-2010
R100-CST-CLN-STTL | R1 | R100 cavity string tooling cleaning | James Davenport | 25-Aug-2010
R100-D3 | R1 | Detours, Deviations and Discrepancies (D3) | V. Bookwalter | 26-Mar-2010
R100-INSR | R1 | Inspection Summary Report | M. Jones | 29-Jun-2010
R100-NCR | R6 | R100 Non-Conformance Report | M. Jones | 29-Jun-2010